## Sheet1
VISION NG PROJECT TEAM DASHBOARD
Process Flow
Next Window Group (Business Driven Priority) | [13 empty] | This dashboard will be managed and updated by BSA Lead
| Priority | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | [7 empty] | This is where we will place the list of next windows to be grouped in to delivery sprnts
Priority can be added if there is a need from users to deliver certain windows first or if we need it to
This is not a Sprint schedule. It’s a business preferred delivery order
This list is a working list and idealy will always have list of windows to put in to spring next
| Each Sprint is a Main AR. Subtasks per window in the sprint |  |  | Subtask title will contain Sprint #. Ex: SG2 Calendar List - w_ct_m_cal_list
Next Sprint Windows (CTS sizing of Sprint)
Sprint # | Subtask | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | Dev | BSA | Days to QA |  |  |  |  | During weekly project planning meeting, leadership meets and finalize this
SG2 VISAR-7418 | VISAR-7419 | 8 | CALENDARING | Calendar List | w_ct_m_cal_list | Medium | [7 empty] | Sprint Group(SG) # will be assigned and Dev/BSA will be assigned.
| VISAR7420 | 8.1 | CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | [7 empty] | Any internal windows can be grouped into a sprint if needed but otherwise will not follow the 2 week deadline path
| VISAR-7421 | 9 | CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | NV | CL | [5 empty] | Internal window does not need to be planned. Dev Lead can request BSA Lead to place a window in the pipeline and assign to a dev.
| VISAR-7422 | 9.1 | CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | NV | CL | [5 empty] | BSA Lead creates the JIRA and assigns Subtasks
| VISAR-7423 | 9.2 | CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | NV | CL | [5 empty] | BSA Lead creates the QA defect log and adds the link to JIRA subtask
SG3 VISAR-7400 | VISAR-7401 | 10 | CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | CN | CL
| VISAR-7424 | 11 | CALENDARING | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | Medium |  |  |  | Might be taken out |  |  |  | New rules and how it impacts current workflow
| VISAR-7425 | 12 | CALENDARING | Court Closure Transfer | w_ct_m_cal_close_transfer | Low High | [7 empty] | A main VISAR will be created per Sprint Group. Internal windows will have it's own Master Internal AR.
| VISAR-7426 | 13 | CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | [7 empty] | Subtask will be created and assigned from the Sprint AR - No change to how Dev/BSA work currently
| VISAR-7427 | 14 | CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | [7 empty] | Subtask title will lead with SG#. Consider that your priority. Always work on lower SG item first.
Hold | VISAR - 7417 | 159 | GENERAL | Simple Case Search | w_ct_r_simple_search | Med High | NV
Hold |  | 58 | GENERAL | Advanced Case Search | w_ct_r_case_search | Med | NV
In Flight
Sprint # | Subtask | # | Menu Group | Window / Subscreen Name | Status | Grouping | Dev | BSA | Open Defects | Defect Log |  |  |  | Once window is in flight, BSA Lead will deliver a daily progress report. Dev Lead ensures continual delivery
SG2 | VISAR-6315 | 53 | COURTROOM | Minutes | QA 2 - In Test | Medium High | SM | BY | 84 | Link |  |  |  | Status will have additional descriptions:
Hold | VISAR-6907 | 33 | COLLECTIONS | FTBCOD Interface | On Hold | High | NV | CC |  | Link |  |  |  | Assigned : Assigned to dev. Not in progress
|  | 34 |  | FTBCOD Payment Processor |  | Medium-High |  | CC | [5 empty] | In development : Indicates the window is being developed. Trigger when Subtask moves into in progress
Internal | VISAR-7296 | 124 | TABLES | Agency X-Ref Maintenance | QA 2 - In test | Low High | CN | BY | 3 | Link
Internal | VISAR-7311 | 131 | TABLES | Court Holidays | QA 1 - In Test | Low High | CN | BY |  | Link
Internal | VISAR-7312 | 1 | ADMIN | Auto Process Schedule | QA 1 - In Mitigation | Low High | JC | BY | 14 | Link
Internal | VISAR-7332 | 2 | ADMIN | Date of Action | In Development | Low | CN | DC |  | Link
Internal | VISAR-7368 | 123 | SECURITY | Agency Codes | In Development | Medium | NV | BY |  | Link
Internal |  | 147 | TABLES | Unit Codes | In Development | Medium | SM | CL |  | Link
SG2 | VISAR-7421 | 9 | CALENDARING | Calendar Report | In Development | Medium | NV | CL
SG2 | VISAR-7422 | 9.1 | CALENDARING | Calendar Batch Print | In Development | Medium high | NV | CL
SG2 | VISAR-7423 | 9.2 | CALENDARING | Web Browser of generated files | In Development | Low High | NV | CL
Hold | VISAR - 7417 | 159 | GENERAL | Simple Case Search | On Hold | Med High | NV
Committed Delivery Windows (Timer On)
Sprint # | Subtask | # | Target Date to UAT | Window / Subscreen Name | Status | Grouping | Dev | BSA | Open Defects | Defect Log |  |  |  | When a window in Spring Grouping goes through first QA test and is back in Dev's queue, 2 week timer starts.
SG1 | VISAR-7012 | 25 | 2026-09-22 | Priors | QA 3 - In Mitigation | High | JL | MU
SG1 | VISAR-7215 | 90 | 2026-09-22 | JBSIS Maintenance | QA 1 - In Test |  | NV | DC
SG1 | VISAR-7188 | 55 | 2026-09-28 | Exhibit List | QA 2 - In test | Low-Medium | JL | DC
|  | 55.1 |  | Exhibit List Case Search
Internal SG1 | VISAR-7206 | 57.1 | Deploy with SG1 | Exhibit Management Search | QA 2 - In Mitigation | Low | NV | DC
SG1 |  | 57.2 | 2026-09-28 | Exhibit History | QA 2 - In Mitigation
InternalSG1 |  | 57.3 | Deploy with SG1 | Exhibit Disposition Notice | QA 2 - In Mitigation
Internal SG1 | VISAR-7189 | 56 | Deploy with SG1 | Exhibit Maintenance | QA 2 - In Test | High | SM | DC
Internal SG1 |  | 56.1 | Deploy with SG1 | New Exhibit Hearing LIst |  | High
Internal SG1 | VISAR-7185 | 57 | Deploy with SG1 | Exhibit Management | QA 1 - In Mitigation | High | NV | DC
Sent to UAT
Sprint # | VISAR | # | Subtask to UAT date | Window / Subscreen Name | Actual UAT Start date | Sign off Date | PDC Notes | [6 empty] | Windows that has passed QA and should go to UAT shows here (When BSA moves the subtask from In QA to In UAT
PDC comments (Internal note) on when the actual UAT Starts on the subtask. (ex. UAT started 9/14/26)
PDC updates subtask to Ready for deployment when signed off
PDC adds comments (internal note) if UAT window has bugs to address. (ex. "UAT Fix bug logged" or "UAT Bug Cleared")
UAT Bugs will be discussed during team meetings
To Be Deployed (To Build Planning Process)
Sprint # | VISAR | # | Menu Group | Window / Subscreen Name |  |  | Dev | BSA | [5 empty] | Next deployment windows will show here.
SG1 | VISAR-7189 | 56 | EXHIBITS | Exhibit Maintenance |  |  | SM | DC | [5 empty] | Should be 1 sprint group and internal window but can reconsider build packaging depending on what we have signed off
|  | 56.1 | EXHIBITS | New Exhibit Hearing LIst
SG1 | VISAR-7188 | 55 | EXHIBITS | Exhibit List |  |  | JL | DC
|  | 55.1 |  | Exhibit List Case Search
SG1 | VISAR-7185 | 57 | EXHIBITS | Exhibit Management |  |  | NV | DC
SG1 | VISAR-7206 | 57.1 | EXHIBITS | Exhibit Management Search |  |  | NV | DC
|  | 57.2 |  | Exhibit History
|  | 57.3 |  | Exhibit Disposition Notice
SG1 | VISAR-7215 | 90 | JBSIS | JBSIS Maintenance |  |  | NV | DC
Tracked Metrics | [8 empty] | Dates | [8 empty] | Hours
Sprint # | Status | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | Dev | BSA | Date Assigned | To 1st QA | Estimate vs Actual | 2 Week start | Date to UAT | UAT Start | Signed Off | Deployed | Build # | Development | QA Test | Mitigation | UAT
SG1 | In UAT | 56 | EXHIBITS | Exhibit Maintenance | w_ct_m_case_package_list | High | NV | DC | 2026-09-01 | 2026-09-03 |  | 2026-09-06 | 2026-09-14 | 2026-09-16 | 2026-09-25 | 2026-10-01 | NG 5.05 | 23 | 13 | 22 | 9
Daily Reports
Sprint # | VISAR | # | Menu Group | Window / Subscreen Name | Status | Grouping | Dev | BSA | Activity Report |  |  |  |  | Analysis and Insight
SG1 | VISAR-7185 | 57 | EXHIBITS | Exhibit Management | QA 2 - In Mitigation | High | NV | DC | - 9/8/2026 09:50 AM: DC logged 4 hours - 9/8/2026 10:00 AM: Moved from QA back to Dev - 9/8/2026 01:00 PM: Moved from Unit test to QA - 9/8/2026 01:05 PM: Assigned to DC - 9/8/2026 04:39 PM: David Chang - we need to discuss defect # 11 |  |  |  |  | - Open bug count is 12. -20 since last Update - 5 Days to 2 week deadline remaining
SG1 | VISAR-7215 | 90 | JBSIS | JBSIS Maintenance | QA 1 - In Test | Mid | JL | CC | - No Activity |  |  |  |  | - No activity on this for 3 Days - Open bug count is 22. No change since last Update - 6 Days to 2 week deadline remaining
Internal | VISAR-7332 | 2 | ADMIN | Date of Action | In Development | Low | SM | BY | - 9/8/2026 11:00 AM: Subtask Created - 9/8/2026 11:05 AM: Subtask assigned - 9/8/2026 01:00 PM: Subtask moved to in Progress - 9/8/2026 05:00 PM: SM logged 3 hours
Sprint Map
Sprint # | Main AR | #Sub | Overall Status
SG1
SG2
SG3
SG4
| Role | Initial | Name
| BSA | DC | David Chang
| DEV | JC | JinLiang Tony Chen
| DEV | CN | Chris Nguyen
| Lead BSA | CC | Joonho Chris Chang
| Lead DEV | JL | Jorge Lichtenstein
| DEV | MC | Menekou Coulibaly
| PDC | MU | Melanie Uyehara
| DEV | SM | Santiago Morales
| DEV | KH | Kyeng Kenny Hwang
| DEV | SS | Sameer Sarangi
| DEV | NV | Nathan Vuong
| BSA | CL | Cung Le
| BSA | BY | Brooke Yale

## Sheet2
Hours
Date | Initials | Dev | QA | Defect Mitigation | UAT
Dashboard Status | Meaning | How to derive
On Hold | Placed on Hold until further action taken | JIRA status is on hold
Backlog | Placed in backlog to work on when no more work in active queue | JIRA Status is Backlog
In Development | Indicates initial development is in progress | When JIRA status moves into Subtask in progress AND never went to In QA status before
In QA - BSA | The window is currently in QA being tested | When JIRA subtask moves to In QA status
In QA - Dev | The window has been tested and is under defect mitigation by developer | When JIRA subtask moves from In QA to In Progress
In UAT | The window is released for UAT by Business SMEs | JIRA status is In UAT
Ready for deployment | The window has been signed off by users and is ready to be deployed | JIRA Status is Ready for Deployment