Purpose: To build a process and automate it to keep track of my project, named Vision NG, for metrics and statuses to be published to a shared dashboard.

Background: We are on a large project to migrate a legacy case management system for the Orange County Superior Court from Powerbuilder app to a modern Blazor stack with Syncfusion library. The project is currently in flight, passed the pilot stage and transitioning to a sprint based project management. To support the deadline tracking and metric reporting, I need to create a dashboard where each task is tracked for status changes, along with key date and hours metrics for the team to reference and be informed.

Project Stages: The project has 6 stages.

- Priority Planning: This is a prioritization stage. It’s an offline process to place 200+ legacy windows in order of business’s preference of being migrated.

- Sprint Planning: This is also a human decision process where we get a set of prioritized windows and break them down to sprints of about 4 windows, depending on complexity. When sprint grouping is determined, Lead Developer designates the developer and Lead BSA designates the BSA to be assigned. Lead Developer also adds LOE of the window. When everything is determined, Lead BSA creates a JIRA Subtask for each window and assigns to the team.

- In Development: This is the stage where analysis, design, coding, unit testing and peer review is done by developers. The subtask for this window stays in this stage until it is delivered to QA and finishes first round of testing. By default, when the window is done with first round of testing , regardless of having defects or not, will be moved to next stage, which is 2 week countdown to UAT. Developer has the option to request for extension during daily meeting if there is a legitimate reason such as technical blockers or vacations.

- Committed to UAT Date: This stage is where subtasks with 2 week to UAT countdown is tracked. Windows in this stage must meet the delivery deadline as business SME to UAT test the windows will be scheduled.

- Sent to UAT: This is the stage where subtasks in UAT will show. We have a role called PDC (Project Delivery Coordinator) who manages the UAT process until signed off. All Subtasks in UAT or signed off will remain in this stage until we have a build date.

- To Be Deployed: Once a build date is determined, Subtasks that’s signed off and belongs to a defined sprint group will get moved to this stage and removed when deployment is completed.

How we manage the project tasks in JIRA

- This project got started within an existing JIRA project and does not have it’s own project space. This is the URL https://ocsuperiorcourt.atlassian.net/jira/servicedesk/projects/VISAR

- Currently, all subtasks for windows are tracked as a subtask in a single main task (We call it Main AR) within this project.  VISAR-6166

- We will now change this to have following rules:

  - A sprint will have it’s own Main AR and each window within the sprint will be a subtask of that Main AR. When spring planning is done, a Main AR for each sprint will be created and subtasks belonging to that sprint will be added there

  - We have configuration and maintenance windows meant only for internal technical users. These windows will not go through the 2week countdown or UAT. VISAR-7398 is the Main AR where all subtasks for internal windows will be created

  - When we find bugs or need patches after deployment, we need to create a subtask to track the patches. This will be created under the Main AR designated for Post Deployment Patches: VISAR-7396

  - If the window is not part of user facing window sprint, they will not be part of the sprint. Those will use “Internal” and “Patch” as their Sprint # in the dashboard.

Things we need to keep track of are below. All other automations and features will either add rows to this or use the data in here to display in the dashboard.

For every window/subtask, we need to keep track of following columns in the Master Tracking Sheet:

- Sprint #: Sprint numbers are represented as “SG”. Sprint 1 =  SG01, Sprint 2 = SG02 etc. Sprint numbers are assigned only for prioritized user facing windows. For internal windows, Sprint # will be “Internal” and for Post deployment Patches, sprint # will be “Patch”

- Main AR: JIRA Task ID of the Main AR

- Subtask: JIRA task ID of the subtask

- W#: This is the window id #. We assigned an ID to every window in the application. Below url is the location of the excel sheet where all the window master inventory is listed: https://occourts.sharepoint.com/:x:/r/sites/Vision_ILJ/General%20Documentation/Knowledge%20Sharing%20Documents/Vision%20Team%20Knowledge/Vision%20NG%20-%20Grouping/VISAR-4987%20Vision%20NG%20-%20Grouping.xlsx?d=w6fda12de80dc4949b5badbc92d3d24d1&csf=1&web=1&e=nWxaIa

- Menu Group: It’s taken directly from the inventory master. Indicates which menu group the window belongs to

- Window Name: Also taken from the inventory master. Indicates the actual name of the window

- Object Name: Object name of the window. Taken from the inventory master

- Status: Status of where the window currently is. JIRA subtask status is used to determine it but how it is represented in the dashboard will be different to better inform the team.

| Dashboard Status | Meaning | How to derive |
| --- | --- | --- |
| On Hold | Placed on Hold until further action taken | JIRA status is on hold |
| Backlog | Placed in backlog to work on when no more work in active queue | JIRA Status is Backlog |
| In Development | Indicates initial development is in progress | When JIRA status moves into Subtask in progress status AND never went to In QA status before |
| In QA - BSA | The window is currently in QA being tested | When JIRA subtask moves to In QA status |
| In QA - Dev | The window has been tested and is under defect mitigation by developer | When JIRA subtask moves from In QA to In Progress |
| In UAT | The window is released for UAT by Business SMEs | JIRA status is In UAT |
| Ready for deployment | The window has been signed off by users and is ready to be deployed | JIRA Status is Ready for Deployment |

- QA Cycle: Is the number of QA – mitigation cycles the window went through. When the subtask first goes to In QA, that is QA Cycle 1. When dev is fixing the defects, that is still QA Cycle 1 but in Dev’s mitigation status. When the Subtask goes to In QA for second time, we up the # to QA Cycle 2. So Cycle = number of movements to In QA.

- Grouping: Taken from inventory master. It is a complexity level of the window

- Dev: Assigned developer.

- BSA: Assigned BSA for testing

- Date Started: Date when subtask moved to Subtask in Progress for first time

- To QA: Date when subtask first moved to In QA

- 2 Week Start: Date the subtask went into 2 week countdown to UAT. By default it moves to 2 week countdown after 1st QA testing is done and subtask is moved back into In Progress.

- Target Date : Date subtask started 2 week countdown plus 2 weeks

- To UAT: Date the subtask moved to In UAT

- UAT Start: Actual date UAT started with SME – PDC will add a comment in internal notes when UAT starts

- Signed Off: Date UAT is signed off for window. PDC will comment on the internal notes of JIRA subtask when the window is signed off

- Deployed: Date of deployment. Will be provided by user when deployment is Scheduled

- Build #: Version number of the application for this deployment. Will be provided by the user when deployment date is set

- LOE to QA: Determined by Dev lead during sprint planning. Will be used to refine our estimations by comparing to actual. Will be provided by user during Sprint Planning

- Development: Hours spent on initial development before QA. There is a time logging sheet in the description section of the subtask where Devs, BSAs, PDC all logs the hours they worked on a date by category. Tally the Development hours column.

- QA Test: Same as development hours but tally the QA Test column

- Mitigation: Same but tally the Mitigation column

- UAT: Same. Tally the UAT column

- Open Defects:  Count of rows in the defect log with defect status of “New”, “Return to Dev” and “Retest in Progress”.

- Total Defects: Count of all defects in the defect log. Defect logs are located in https://occourts.sharepoint.com/:f:/r/sites/Vision_ILJ/General%20Documentation/Knowledge%20Sharing%20Documents/Vision%20Team%20Knowledge/Vision%20NG%20-%20Grouping/QA%20Defect%20Logs?d=wdb028acb549a4cae812993467ec5a7d1&csf=1&web=1&e=B982sW

This is a complete roster of the project Team.

Initials will be used for entering Dev and BSAs but JIRA assigning will need actual names. Use below table as roster.

| Role | Initial | Name |
| --- | --- | --- |
| BSA | DC | David Chang |
| DEV | JC | JinLiang Tony Chen |
| DEV | CN | Chris Nguyen |
| Lead BSA | CC | Joonho Chris Chang |
| Lead DEV | JL | Jorge Lichtenstein |
| DEV | MC | Menekou Coulibaly |
| PDC | MU | Melanie Uyehara |
| DEV | SM | Santiago Morales |
| DEV | KH | Kyeng Kenny Hwang |
| DEV | SS | Sameer Sarangi |
| DEV | NV | Nathan Vuong |
| BSA | CL | Cung Le |
| BSA | BY | Brooke Yale |

Following are workflows and automations to be built

Workflow 1: Add windows to Priority Planning list

- When I prompt to add window # 50 to 60,  or ask  #5, 6, 7.1, 9, 23, 32 as next priority, grab the corresponding window details from inventory master and add to the list with next priority number on the list. It should include columns for

  - Priority

  - W#

  - Menu Group

  - Window Name

  - Object Name

  - Grouping

Workflow 2: Move windows to Sprint Planning – This is to move the prioritized windows into Sprint planning worksheet so lead Dev can determine how to scope the sprints, which dev to assign to and estimate LOE to QA.

- When prompted to move priority 1 windows or priority 2 to 4 windows to sprint planning, Add the window to Sprint Planning list.

- When in Sprint Planning, grey out the corresponding windows in Priority Planning

- Sprint Planning list should have following columns:

  - Sprint # - Leave Blank

  - Main AR – Leave Blank

  - Subtask – Leave Blank

  - W#

  - Menu Group

  - Window Name

  - Object Name

  - Grouping

  - Dev – Leave Blank

  - BSA – Leave Blank

  - LOE to QA – Leave Blank

Workflow 3: Assign Sprints – When Sprint Planning is done, all the columns in the sprint planning sheet will be filled except Main AR and Subtask. This workflow will create the subtasks and assign into our pipeline.

- When prompted to inject or initiate a sprint # in the Sprint Planning sheet,

- Confirm all fields have valid answers except Main AR and Subtask left blank

- If missing any of the fields, inform the user it can’t initiate due to missing field

- When fields are validated, Create a Main AR for the Sprint #.

  - Title naming convention: “SG## - Sprint ## Master”

  - Department is *Vision Internal Only

  - Supervisor / Manager is Sendhivel Anandhajothi

  - Global Approval = No Global Impact

  - In the description, list the W#, Window name and object name of all windows under the sprint.

  - Assignee should always be Joonho Chang

  - Leave all else as is

- Create subtask per window under the Main AR within the sprint

  - Subtask Title naming convention: SG## - [Window Name] – [Object name]

  - Create an empty defect log in the same folder where all defect logs are in with Naming convention of “Defect Log_SG##_[Window Name]”. Use this template https://occourts.sharepoint.com/:x:/r/sites/Vision_ILJ/General%20Documentation/Knowledge%20Sharing%20Documents/Vision%20Team%20Knowledge/Vision%20NG%20-%20Grouping/QA%20Defect%20Logs/QA%20Defect%20Log%20-%20Template.xlsx?d=we15c485875e6419187a681bca552d707&csf=1&web=1&e=pDZrYF

  - Add the link to the defect log in the description of each subtask so team can navigate to it easily

  - Add Dev identified in the Sprint plan as Assignee

  - Add Both the dev and BSA as Project Team. Devs know who their BSA counterpart is by looking at the project team.

  - Add a table like below in the description. It is meant to be used as an hour logging sheet. When any resource works on the subtask, they need to edit the description, enter in the date, initials and hours they worked under the right category and save

| Hours |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Date | Initials | Dev | QA | Defect Mitigation | UAT |

- Once the Main AR and subtask has been created and assigned, Grey out the assigned windows from Sprint Planning

- Add the new subtasks to Master Tracking to be tracked going forward.

Workflow 4: Refresh Master Tracking sheet – For updating all the columns to latest info

When prompted to refresh the master tracking, update the updatable fields in the master tracking sheet.

- For all subtasks undeployed, meaning it doesn’t have a deployed date, grab the status move history any internal notes and Hour log data from the subtask

- Also check the defect log and tally the defect counts for open and total

- Using the data gathered, update the applicable dates, Hours, defects and Dashboard status etc as defined in the Master tracking sheet definitions.

- Maintain a history trail doc of what has been changed over time for every window. This will be used to audit and roll back any changes made if incorrect

- Until I say to stop, output the change action summary on what rows and fields this will update and get confirmation from me. Apply changes when approved.

Workflow 5: Publish Dashboard

When prompted to refresh or publish the dashboard, update or recreate a dashboard in a self contained html page with following sections and columns and cosmetic features

Dashboard Title: Vision NG Project Dashboard

Last Refresh On : Date and Time in PST when dashboard last refreshed

Section 1: In Development

  - Sprint #

  - Subtask – Link to actual JIRA subtask

  - W# - Link to open the master inventory sheet. Opens to the row where this number is on without scrolling

  - Menu Group

  - Window Name

  - Status

  - Grouping

  - Dev

  - BSA

  - Open Defect

  - Total Defects

  - Link to defect log

Section 2: Committed to UAT – Use default trigger.  Move from In QA to In Progress for the first time

  - Sprint #

  - Subtask – Link to actual JIRA subtask

  - W# - Link to open the master inventory sheet. Opens to the row where this number is on without scrolling

  - Target Date (Days) – Display the date it needs to get to UAT by add remaining number of days in parenthesis as “D-##”)

  - Window Name

  - Status

  - Grouping

  - Dev

  - BSA

  - Open Defect

  - Total Defects

  - Link to defect log

Section 3: Sent to UAT

  - Sprint #

  - Subtask – Link to actual JIRA subtask

  - W# - Link to open the master inventory sheet. Opens to the row where this number is on without scrolling

  - To UAT – Add in parenthesis how many days under or over target date. Red if late Green if on or before

  - Window Name

  - Dev

  - BSA

  - UAT Start

  - Signed Off

  - Window Name

  - Object Name

  - Dev

  - BSA

  - UAT Start

  - Signed Off

  - Build #

Other commands/skills:

- User will prompt to do a QA cycle exception on a window or subtask. If so, place the  subtask or window that just went into 2 week countdown back into In Development until In QA moves to In Progress again.

- User will prompt to do an extension with number of additional days for windows already in 2 week countdown. If so, add the specified number of days to the Target Date

- User can inject an Internal or Patch window directly to In Development section. User will prompt “assign internal [window name] or [W#] to [Initial] and [Initial]”

  - If so, create a subtask under the Internal Master AR, using the same steps for Sprint subtasks and assign

  - Add the row to Master Tracking

  - Same apply to Patch but use the PATCH Master AR to create subtask

  - These will not go through 2 week countdown or UAT. When BSA tests during QA and is good, BSA will move the subtask from In QA to Ready for Deployment.

My Initial Goal: To run this process within an AI coding tool like Codex with scheduled automation for Workflow 4 and workflow 5 every couple hours. The dashboard to be published as a self contained html file, saved in one drive and accessible by my team members via Sharepoint page with embedded html from one drive.

My environment: I have my workstation connected to work VPN with Zscaler security. I have license to use power automate. I have MS Teams as my main chat and communication tool. I have admin access to a sharepoint site. I have OneDrive as shared drive with my team. I want to avoid making any deployments to a web server or request config change to our infra team for now.