## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-08-18 | Both | UI | Minor | Resolved | Agency, Ref Category fields | X button location in field | 1. Open window 2. Select Agency dropdown 3. Type search criteria - X clear button is located in the middle of the field rather than right edge | See Violations window Statute dropdown for reference | 2026-09-01 | Pass |  | fixed
2 | 2026-08-20 | Both | Functionality | Minor | Resolved | Agency, Ref Category fields | F3 Refresh does not select the default options | 1. Open window 2. Select values for Agency and/ or Ref Category dropdowns 3. F3 Refresh - previous selection remains. Expected behavior is for the defaults to be selected. | UI Guideline 54 | 2026-09-01 | Pass |  | fixed
3 | 2026-08-20 | Both | Functionality | Major | Resolved | Court Value, Ref Value | Cells with spaces only have validation errors | PB window allows fields with spaces only. NG has a validation message | See Agency DOJ, Ref Category Court Disposition Type for translation for DOJ, Court Value CIPTDO in CRMD | 2026-09-01 | Pass |  | fixed
4 | 2026-08-25 | Both | Functionality | Minor | Resolved | Agency, Ref Category fields | Search field does not have character limit | Dropdown search character limit should be 30. See Bail Schedule Maintenance / Bail Schedule Review | BSA will determine the character limit window by window | 2026-09-01 | Pass |  | fixed
5 | 2026-08-25 | Both | UI | Major | Resolved | Agency, Ref Category fields | Incorrect field flashes when pending changes "Yes" is selected | 1. Open Agency/ Ref Category with rows 2. Add, update, or delete a row 3. Switch the Agency or Ref Category - user receives Pending Changes message 4. Select "Yes" - while updates are loading for the selected field, the field flashes to the old field, and sometimes ends the load displaying the old field |  | 2026-09-01 | Pass with Comments | This fix might be related to Defect 7 | fixed
6 | 2026-08-26 | Both | Functionality | Minor | Resolved | Agency, Ref Category fields | Incorrect field displays when switching tabs | 1. Follow Defect 5 steps 2. Open another Vision window - NG or PB 3. Switch back to NG tab - the agency/ ref category field where changes were made appears instead of the last selected value |  | 2026-09-01 | Pass |  | fixed
7 | 2026-09-01 | Both | Functionality | Regression | Resolved | Agency, Ref Category fields | Incorrect fields displays when cancelling pending changes | 1. Open Agency/ Ref Category with rows 2. Add, update, or delete a row 3. Switch the Agency or Ref Category - user receives Pending Changes message 4. Select "Cancel" - child record remains, but the Agency/ Ref Category selection changes to the new selection. Expect the old selection to return. If I click anywhere on the window after selecting Cancel, the Old selection does return |  | 2026-10-14 | Pass |  | fixed
8 | 2026-09-01 | Both | Functionality | Minor | Return to Dev | F3 Refresh | Pending Changes message removes focus | Window loses focus after Pending Changes message option is selected. This occurs regardless of the selection Yes, No, Cancel |  | 2026-10-14 | Fail | 10/14 BY: Defect is not addressed | fixed
9 | 2026-09-01 | Both | UI | Minor | Resolved | N/A | Resizing window does not stack | Tile Vertical and Tile Horizontal Views should add scroll bars and stack the sections as needed to fit the reduced window size | See Violations with Violation Summary tab selected for resizing reference | 2026-10-14 | Pass
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## SUMMARY
QA Cycle 1: 3.5 HR
Count of Status | Status
Scenario Type | New | Grand Total
Functionality | 4 | 4
UI | 2 | 2
Grand Total | 6 | 6
QA Cycle 2: 1 HR
Count of Status | Column Labels
Row Labels | New | Resolved | Grand Total
Functionality
Major |  | 1 | 1
Minor | 1 | 3 | 4
Regression | 1 |  | 1
UI
Major |  | 1 | 1
Minor |  | 1 | 1
Grand Total | 2 | 6 | 8

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action