## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-08-26 | Both | UI | Minor | Resolved | Process Date | Missing Seconds | Process Date column is missing seconds in the timestamp |  | 2026-10-14 | Pass |  | Fixed
2 | 2026-08-26 | Both | UI | Minor | Resolved | Process Seq Nbr | Format includes comma | UI Guidelines state to have numbers right aligned. This PB window uses commas. |  | 2026-10-14 | Pass |  | Fixed
3 | 2026-08-26 | Both | UI | Major | Return to Dev | Top Section | Entering edit mode when the window is scrolled to the right shifts the view left | 1. Open window 2. Scroll right 3. Double click any row - the scroll bar shifts left. expected result is the view stays locked where the scroll bar was | Will discuss during 8/31 standup. if possible, place cursor where user double clicked. otherwise don't place cursor so the view does not shift. See court control with expanded columns for reference. |  |  |  | Fixed
4 | 2026-08-26 | Both | Functionality | Major | Resolved | Process Status, Dt Status, Retval Out, Message Out, Parms Out | Columns do not update after job is executed | 1. Select Execute button 2. Select Yes - bottom section updates as expected. Process Status, Dt Status, Retval Out, Message Out, Parms Out values do not update with the latest job information |  | 2026-10-14 | Pass |  | Fixed
5 | 2026-08-26 | Both | UI | Minor | Resolved | Description, Message Out, Parms Out | Tooltip | Tooltip should be enabled for Description, Message Out, Parms Out, and all editable text fields | Similar changes were added to Court Control since we could not wrap the text | 2026-10-14 | Pass |  | Fixed
6 | 2026-08-26 | Both | UI | Minor | Resolved | Top Section | Ctrl + F split screen | 1. APS and any other vision window 2. Window > Tile Vertical view 3. Click the top section of APS 4. Ctrl + Shift + F 5. Type a search with no valid results - a blank blue section appears at the top | See Screenshot 6 | 2026-10-14 | Pass |  | Fixed
7 | 2026-08-26 | Both | UI | Minor | Return to Dev | Process ID | Process ID fluent validation is cut off on the left side | See Screenshot 7 |  | 2026-10-14 | Fail | 10/14 BY: Defect has not been addressed | Fixed
8 | 2026-08-27 | Both | UI | Minor | Return to Dev | Bottom section columns - Process Date, Description, Process Sp | Column Filters cut off | Column Filters for Process Date, Description, and Process Sp are cutoff at the bottom. Expected result is for the column filters to go outside of the grid. If needed, a scroll bar can be added to the window like we did for SP Registry | UI Guideline 40 | 2026-10-14 | Fail | 10/14 BY: Defect has not been addressed | Fixed by Jorge's push for another screen on the base component
9 | 2026-08-28 | Both | UI | Minor | Resolved | N/A | Page Up/ Down lands in middle | Page Up/ Page Down lands in the middle of the page instead of the top | See SP Registry page up/ page down | 2026-10-14 | Pass |  | Fixed
10 | 2026-08-28 | Both | Functionality | Minor | Resolved | Description | Optional field is marked as required | Description field is required and has fluent validation. PB window allows Description to be empty. | CRMD killsess process ID is an example with a blank description | 2026-10-14 | Pass |  | Fixed
11 | 2026-08-28 | Both | Functionality | Major | Resolved | Cancel Button | Cancel button closes the window | 1. Open window 2. Select Cancel button - PB closes the APS window. NG refreshes the window |  | 2026-10-14 | Pass with Comments | See defect 17 | Fixed
12 | 2026-08-28 | Both | Functionality | Minor | Return to Dev | F3 Refresh | Window loses focus after execute | 1. Click a row 2. Select Execute button 3. Select yes on the popup 4. Select OK on the batch job completed validation message 5. F3 refresh - refresh does not work since the window loses focus. Clicking the window then F3 refresh works as expected |  | 2026-10-14 | Fail | 10/14 BY: Defect has not been addressed | Fixed
13 | 2026-08-28 | Both | UI | Minor | Resolved | Active Ind | Checkbox does not display correctly in Edit mode | 1. Enter edit mode for any row 2. Check, or uncheck, the Active Ind checkbox - changes do not show while in edit mode 3. Exit edit mode - Active Ind changes are visible | This was a bug with a Syncfusion update that was previously addressed in SP registry | 2026-10-14 | Pass |  | Fixed
14 | 2026-09-01 | Both | UI | Minor | Return to Dev | N/A | Resizing window does not stack | Tile Vertical and Tile Horizontal Views should add scroll bars and stack the sections as needed to fit the reduced window size. Execute and Cancel buttons are also not visible or reachable when the window is minimized | Have 3 windows for Tile Vertical issue, and 2 for Tile Horizontal Issue | 2026-10-14 | Fail | 10/14 BY: Tile Vertical is fixed. Tile horizontal is not.
15 | 2026-09-01 | Both | UI | Minor | Resolved | N/A | Blank area in split screen | 1. Select a job with no recent runs, ie bottom section says "No records to display" 2. Open another NG or PB window 3. Window > Tile Vertical - Blank space above the bottom section appears. This space disappears if the child row has data | Similar to Defect 6 issue. This occurs when there are no records to display rather than Ctrl + Shift + F | 2026-10-14 | Pass
16 | 2026-10-14 | Both | UI | Minor | New | Process ID, Process Seq Nbr, Active Ind, Process Status, Dt Status, Retval Out, Parms Out, Dt. Updated | Column Titles cut off | Column titles Process ID, Process Seq Nbr, Active Ind, Process Status, Dt Status, Retval Out, Parms Out, and Dt. Updated are cut off. Since this is a scroll
17 | 2026-10-14 | Both | UI | Minor | New | Cancel Button | Remove the cancel button | Remove the cancel button from APS window. Decision made to remove all "Close" buttons from NG windows
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42

## Summary
QA Cycle 1 : 4 HR
Count of Status | Column Labels
Row Labels | New | Grand Total
Functionality
Major | 2 | 2
Minor | 2 | 2
UI
Major | 1 | 1
Minor | 8 | 8
Grand Total | 13 | 13

## Screenshots
ID | Screenshot
6 | Defect | Expected
7
15

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action