## DEFECTS
ID | Date Reported | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | ST5.0.2 | BSA Comments | Dev Comments
1 | 2026-03-12 | Both | UI | Minor | Resolved | General | 4k Monitor Window Resolution | Borders around sections are larger than sections | Should the data sections within the borders be dynamic? | 2026-04-14 | Pass | Pass | 03/13 - Dev to review/address 03/25 - still occurring 04/14 - issue resolved | sm - css issue will look into 4/7/2026 fixed
2 | 2026-03-12 | Both | UI | Minor | Resolved | Violation | Highlight on initial load | Highlight is missing on first violation after opening window | 03/13 - devs to address | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - make first selected | side note on dropdown options when they are empty.
3 | 2026-03-12 | Both | UI | Minor | Resolved | Violation | Search field | Alignment of text is bottom right of search field | currently, the empty ones are put at the bottom, however | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - look into filter | currently, the empty ones are put at the bottom, however
4 | 2026-03-12 | Both | Functionality | Major | No Action | Violation | Scroll Latency | When using mouse wheel, same violations appear in scroll. Once user stops, then the window momentarily displays loading window then displays violations; same occurs if user clicks scroll bar and drags quickly |  |  | Pass with Comments |  | 03/13 - leave as-is | sm - occurs because grid is virtual. Needs further discussion | other windows have it as the first option. Need to standardize
5 | 2026-03-12 | Both | UI | Minor | Resolved | Violation | Gradient display for read-only rows | Remove gradient blue and replace with solid blue as these are read-only rows | UI Guidelines #40: search field should be cleared and not reappear with previously entered search; should behave as if user just used enter key | 2026-03-25 | Pass with Comments |  | 03/13 - Dev to review/address 03/25 - see ID 30 | 3/13 SM - has been addressed. solid blue/white added
6 | 2026-03-12 | Both | Functionality | Major | Resolved | Violation | Search field retains previous search with F3 Refresh | 1. Enter violation in search field (e.g. PC 11) 2. Select violation towards bottom of list (e.g., PC 1192.7(c)(25)) 3. F3 Refresh window 4. Violations do not display; Bail Schedule & Bail Schedule Qualifier sections remain for selected violation in Step 1 (ID 16) 5. Go to search field and use Enter keypress 6. Search field reappears/searches with data entered in Step 1 | UI Guidelines #40: search field should be cleared and not reappear with previously entered search; should behave as if user just used enter key | 2026-04-14 | Pass | Fail | 03/13 - Dev to review/address 03/25 - Steps 1-4 resolved; 5-6 still occurring 04/11 - all steps resolved as old filter does not reappear | sm - looks like the filter is still not being removed on refreshing. Will look into 4/7/2026 unable to replicate 4/10: JL to filter nothing so that ENTER does not bring back old filter
7 | 2026-03-12 | Both | Functionality | Minor | Resolved | Violation | Search Field Character Limit | NG - no character limit; PB - 30 characters |  | 2026-04-14 | Pass |  | 03/13 - Dev to review/address 04/14 - regression test pass
8 | 2026-03-12 | Both | UI | Minor | No Action | Violation | Search Field/Scroll bar | When no search executed scroll bar appears with an empty blue cell above it; when search executed and results are less than section height, scroll bar disappears and empty blue cell disappears (e.g. VC 23152(a)) |  |  | Pass with Comments |  | 03/13 - leave as-is
9 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule | Effective Date | 01/01/1900 returns "Effective date must be a valid date" FluentValidation | 01/01/1900 should save as it is a valid date for date range | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - reduce min date to 12/31/1899 max to 01/01/2100
10 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule | Delete button | Red button and "Delete" text appears right justified slightly | Confirm button color as this is new scenario; text should be centered (appears right justified) | 2026-04-14 | Pass |  | 03/13 - devs to address centering of text; leave button as red 04/14 - regression test pass | sm - looks right aligned bcz set width is being applied as a style. Removing width = 75px aligns it but increases width by 8px
11 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule | Post Amount/POC | FluentValidations are covering fields |  | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - try doing ct control FV DependentRules() or onBlur
12 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule | POC | FluentValidation states that an amount is required | PA Dist Sched: PC 11412, PC 115(a) Bail Dist Sched: PC 115(a) | 2026-04-14 | Pass |  | 03/13 - devs to address to default field to $0.00 04/14 - regression test pass
13 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule | PA Dist Schedule dropdown height briefly expands when changing view | There is a brief expansion/reduction in PA Dist Schedule dropdown when toggling between violations |  | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - add padding to reason grid 2nd
14 | 2026-03-12 | Both | UI | Minor | No Action | Bail Schedule | FluentValidation Green highlight appears on fields not edited | PA Dist Sched: PC 11412, PC 115(a) Bail Dist Sched: PC 115(a) | Fields are highlighted green but no changes were made to these cells; display looks as though it is passing FVs without modifications | 2026-03-25 | Pass with Comments |  | 03/13 - to be reviewed later
15 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule | Bail Dist Sched & PA Dist Sched bolded dropdowns | PA Dist Sched: PC 11412, PC 115(a) Bail Dist Sched: PC 115(a) When viewing dropdowns, options are all bolded | Should the dropdowns be bolded? | 2026-04-14 | Pass |  | 03/13 - bold to remain; add underline to mandatory fields; add empty row to PA Dist Sched and Bail Dist Sched dropdowns 04/14 - regression test pass | sm - bolded occurs because the dropdown was modified. Besides that, please elaborate on previous ^
16 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule | PA Dist Sched | Formal Probation selection code is cut off | Increase Bail Schedule column width so that this field is slightly expanded | 2026-04-07 | Pass |  | 03/13 - devs to address 03/25 - issue still occurring 04/07 - issue resolved | sm - increate ddm option width bcz code is cut off. ie 'FMLP...'
17 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule | FluentValidations appearing to early | Enter Dt Effective and tab or click to next cell triggers the following: - Number of Priors is required - Post Amt is required - POC Amount is required | Update to only display FV when user leaves cell and fails FV | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass
18 | 2026-03-12 | Both | UI | Minor | No Action | Bail Schedule Qualifier | Spacing of first/last rows | Reduce spacing above Qualifier type and below Added section | Match spacing used between Qualifier/Value rows | 2026-03-25 | Pass with Comments |  | 03/13 - devs to address 03/25 - issue still occurring 04/10 - no action - any further reduction will show partial 6th row and then break navigation | sm - will look into. css related 4/7/2026 reduced and now fits 5 records any further reduction and will show partial 6th row and then navigation wont work right
19 | 2026-03-12 | Both | UI | Minor | Resolved | Bail Schedule Qualifier | Qualifier text updates to black after exiting edit mode | Should remain dark blue when exiting edit mode |  | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - only modify the input box not the qualifier text? maybe rm text box for label
20 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule Qualifier | Added in initial bail schedule row creation - does not save | If user adds BSQ at the time of creating bail schedule row, bail schedule row saves but none of the qualifiers save |  | 2026-04-14 | Pass | Pass | 03/13 - devs to address 04/06 - issue sporadically occurs, latest was on 4/6 - screenshot of error message attached 04/14 - regression test pass | sm - insert is failing 4/7/2026 fixed
21 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule Qualifier | Added after bail schedule row creation - does not save | User adds BSQ after creating bail schedule row, receives this message: Error saving Bail Schedule See Details... ORA-20000: 46001^-1^cta_bail_sched_qlfr_ins^ ORA-06512: at "COURT.CTW_BAIL_SCHEDULE_QUALIFIER", line 146 ORA-06512: at line 1 https://docs.oracle.com/error-help/db/ora-20000/ | If user adds BSQ at the time of creating bail schedule row, bail schedule row saves but none of the qualifiers save | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - insert is failing
22 | 2026-03-12 | Both | Functionality | Minor | Resolved | Bail Schedule Qualifier | View retained after save | If user is at bottom of Bail Schedule Qualifiers and saves, view remains at bottom of bail schedule qualifiers after save | Shouldn't view reset to show top of BSQ section? | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - reset focus to top of grid?
23 | 2026-03-12 | Both | Functionality | Major | Resolved | Violation | F3 Refresh triggers "No records to display" Highlight placement in OL column only | 1. Scroll down and select violation (e.g. PC) 2. Refresh window 3. Violations display "No records to display" after refresh 4. Click in Violations search field 5. User Enter keypress 6. Violations reappear and highlight only appears on the OL | Expect refresh to display first row highlighted with corresponding Bail Schedule row / associated BSQs | 2026-04-14 | Pass |  | 03/13 - Dev to review/address 04/14 - regression test pass | sm - this issue is related to ID#6. Issue is filtering is not being reset on refresh.
24 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule & Bail Schedule Qualifier | F3 Refresh does not reset columns | 1. Scroll down and select violation (e.g. PC) 2. Refresh window 3. Bail Schedule and Bail Schedule Qualifier sections remain for selected violation in Step 1 4. User scrolls in Violations search field - no highlight on violation selected in Step 1 | Expect refresh to display first row highlighted with corresponding Bail Schedule row / associated BSQs when refresh occurs - should not display previous data | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass | sm - this issue is related to ID#2. highlighting first row on refresh add on base grid
25 | 2026-03-12 | Both | Functionality | Major | Resolved | Violation & Bail Schedule Qualifier | PgUp/PGDn Keypress & Up/Down arrow keypress fail | F7/F8/F10/F11 keypresses work, however the PgUp/PgDn and Up/Down arrow keypresses fail both sections |  | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass
26 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule History | Launches case search | Should launch Bail Schedule History |  | 2026-03-25 | Pass with Comments |  | 03/13 - devs to address 03/25 - case search no longer appears, see ID 42
27 | 2026-03-12 | Both | Functionality | Major | Resolved | General | Newly added violations not appearing | 1. User adds new violation in Violations window 2. Open Bail Schedule - search/scroll does not show newly added violation | Appears to be related to cache, after 30 minutes could see new violation; this needs to be addressed as users cannot wait 30 minutes to configure bail schedule row after adding violation | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass
28 | 2026-03-12 | Both | Functionality | Major | Resolved | Bail Schedule History | Reason/Comments remain after selecting different violation | 1. User attempts to add Bail Schedule Qualifier to Bail Schedule row and adds Reason/Comments 2. Attempts to save - errors (ID 20, 21) 3. Click on another violation - Pending Changes validation appears - No 4. Proceeds to violation selected: Reason/Comments remains populated |  | 2026-04-14 | Pass |  | 03/13 - devs to address 04/14 - regression test pass
29 | 2026-03-12 | Both | Functionality | Major | Resolved | General | Launching read-only view | Open blazor window as read-only from other Vision Windows (e.g., Case Summary, Counter, etc.) |  | 2026-04-06 | Pass |  | 04/14 - regression test pass | waiting on Sameers popup window
30 | 2026-03-25 | Both | UI | Minor | No Action | General | Scroll changes blue color of rows | Slowly scrolling through violations makes the blue rows temporarily lighter |  |  | Pass with Comments |  | 04/10 - leave as-is, cannot fix | 4/7/2026 scrol color is syncfusion
31 | 2026-03-25 | Both | Functionality | Major | No Action | Violation & Bail Schedule Qualifier | PgUp/PGDn Keypress & Up/Down arrow keypress causes highlight to flash | F8/PgDn: next row is highlighted at the bottom of the section, moves to the middle, then ends at the top so user sees the blue highlight in the 3 locations F7/PgUp: highlight disappears/reappears at top of section (ok with this) | Issue occurs in both sections, but more noticeable in Violations |  | Pass with Comments |  | 04/10 - leave as-is, cannot fix | 4/7/2026 works as is
32 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule | Expires Date flickers date format if field is disabled | When Expires field is disabled (profile in PROFIL/BSDTEXP category), user sees date format flash before final MM/DD/YYYY format. Occurs quickly but seems to be YYYY-MM-DD that flashes | This does not occur if Expires Date field is enabled for user | 2026-04-14 | Pass | Pass | 04/14 - Effective (BS Review window) and Expires (both windows) fields reduced flickering | 4/7/2026 minimized the flickering
33 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule | Expires Date - cannot remove | 1. Enter Expires Date and save changes 2. Attempt to remove Expires Date (delete, type '0's) 3. Expires date resets to last value | NG window incorrectly resetting value in field. User should be able to unexpire records if they are in PROFIL/BSDTEXP category | 2026-04-14 | Pass | Pass |  | 4/7/2026 removed strict mode
34 | 2026-03-25 | Both | Functionality | Minor | Resolved | Bail Schedule | Tab keypress placements | When user is in Priors field, Tab keypress goes to Compute Bail, then NC checkbox, down the column , then up to Base Amt When user is in bottom portion at Special Schedule, the tab keypress goes across to Bail Category rather than going down | Can the tab keypress be configured to go to the next field that is not a checkbox? Priors > Base Amt, PA Dist Sched > Special Schedule, Special Schedule > Charge Type > Diversion Type > Bail Category > DOJ > JBSIS | 2026-04-14 | Pass | Fail |  | 4/7/2026 fixed
35 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule | Bail Dist Sched & PA Dist Sched | When checked, they have the same dropdown selections. Unchecked, they have different dropdowns | Confirm if this is correct behavior or if the dropdowns should be different? Currently there is no way for BSA to validate as this is bug in the PB window | 2026-04-14 | Pass | Pass |  | 4/7/2026 both special dists are same - images on right
36 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule | PA Dist Sched dropdown arrow changes placement | 1. User selects value from PA Dist Sched dropdown 2. User then selects empty value from dropdown | Dropdown arrow moves from right side of field to left. When the Special PA Dist Ind box is selected and the same steps occur, the issue does not happen | 2026-04-14 | Pass | Pass |  | 4/7/2026 fixed
37 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule | Amount Fields (Base Amt, Post Amt, POC, PA Inelig Amt) | User tries to enter value greater than, 10,000,000,000.00 an tabs out of field, field overrides to max value 9,999,999,999.99 | If user enters a value higher than the allotted value, can a FluentValidation appear instead of overriding to max value? | 2026-04-14 | Pass | Pass |  | 4/7/2026 fluent validations - removed max amt
38 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule | Alignment of check boxes and fields | Can the alignment of the checkboxes (NC through Special PA Dist Ind) align with Post Amount through PA Dist Sched rows? | Current view looks like checkboxes are lower than the fields in right column | 2026-04-14 | Pass | Fail |  | 4/7/2026 fixed
39 | 2026-03-25 | Both | Functionality | Major | Resolved | Delete | Window resets after Delete Bail Schedule Row | Deleting latest bail schedule row resets window to first row in violation as if the window was newly opened | Shouldn't the highlight remain on the violation after a delete since it remains highlighted on edits? | 2026-04-14 | Pass | Pass
40 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule | JBSIS value alignment | Values misaligned in comparison to Bail Category and DOJ; should be moved slightly to the right in the field |  | 2026-04-14 | Pass | Pass |  | 4/7/2026 fixed
41 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule | New Bail Schedule Row visible after abandoning in Pending Changes message | 1. Add new row 2. Use Prev button to view previous bail schedule record 3. Pending Changes message - No | Unsaved bail schedule row still appears with copied data but bail schedule qualifiers get wiped If user selects No seems like the bail schedule record created in step 1 shouldn't be retained | 2026-04-14 | Pass | Pass |  | 4/7/2026 fixed
42 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule History | Error Message when launching | 1. Error message displays when attempting to launch - there's an OK and "X" icon to close out message but neither work 2. User can click and highlight rows behind message | 03/26: Can now launch Bail Schedule however, not sure if review needs to occur on message? | 2026-04-14 | Pass with Comments | Pass | 04/14 - see ID 54, 55. Error messages appear so was able to test X and Close buttons | 4/7/2026 added error handling and now shows message, and it allowed me to close popup - image to right
43 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule History | Dt Effective/ Expires Missing from NG report | NG displays #Error instead of Effective and Expires Date |  | 2026-04-14 | Pass | Pass | 04/14 - cannot validate due to ID 54, 55 04/14 - fixed after afternoon deployment | 4/7/2026 fixed
44 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule History | Reduce spacing below each update row | Gray lines are sufficient to distinguish each row, added space means less rows display on each page |  | 2026-04-14 | Pass | Pass | 04/14 - cannot validate due to ID 54, 55 04/14 - fixed after afternoon deployment | 4/7/2026 fixed
45 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule History | No history view | Window displays: No bail schedule history found for this violation. | If there is no bail schedule history, can we display a blank report to match current PB window? User might think this is an error since they're used to seeing a blank report | 2026-04-14 | Pass | Fail | 04/14 - cannot validate due to ID 54, 55 04/14 - fixed after afternoon deployment | 4/7/2026 fixed
46 | 2026-03-25 | Both | Functionality | Minor | Resolved | Bail Schedule History | Tab keypress placement | Reason dropdown > Show History button > Comments | Can Tab keypress be configured to go to Comments action rather than Show History button? If not, workarounds include clicking in field or using Tab keypress twice | 2026-04-14 | Pass | Pass |  | 4/7/2026 done
47 | 2026-03-25 | Both | UI | Minor | Resolved | Bail Schedule Qualifiers | Missing borders around rows | Gray borders surrounding each of the BSQ rows no longer display and appear to be missing gradient | Unsure why these were removed; gradient reappears when user enters edit mode | 2026-04-14 | Pass | Pass |  | 4/7/2026 fixed
48 | 2026-03-25 | Both | Functionality | Major | Resolved | Bail Schedule Qualifier | Section Freezes for non-PROFIL/BSQEDIT profiles | 1. Removed ct_developer from PROFIL/BSQEDIT category 2. Attempt to edit DMV Dispositions bail schedule qualifier (qualifier is in BLSCQL/IMPACT category) | User is unable to edit it as expected, however the BSQ section freezes and user cannot edit any other row; seems as though row is stuck in edit mode as context menu fails to appear/user cannot exit edit mode | 2026-04-14 | Pass | Fail | 04/14 - resolved as row no longer goes into edit mode if profile is not in BSQEDIT category | 4/7/2026 fixed
49 | 2026-03-25 | PB Only | Functionality | Major | Resolved | Read-Only Bail Schedule | Ctrl + Shift + Click displays error message before opening old window | Expression is not valid message appears twice , window opens with all violations highlighted rather than the violation selected |  | 2026-04-14 | Pass |  |  | 4/7/2026 sameer will is reviewing this 4/9/2026 double click working with Sameer
50 | 2026-03-25 | PB Only | Functionality | Major | Resolved | Read-Only Bail Schedule | Does not open correct bail schedule row | 1. Open Case Summary with 08CF0002 and double click count 1 (DOV 12/30/07) 2. Blazor Bail Schedule window opens to row 3 of 3 (latest row) | Current logic is incorrect, window should have opened row 1 of 3 as DOV falls within range of bail schedule row 1 | 2026-04-14 | Pass | Pass |  | 4/7/2026 fixed
51 | 2026-04-14 | Both | Functionality | Minor | Resolved | Effective Date Expires Date | FluentValidations placement | Effective Date FluentValidation (FV) is cut off, Expires Date message is close to the border but still visible | Move FVs to bottom of cell so that entire FV messages display | 2026-04-14 | Pass | Pass
52 | 2026-04-14 | Both | UI | Regression | Resolved | Bail Schedule | PA Dist Sched | Formal Probation selection code is cut off | Increase Bail Schedule column width so that this field is slightly expanded | 2026-04-16 | Pass |  | 04/14 - previously fixed (ID 16) but now is reocurring 04/14 - re-reported as display issue occurs with bolded text; seeing if section can be expanded to account for bolded text
53 | 2026-04-14 | Both | UI | Minor | Resolved | Bail Schedule Qualifier | FluentValidations placement | Edit mode cuts off the FV for Value as cell reduces in height | Can edit mode cell height remain so entire FV is showing | 2026-04-14 | Pass |  | 04/14 - fixted to display on bottom of cell
54 | 2026-04-14 | Both | Functionality | Regression | Resolved | Bail Schedule History | Show History button message | When history has no data, should display blank report. Instead receiving this message: "Operation returned an invalid status code 'NotFound'" | ANMC 11.04.010 sample violation | 2026-04-14 | Pass |  | 04/14 - previous ST testing passed, however it's failing in both ST/QA now 04/14 - fixed after afternoon deployment
55 | 2026-04-14 | Both | Functionality | Regression | Resolved | Bail Schedule History | Show History button message | When history has data, should display blank report. Instead receiving this message: "ORA-22835: Buffer too small for CLOB to CHAR or BLOB to RAW conversion (actual: 6937, maximum: 4000) https://docs.oracle.com/error-help/db/ora-22835/" | TC NGTEST01 sample violation | 2026-04-14 | Pass |  | 04/14 - previous ST testing passed, however it's failing in both ST/QA now 04/14 - fixed after afternoon deployment
56 | 2026-04-14 | Both | Functionality | Major | Resolved | Bail Schedule | Charge Type & Diversion Type display additional selections | Displaying expired code entries in dropdowns; user is able to select and save expired values | PB window does not display expired values | 2026-04-14 | Pass
57 | 2026-04-16 | Both | Functionality | Major | Resolved | Bail Schedule | Number fields (Amts, POC, PA Inig, Bail Category, DOJ) | Arrow keys can increase/decrease values | Disable arrow keys | 2026-04-16 | Pass
58 | 2026-04-16 | PB Only | Functionality | Major | Resolved | Read-Only Bail Schedule | Does not open correct bail schedule row | 1. Open Case Summary with IVRMCTS02 and double click count 2 (DOV 12/30/07) 2. Blazor Bail Schedule window opens to row 1 of 6 | Some violations have duplicate rows with same Expires/Effective date as Priors amount varies; NG window is capturing the wrong violation | 2026-04-16 | Pass

## SUMMARY
|  | Count of Status | Column Labels
QA # | HH:MM | Row Labels | Resolved | No Action | Grand Total | Row Labels | Count of Bug Type | Row Labels | Count of Status
1 | 16:00 | 2026-03-12 | 25 | 4 | 29 | Major | 29 | Resolved | 52
|  | Functionality | 15 | 1 | 16 | Minor | 26 | No Action | 6
|  | Major | 13 | 1 | 14 | Regression | 3 | Grand Total | 58
|  | Minor | 2 |  | 2 | Grand Total | 58
|  | UI | 10 | 3 | 13
|  | Minor | 10 | 3 | 13
2 | 10:00 | 2026-03-25 | 19 | 2 | 21
|  | Functionality | 13 | 1 | 14
|  | Major | 11 | 1 | 12
|  | Minor | 2 |  | 2
|  | UI | 6 | 1 | 7
|  | Minor | 6 | 1 | 7
3 | 4:00 | 2026-04-14 | 6 |  | 6
|  | Functionality | 4 |  | 4
|  | Major | 1 |  | 1
|  | Minor | 1 |  | 1
|  | Regression | 2 |  | 2
|  | UI | 2 |  | 2
|  | Minor | 1 |  | 1
|  | Regression | 1 |  | 1
3 | 1:00 | 2026-04-16 | 2 |  | 2
|  | Functionality | 2 |  | 2
|  | Major | 2 |  | 2
|  | Grand Total | 52 | 6 | 58

## UAT
Issue ID | Section/Field | Date Reported | Reported By | Finding/Request | Date Decision | Decisions
1 | Violations | 2026-05-07 | Operations | Request for search field to be moved above “Violation” and “OL” column headers | 2026-05-12 | Leave as-is: this field is used as a filter rather than a search field and therefore needs to be placed underneath the column headers
2 | Bail Dist Sched (Bail Schedule section) | 2026-05-07 | Operations | “HSHW” listed in dropdown, but value does not exist in production | 2026-05-12 | Leave as-is: this is a region-specific finding as this value is not configured in production; if needed, please consult Fiscal for questions on the configuration differences in CRMQ/CRMP
3 | PA Dist Sched (Bail Schedule section) | 2026-05-07 | Operations | NG window displays code (e.g., STND) rather than description (e.g., Standard); request to use description to match current display in production | 2026-05-12 | Fixed: now available in CRMQ for UAT
4 | Bail Schedule Qualifier | 2026-05-07 | Operations | Request for section’s default display to list qualifiers alphabetically regardless of capitalization; NG displays “CCAPK” qualifier before “Case Statistic” qualifier in default display | 2026-05-12 | Fixed: now available in CRMQ for UAT
5 | Bail Schedule Qualifier | 2026-05-21 | Operations | To select a qualifier the user has to double click the value field and then click the box to make the selection. In Production the user simply makes one click to check off the box. Not all qualifiers require a value. | 2026-06-03 | Fixed: now available in CRMQ for UAT
6 | Violations | 2026-05-21 | Operations | When the user searches in the filter if characters or spaces are added it filters out to much which will have users miss violation entries. | 2026-06-03 | Fixed: now available in CRMQ for UAT; violations that contain entry made in the search field will appear in results; example shown below shows all violations containing “23152” as this is what the user entered in search field
7 | Violations | 2026-06-08 | Operations | As you type in the violation search field, there's a glitch where it will stop typing in the search field and start typing in the effective date box or the qualifer pane | 2026-06-22 | Fixed: cursor remains in search field when typing for violations. Additionally, we implemented an enhancement where spaces are removed from the search if they are entered in the search criteria. This enhancement addresses the previous concern of violations being filtered out if users inadvertently entered a space in the search field.
8 | History | 2026-06-08 | Operations | There is latency when assessing the history tab, the report does not load timely and it gives impression that there is a blank report retrieved. | 2026-06-22 | Leave as-is: we added more logs to track the issue. However, after reaching out to user, the issue has not occurred since initial reporting. If the issue occurs again, please provide the user’s name, date, time, and violation they were trying to access and we can review the logs.

## Drop Downs
Bail Dist Sched | PA Dist Sched | Special Schedule | Charge Type | Diversion Type
AQ | CRPA Child Safety Restraint
BH | DUI DUI | Bail Categories | Criminal Violation | Traffic School
BP1 | FISH Fish and Game | Over Catch Limit Fish | Traffic Violation
BP2 | FMLPRB Formal Probation | Over Weight Limit
BP3 | RAIL Rail Road | Speed Schedule
BP4 | RDLT Red Light | Speed Schedule 2
BP5 | RLTS Red Light Traffic School | Speed Schedule Trailers
CO | STND Standard
CR | TRSC Traffic School
DL
DUI
FG
FGAB
FGBG
FGPO
FGWB
FW
GN
GNW
GNW1
HMNTR
HN
HS
HSO
HSRV
IW
LA
LG
LTR
RD1
RD2
RL
RLTS
RR
RRTS
RTSM
SE
SE2
TL
TM
TS
UC
VC
VW
VW1

## 1
4K
Standard

## BSA - Scenarios (hidden)
ID | Scenario | Window Column | Element | Header/Row | Vision Display | NG Display | Violation | Pass/Fail | Comments
1 | UI | Header | Window Name/Header | Header | Window title: Bail Schedule Maintenance Placement is to the right of gavel icon | Window title: Bail Schedule Maintenance Placement is to the right of gavel icon |  | Pass
2 | UI | Left | Search Field | 1 | Placement: Located in upper left of window | Placement: Located in upper left of window New: "X" feature appears in right side of search field(s) to clear search |  | Pass with Comments | 04/07/26: acts as filter so needs to be placed under column title
3 | UI | Left | Search Field | 1 |  | Search box height should be smaller |  | Pass
4 | Functionality | Left | Search Field | 1 | Max character limit is 30 | Max character limit is 30 |  | Pass
5 | Functionality | Left | Search Field | 1 | Type number first, top row remains highlighted | Type number first, No records to display message appears |  | Pass
6 | Functionality | Left | Search Field | 1 | Type "B" to direct user to BP 10085 as it is first alpha/numbercial violation starting with the letter; row is highlighted and bail schedule loads | Type "B" to direct user to BP 10085 as it is first alpha/numerical violation for the search criteria; row highlighted and BP 10085 bail schedule loads; search results only display "B" violations |  | Pass
7 | Functionality | Left | Search Field | 1 | Type "VC 23152 (a)" search field, user directed to VC 23152 violations | Type "VC 23152 (a)" search field, No records to display message appears |  | Pass with Comments | 04/07/26: user needs to enter exact section/code
8 | Functionality | Left | Search Field | 1 | Type "VC 23152(a)" search field, scroll bar remains | Type "VC 23152(a)" search field, scroll bar disappears and search only displays VC 23152; moving search field(s) above Violation/OL columns (ID #2) might fix this issue and the empty cell to the right of the column titles/search field(s) when scroll bar is present |  | Pass with Comments | 04/07/26: decision to leave as-is on 03/13
9 | UI | Left | Violations | Header | Column header reads "Violation" and is center aligned | Column header reads "Violation" and is center aligned |  | Pass
10 | UI | Left | Violations | 1 | Violations display in alphabetical/numerical order based on statute and section | Violations display in alphabetical/numerical order based on statute and section - offense levels appear to be in different order | VC 23152(a) F, M, N | Pass with Comments | 04/07/26: decision to leave as-is during POC
11 | UI | Left | Violations | Header | Header reads "OL" and is center aligned | Header reads "OL" and is center aligned |  | Pass
12 | UI | Left | Violations | 1 | Displays F, M, I, N | Displays F, M, I, N | VC 23152(a) N | Pass
13 | UI - Display | Center | Bail Schedule Row | 1 | Displays "BAIL SCHEDULE [#] of [#]" Placement: 1st grouping, left justified in box | Displays "BAIL SCHEDULE [#] of [#]" Placement: 1st grouping, left justified in box |  | Pass
14 | UI - Display | Center | Bail Schedule Row | 1 | Displays Prev and Next buttons; alignment to the right of #7 Placement: 1st grouping, right justified in box | Displays Prev and Next buttons; alignment to the right of #7 Placement: 1st grouping, right justified in box Buttons are gray; text should be centered in buttons New: buttons are disabled until multiple rows exist |  | Pass
15 | Functionality | Center | Bail Schedule Row | 1 | Prev button - section updates to previous bail schedule row If 1 of 1 row exists, not action is completed | Prev button - section updates to previous bail schedule row Button is gray; text should be centered in button New: If 1 of 1 row exists, button is disabled | ADB 202 (1 of 1) AG 18844 (2 of 2) | Pass
16 | Functionality | Center | Bail Schedule Row | 1 | Next button: section updates to subsequent bail schedule row If 1 of 1 row exists, not action is completed | Next button: section updates to subsequent bail schedule row Button is gray; text should be centered in button New: If 1 of 1 row exists, button is disabled | ADB 202 (1 of 1) AG 18844 (2 of 2) | Pass
17 | UI | Center | Bail Schedule Row | 2 | Effective: displays DT_EFFECTIVE as mm/dd/yyyy format For new violations, displays 00/00/0000 Placement: 2nd grouping, first row left justified | Effective: displays DT_EFFECTIVE as mm/dd/yyyy format For new violations, displays 00/00/0000 New: calendar icon displays calendar for user to select date when clicked on | VC 23152(a) F | Pass
18 | UI | Center | Bail Schedule Row | 2 | Expires: displays DT_INVALID as mm/dd/yyyy format Placement: 2nd grouping, same row as Effective field Right edge of date field aligns with right edge of Description field | Expires: displays DT_INVALID as mm/dd/yyyy format Placement: 2nd grouping, same row as Effective field Right edge of date field aligns with right edge of Description field New: calendar icon displays calendar for user to select date when clicked on | VC 23152(a) F | Pass
19 | UI | Center | Bail Schedule Row | 2 | Description: displays DESCRIP Placement: 2nd grouping, below Effective/Expires fields | Description: displays DESCRIP Placement: 2nd grouping, below Effective/Expires fields | TC 1234 F | Pass
20 | UI | Center | Bail Schedule Row | 2 | Type: displays Count, Enhancement, Prior, or Other Allegation Placement: 2nd grouping, below Description | Type: displays Count, Enhancement, Prior, or Other Allegation Placement: below Description Field name should align with search field Data should be aligned left/middle of field | VC 23152(a) F Count VC 23152(a)&(b) OA PC 667(a) Prior PC 12022.1 Enhancement | Pass
21 | UI | Center | Bail Schedule Row | 2 | Off Level: displays F, M, I, N (should match #8) Placement: 2nd grouping, same row as Type | Off Level: displays F, M, I, N (should match #8) Placement: 2nd grouping, same row as Type | VC 23152(a) F VC 23152(a) M VC 23123.5(a) I VC 23152(a) N | Pass
22 | UI | Center | Bail Schedule Row | 2 | Priors: display NUMBER_PRIORS Placement: 2nd grouping, same row as Type | Priors: display NUMBER_PRIORS Placement: 2nd grouping, same row as Type | VC 23123.5(a) I | Pass
23 | UI | Center | Bail Schedule Row | 2 | Compute Bail: checkbox COMPUTE_BAIL Placement: 2nd grouping, same row as Type | Compute Bail: checkbox COMPUTE_BAIL Placement: below Count/Off Level; right of Priors | VC 23123.5(a) I | Pass
24 | UI | Center | Bail Schedule Row | 3 | Delete button - deletes BS row Placement: 3rd grouping, first column of third row with check boxes/base amt | Delete button - deletes BS row Placement: 3rd grouping, first column of third row with check boxes/base amt | TC NGTETST01 | Pass
25 | Functionaltiy | Center | Bail Schedule Row | 3 | Select Delete button - Validation Error message 'Please enter Reason.' appears Enter Reason/Comments and save, row deleted | Select Delete button - Validation Error message 'Please enter Reason.' appears Enter Reason/Comments and save, row deleted | TC NGTEST03 | Pass
26 | UI | Center | Bail Schedule Row | 3 | NC: checkbox NC_ELIG_IND Placement: 3rd grouping, top of checkbox column to the right of Delete button | NC: checkbox NC_ELIG_IND Placement: 3rd grouping, top of checkbox column to the right of Delete button | TC NGTEST03 | Pass
27 | UI | Center | Bail Schedule Row | 3 | Correctable: checkbox CORRECTABLE_IND Placement: 3rd grouping, 2nd checkbox in column to right of Delete button | Correctable: checkbox CORRECTABLE_IND Placement: 3rd grouping, 2nd checkbox in column to right of Delete button | VC 4000(a)(1) | Pass
28 | UI | Center | Bail Schedule Row | 3 | Special Dist Ind: checkbox SPECIAL_DIST_IND Placement: 3rd grouping, 3rd checkbox in column to right of Delete button | Special Dist Ind: checkbox SPECIAL_DIST_IND Placement: 3rd grouping, 3rd checkbox in column to right of Delete button | TC NGTEST03 | Pass
29 | UI | Center | Bail Schedule Row | 3 | PA Eligible: checkbox PA_ELIG_IND Placement: 3rd grouping, 4th checkbox in column to right of Delete button | PA Eligible: checkbox PA_ELIG_IND Placement: 3rd grouping, 4th checkbox in column to right of Delete button | ADB 202 | Pass
30 | UI | Center | Bail Schedule Row | 3 | Special PA Dist Ind: checkbox SPECIAL_PA_DIST_IND Placement: 3rd grouping, 5th checkbox in column to right of Delete button | Special PA Dist Ind: checkbox SPECIAL_PA_DIST_IND Placement: 3rd grouping, 5th checkbox in column to right of Delete button |  | Pass
31 | UI | Center | Bail Schedule Row | 3 | Base Amt: display BASE_AMT Placement: 3rd grouping, top of third column to right of checkboxes | Base Amt: display BASE_AMT Placement: 3rd grouping, top of third column to right of checkboxes | VC 4000(a)(1) | Pass
32 | UI | Center | Bail Schedule Row | 3 | Post Amt: display POST_AMT Placement: 3rd grouping, 2nd in column to right of checkboxes; aligned in same row as NC checkbox | Post Amt: display POST_AMT Placement: 3rd grouping, 2nd in column to right of checkboxes; aligned in same row as NC checkbox | VC 4000(a)(1) | Pass
33 | UI | Center | Bail Schedule Row | 3 | POC: display POC_AMT Placement: 3rd grouping, 3rd in column to right of checkboxes; aligned in same row as Correctable | POC: display POC_AMT Placement: 3rd grouping, 3rd in column to right of checkboxes; aligned in same row as Correctable | FG 7145 | Pass
34 | UI | Center | Bail Schedule Row | 3 | Bail Dist Sched: display SCHED_ID Placement: 4th in column to right of checkboxes; aligned in same row as Special Dist Ind checkbox | Bail Dist Sched: display SCHED_ID Placement: 4th in column to right of checkboxes; aligned in same row as Special Dist Ind checkbox | FG 7145 | Pass
35 | UI | Center | Bail Schedule Row | 3 | PA Inelig Amt: display PA_INELIG_AMT Placement: 3rd grouping, 5th in column to right of checkboxes; aligned in same row as PA Eligible checkbox | PA Inelig Amt: display PA_INELIG_AMT Placement: 3rd grouping, 5th in column to right of checkboxes; aligned in same row as PA Eligible checkbox | VC 40508(a) M (1 of 4) | Pass
36 | UI | Center | Bail Schedule Row | 3 | PA Dist Sched: display PA_SCHED_ID Placement: 3rd grouping, 6th in column to right of checkboxes; aligned in same row as Special PA Dist Ind | PA Dist Sched: display PA_SCHED_ID Placement: 3rd grouping, 6th in column to right of checkboxes; aligned in same row as Special PA Dist Ind | FG 7145 | Pass
37 | UI | Center | Bail Schedule Row | 4 | Special Schedule: display SPECIAL_SCHED_CODE Placement: 4th grouping, top of left column dropdowns | Special Schedule: display SPECIAL_SCHED_CODE Placement: 4th grouping, top of left column dropdowns | CR T14/29.85(b)(3) | Pass
38 | UI | Center | Bail Schedule Row | 4 | Charge Type: display CHARGE_TYPE_CODE Placement: 4th grouping, middle of left column dropdowns | Charge Type: display CHARGE_TYPE_CODE Placement: 4th grouping, middle of left column dropdowns | CR T14/29.85(b)(3) | Fail
39 | UI | Center | Bail Schedule Row | 4 | Diversion Type: display DIVERSION_TYPE_CODE Placement: 4th grouping, bottom of left column dropdowns | Diversion Type: display DIVERSION_TYPE_CODE Placement: 4th grouping, bottom of left column dropdowns | CR T14/29.85(b)(3) | Fail
40 | UI | Center | Bail Schedule Row | 4 | Bail Category: display BAIL_CATEGORY Placement: 4th grouping, top of right column dropdowns | Bail Category: display BAIL_CATEGORY Placement: 4th grouping, top of right column dropdowns | VC 23152(a) | Pass
41 | UI | Center | Bail Schedule Row | 4 | DOJ: display DOJ_HIERARCHY Placement: 4th grouping, middle of right column dropdowns | DOJ: display DOJ_HIERARCHY Placement: 4th grouping, middle of right column dropdowns | VC 23152(a) | Pass
42 | UI | Center | Bail Schedule Row | 4 | JBSIS: display JBSIS_CATEGORY_CODE Placement: 4th grouping, bottom of right column dropdowns | JBSIS: display JBSIS_CATEGORY_CODE Placement: 4th grouping, bottom of right column dropdowns | VC 23152(a) | Pass
43 | UI | Center | Bail Schedule Row | 5 | Updated: display DT_UPDATED Placement: 5th grouping, left justified in box aligns with Special Schedule left edge of field | Updated: display DT_UPDATED Placement: 5th grouping, left justified in box aligns with Special Schedule left edge of field | VC 23152(a) | Pass
44 | UI | Center | Bail Schedule Row | 5 | By: display USER_ID as last name, first name format Placement: 5th grouping, same row as Updated | By: display USER_ID as last name, first name format Placement: 5th grouping, same row as Updated | VC 23152(a) | Pass
45 | UI | Center | Bail Schedule Row | 6 | Reason: dropdown contianing options (Correction, Distribution Schedule Updated, New Violation, Other, Per JCUBS, Per OCUBS) Placement: separate section below bail schedule data, right side of box above Show History button | Reason: dropdown contianing options (Correction, Distribution Schedule Updated, New Violation, Other, Per JCUBS, Per OCUBS) Placement: separate section below bail schedule data, right side of box above Show History button | VC 23152(a) | Pass
46 | UI | Center | Bail Schedule Row | 6 | Show History button - launches Bail Schedule History Report window Placement: below Reason field | Show History button - launches Bail Schedule History Report window Placement: below Reason field | VC 23152(a) | Pass
47 | Functionality | Center | Bail Schedule Row | 6 | Comments: text box with max character limit 1000 (including spaces) Placement: right of Reason/Show History with | Comments: text box with max character limit 1000 (including spaces) Placement: right of Reason/Show History with | VC 23152(a) | Pass
48 | UI | Right | Bail Schedule Qualifier | Header | Header reads "BAIL SCHEDULE QUALIFIER" and is center aligned | Header reads "BAIL SCHEDULE QUALIFIER" and is center aligned |  | Pass
49 | UI | Right | Bail Schedule Qualifier | 1 | Bail schedule qualifier(s) associated to VIOL_ID_NBR display | Bail schedule qualifier(s) associated to VIOL_ID_NBR display | TC NGTEST03 | Pass
50 | UI | Right | Bail Schedule Qualifier | 1 | Each bail schedule qualifier displays (court.bail_schedule_qualifier): Qualifier: QUALIFIER_CODE descrip Value: QUALIFIER_VALUE Updated by: USER_ID as last name, first name format Added: DT_UPDATED | Each bail schedule qualifier displays (court.bail_schedule_qualifier): Qualifier: QUALIFIER_CODE descrip Value: QUALIFIER_VALUE Updated by: USER_ID as last name, first name format Added: DT_UPDATED | ADB 202 (2 of 2) | Pass
51 | UI | Right | Bail Schedule Qualifier |  | Qualifier: description is left justified and on one line | Qualifier: description is left justified and on one line | VC 4000(a)(1) i | Pass
52 | UI | Right | Bail Schedule Qualifier |  | Qualifier, Updated By, and Added are blue fields as they are not editable by user Value remains white as field can be updated | Gray out Updated By/Added as they are not editable by user (UI to match bail schedule row) |  | Pass
53 | Functionality |  | New Violation |  | 1. Create count in Violations window 2. Open Bail Schedule window, select count created: - Bail Schedule row should not exist - Blank Reason/Comments, Show History button displays - Bail Schedule Qualifiers unchecked and NULL 3. Create row 1 of 1 and save | 1. Create count in Violations window 2. Open Bail Schedule window, select count created: - Bail Schedule row should not exist: Displays "No bail schedule found" message - Blank Reason/Comments, Show History button displays - Bail Schedule Qualifiers unchecked and NULL 3. Create row 1 of 1 and save (see ID #54-57) a. User clicks "Add" button: (Pass: not a button, menu Edit > Add Row or Shift + F6) b. System creates a new row with default values c. System sets default effective date to 00/00/0000 d. User enters required fields (effective date, description, amounts) e. User clicks "Save" f. System validates required fields g. System saves the new bail schedule | TC NGTEST04 | Pass
54 | Functionality |  | New Violation |  | Tab keypress: Description > tab > Priors | Tab keypress: Description > tab > Priors | TC NGTEST04 | Pass
55 | Functionality |  | New Violation |  | Bail Dist Sched: listed in alphabetical order | Bail Dist Sched: listed in alphabetical order | TC NGTEST04 | Pass
56 | Functionality |  | New Violation |  | PA Dist Sched: listed in alphabetical order with codes | PA Dist Sched: listed in alphabetical order with codes | TC NGTEST04 | Pass
57 | Functionality |  | New Violation |  | DOJ: enter value > tab > value remains | DOJ: enter value > tab > value cleared | TC NGTEST04 | Pass
58 | Functionality |  | New Violation |  | Update successful status bar in bottom left updates after save | Tast message appears for successful save | TC NGTEST04 | Pass
59 | Functionality |  | Update existing row |  | 1. User selects a bail schedule record 2. User modifies one or more fields 3. User selects save | 1. User selects a bail schedule record 2. User modifies one or more fields (DOJ, added qualifier) 3. System tracks changes for audit trail 4. User clicks "Save" 5. System validates changes 6. System updates the bail schedule | TC NGTEST04 | Pass
60 | Functionality |  | Update existing row (Expires Field) |  | 1. Open Bail schedule window, select count and enter Expires Date 2. Enter Reason, Comments 3. Save | 1. Open Bail schedule window, select count and enter Expires Date 2. Enter Reason, Comments 3. Save | TC NGTEST04 (1 of 1) | Pass
61 | Functionality |  | Update existing row (Expires Field) |  | 1. Open Bail schedule window, select count and remove Expires Date 2. Enter Reason, Comments 3. Save | 1. Open Bail schedule window, select count and remove Expires Date 2. Enter Reason, Comments 3. Save | TC NGTEST04 (1 of 1) | Fail | 04/07/26: Cannot remove Expires date, field keeps resetting
62 | Functionality |  | Update existing row (Expires Field) |  | 1. Open Bail schedule window, select count and modify expires Expires Date 2. Enter Reason, Comments 3. Save | 1. Open Bail schedule window, select count and modify expires Expires Date 2. Enter Reason, Comments 3. Save | TC NGTEST04 (1 of 1) | Pass
| Functionality |  | Update existing row (Expires Field) |  | 1. Update PROFIL/BSDTEXP to remove ct_developer Profile 2. Open Bail schedule window, select count and modify expires Expires Date 3. Expires Date locked - user unable to edit | 1. Update PROFIL/BSDTEXP to remove ct_developer Profile 2. Open Bail schedule window, select count and modify expires Expires Date 3. Expires Date locked - user unable to edit | TC NGTEST04 (1 of 1) | Pass
64 | Functionality |  | Update existing row (Effective Field) |  | 1. Open Bail schedule window, select count and modify expires Effective Date 2. Enter Reason, Comments 3. Save | 1. Open Bail schedule window, select count and modify expires Effective Date 2. Enter Reason, Comments 3. Save | TC NGTEST03 (1 of 1) | Pass
65 | Functionality |  | Update existing row (overlap) |  | No error message appears Effective Date of subsequent row automatically updates | Error saving Bail Schedule See Details... Date range overlaps with an existing bail schedule for the same number of priors (1). User returns to view to address | TC NGTEST03 (2 of 2) | Pass
66 | Functionality |  | Add new row |  | 1. Open Bail schedule window, add new row: - Expires/Effective NULL - Maintains all other fields from previous bail schedule row 2. Enter Reason, Comments 3. Save | 1. Open Bail schedule window, add new row: - Expires/Effective NULL - Missing Offense Level, 2. User clicks "Copy" or "Replicate" button; only Add Row or Shift F6 3. System creates a new record with all values copied from the selected record 4. System clears the primary key and sets a new one 5. System sets the effective date to the current date (retest and sets to 00/00/0000) 6. User modifies any necessary fields (e.g., effective date, description) 7. User clicks "Save" 8. System validates the new record 9. System saves the new bail schedule 2. Enter Reason, Comments 3. Save | TC NGTEST02 (2 of 2) | Pass with Comments | 04/07/26: issue with Prev/Next buttons after Pending Changes message
67 | Functionality |  | Add new row |  | NULL Expires > Save: Application error displays: Error code: 49999 Window/Object: w_ct_m_fscl_bail_sched_maint dw_bail_sched_detail Error message: An unexpected error has occurred. Additional Information : Please enter Date effective | NULL Expires > Save: following message displays: visionngwebdev.azurewebsites.us says Error saving bail schedule: Failed to save bail schedule detail and qualifiers. Fail to save bail schedule detail and qualifiers Pleaser enter Date effective Message is redundant, spelling error in actual error |  | Pass | 04/07/26: FluentValidation prevents NULL Effective Date
68 | Functionality |  | Initial Window Load |  | 1. System displays the bail schedule grid 2. System populates dropdowns for schedule types and special schedules 3. System enables/disables fields based on user permissions 4. System shows existing bail schedule records if any exist | 1. System displays the bail schedule grid 2. System populates dropdowns for schedule types and special schedules 3. System enables/disables fields based on user permissions 4. System shows existing bail schedule records if any exist | TC 1234 I | Pass with Comments | 04/07/26: issue with user stuck in edit mode for DMV Dispositions BSQ
69 | Functionality |  | Toggle Special Distribution |  | 1. User checks/unchecks "Special Distribution" checkbox 2. System shows/hides special distribution schedule ID field (broken functionality) 3. System updates validation rules accordingly | 1. User checks/unchecks "Special Distribution" checkbox 2. System shows/hides special distribution schedule ID field 3. System updates validation rules accordingly | TC 1234 I (2 of 2) | Pass
BSM-007 | Functionality |  | Cancel |  | 1. User makes changes then clicks out to prompt pending changes message 2. System discards all unsaved changes 3. System reverts to last saved state | 1. User clicks "Cancel" button: user makes changes then clicks out to prompt pending changes message 2. System discards all unsaved changes 3. System reverts to last saved state |  | Pass | 04/07/26: context menu cancel for BSQ reverts as expected
BSM-008 | Functionality |  | Show History |  | 1. User selects "Show History" button 2. System displays history window with all changes chronological order 3. System shows old and new values for each change 4. System includes timestamp and user who made each change | 1. User selects "Show History" button 2. System displays history window with all changes chronological order 3. System shows old and new values for each change 4. System includes timestamp and user who made each change |  | Pass with Comments | 04/07/26:issue in display of Dt Effecitve, Expires
BSM-010 | Functionality |  | Search/Filter |  | 1. User enters search criteria 2. System jumps to row matching criteria | 1. User enters search criteria 2. System filters the display to show matching records 3. User can clear filters to show all records (IDs # 6-8) |  | Pass
BSM-014 | Functionality |  | Future Effective Date |  | 1. User clicks Actions > Add Record 2. User enters a future effective date 3. System accepts the future date 4. User completes remaining fields 5. User clicks "Save" 6. System validates the record 7. System saves the new record with the future effective date | 1. User clicks Actions > Add Record 2. User enters a future effective date 3. System accepts the future date 4. User completes remaining fields 5. User clicks "Save" 6. System validates the record 7. System saves the new record with the future effective date 8. System marks the record as pending until the effective date - not sure what this means/how to validate | TC 1234 (3 of 3) | Pass

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action