## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-10-08 | Both | Functionality | Major | Resolved | Batch Print - Calendar Batch Print | Sort applied to the Batch Print does not reflect in the printout | 1. Search for calendar with multiple cases and retrieve 2. Click Batch Print 3. Add column sort to any column 4. Click Generate Document - printout order should match the sort selected in the Batch Print. The case number message while the document is loading should also match the sort order. Current NG behavior matches the default sort. | The case number message while the document is loading should also match the sort order | 2026-10-21 | Pass | Provided sample to developer. See also new defect #6 | 10/12: Adjusted printout order to match original, responds to sorting, goes from top to bottom of view 10/19: Batch print view also responds to sorting on the calendar list grid like the original
2 | 2026-10-08 | Both | Functionality | Minor | Resolved | Court Calendar popup - No button | Enter keypress default | When the Court Calendar popup appears, the enter keypress should work for the "No" button. Tabbing would switching the selected button to "Yes" | Not sure if this can be fixed. Similar to Defect 5 on the Calendar Report log | 2026-10-16 | Pass with Comments | See new defect #7 | 10/13: Updated dialog to support this
3 | 2026-10-08 | Both | UI | Minor | Resolved | Batch Print - Court Calendar - Yes and No buttons | Button size | Yes button is slightly larger than No button |  | 2026-10-16 | Pass |  | 10/12: Done, adjusted "No" buttons dimensions in confirmation dialog
4 | 2026-10-08 | Both | Functionality | Minor | Resolved | Generate Document in the batch print | Alt + (underscore letter) shortkey functionality can be removed | Alt + G for generate document functionality can be removed. BSA decision was made 10/8 to remove these short keys from NG windows |  | 2026-10-16 | Pass |  | 10/12: Done, no more Alt + Key combos
5 | 2026-10-15 | PB Only | UI | Major | Resolved | Calendar Batch Print - Column Filter | Remove all Filter Pop-up from all columns | The Filter Pop-up is not needed for the columns in the Calendar Batch Print |  | 2026-10-21 | Pass with Comments | See new item #8 Need to review. I missed this in previous cycle as to tabbing in the Calendar Batch Print | 10/19: No more filtering.
6 | 2026-10-16 | PB Only | Functionality | Major | Resolved | Calendar Batch Print | Printing large calendar | NG Batch print is erroring out on large calendar. Getting popup message of "We can't open this file…Something went wrong." Click on the Refresh button in the pop-up and nothing happens. | Old PB window batch print is working as expect on same calendar. Provided samples to Developer | 2026-10-21 | Pass | Large calendar for H7 on 10-23-2026 batch printed with no issues. | 10/19: PB was cutting off large data. Now, instead of loading all the data at once, I am following Jorge's advice to have each JSON line be looped through instead of loading the whole thing. Found a test case that was failing in the same way, and now it works, generating 370 pages.
7 | 2026-10-16 | Both | UI | Minor | Resolved | Court Calendar - Pop;up | Switching between "Yes" and "No" button | User is unable to use the arrow-pointer left-right key on the keyboard to swich between the "Yes" and "No" buttons | Old PB window pointer key on keyboard is working | 2026-10-21 | Pass |  | 10/19: Added functionality to YesNo dialog.
8 | 2026-10-21 | PB Only | UI | Minor | Resolved | Batch Print | Calendar Batch Print pop up dialog box | #1 - The focus/cursor should be on the button when open #2 - Tabbing should be from left to right and top to bottom. It should remain in the pop up and not move to the background window. #3 - Enter keypress should work and click on the button when enter is pressed #4 - Remove message of "Dedicated to…" | When open the focus/cursor is not visible | 2026-10-22 | Pass with Comments | See new defect #9
9 | 2026-10-22 | Both | UI | Minor | New | Calendar Batch Print pop up dialog box | Button size | The "DeSelect All" and "Select All" buttons should be the same size. | In old PB window it is the same size.
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action

## Screen View
Defect #1 | NG Calendar Batch Print popup does not reflect soring
Old window popup reflects the sorting
QA Cycle 2 - Defect #1
Official Sorting on data grid and print to PDF in NG - Retesting - Pass
Official Sorting on data grid and batch printing on large calendar
Process in QA throws an error when no chaging document image exists in the Minutes and continues with other cases as expected