## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-09-21 | Both | Functionality | Minor | No Action | Field Input | Field Input data do not register | When type into a data field and tab, it deletes the entry. It must be selected by using a mouse click. |  |  |  |  | This is an issue when Filtering is enabled - this is broken in all dropdowns that have filtering enabled - Jorge will take this one over
2 | 2026-09-21 | Both | Functionality | Minor | Resolved | Field Input | Field Input do not delete | When attempting to delete a field input, it won't delete on "Court", "Hearing", and "ROC". | When F3 is used, clear the search data fields. | 2026-10-02 | Pass |  | Fixed - f3 refresh will now reset dropdowns to blank
3 | 2026-09-21 | Both | Functionality | Minor | Resolved | Field Input | Field Input error tooltip remains open | Field input error tooltip remains open even if you click away from it. If clicking away or clicking into other field, the message should disappear. |  | 2026-10-01 | Pass |  | Fixed
4 | 2026-09-21 | Both | UI | Minor | Resolved | Field Input width | Court/Hearing/ROC fields width expansion | Expand the width of Court/Hearing/ROC fields Sample data to be able to show: Court: "CCB1 - Community Court Building 1" Hearing: "HRGPC - Remote Hearing PC" ROC: "MHPTD - Mental Health Pre-Trial Diversion" Court field should be addressed in "From" and "To" sections. |  | 2026-10-02 | Pass | Expand the fields to accomodate the samples: Sample data to be able to show: Court: "CCB1 - Community Court Building 1" Hearing: "HRGPC - Remote Hearing PC" ROC: "MHPTD - Mental Health Pre-Trial Diversion" Court field should be addressed in "From" and "To" sections. | Fixed
5 | 2026-09-21 | Both | UI | Minor | Resolved | Hearing Field | Hearing field duplicates | Hearing events in the Hearing dropdown are duplicating. |  | 2026-10-02 | Pass | Hearing field still duplicating. | Fixed
6 | 2026-09-28 | Both | UI | Minor | Resolved | Column Header alignments | Left Align "Case, Defendant" columns |  | Revert to center align in all columns. | 2026-10-02 | Pass |  | Fixed
7 | 2026-09-28 | Both | UI | Minor | Resolved | JO Alert Column | Add JO Alert Column | Add JO Alert Column to both "From" and "To" sections. | Sample: C61, 12/03/2026 | 2026-10-01 | Pass |  | Fixed
8 | 2026-09-28 | Both | Functionality | Major | Resolved | Case Transfer | Transfer errors | When transferring cases, an error displays. Transfer is unsuccessful. | Error applying calendar transfer. See Details... ORA-01400: cannot insert NULL into ("COURT"."CASE_DOCKET"."SEALED_IND") ORA-06512: at line 6 https://docs.oracle.com/error-help/db/ora-01400/ | 2026-10-02 | Pass | Window says saved, but no docket code entered on the case. Case reflects the transfer hearing. | Fixed
9 | 2026-09-28 | Both | UI | Minor | Resolved | Court field "To" section | Expand the Court field to accommodate the full width of the data. | Common courtroom appears as "C1 - Departme…". Expand the Court field in TO section to accomoate the full description of the common courtrooms. |  | 2026-10-02 | Pass | Expand the fields to accomodate the samples: Sample data to be able to show: Court: "CCB1 - Community Court Building 1" Hearing: "HRGPC - Remote Hearing PC" ROC: "MHPTD - Mental Health Pre-Trial Diversion" Court field should be addressed in "From" and "To" sections. | Fixed - with the 12px font size I did the best I could
10 | 2026-09-29 | Both | Functionality | Minor | Resolved | JO Alert Warning | Cases with JO Alert should display pop-up warning | When transferring a case with JO Alert, then a warning message should pop-up. "Warning - You have selected case(s) that contains a judicial officer alert. Do you want to proceed? Yes / No" |  | 2026-10-01 | Pass |  | Fixed
11 | 2026-10-01 | Both | UI | Minor | Resolved | Search section font size | Increase the font size for the Search sections | Previously requested to decrease the font sizes in the Search sections, however, they are too small now. | Data input field fonts are larger when selection dropdown is used, however, registered data is much smaller. | 2026-10-02 | Pass | Revert all font sizes to match the UI guideline. | Fixed
12 | 2026-10-01 | Both | UI | Minor | Resolved | Checkbox | Checkbox to be center aligned | Center align the checkbox |  | 2026-10-02 | Pass |  | Fixed
13 | 2026-10-23 | Both | Functionality | Minor | No Action | Transfer | Multiple calendar source to single target | When transferring mulitple large calendar sources to single target courtroom by multiple users fails with unique constraint errors. |  | 2026-10-23 | Fail | Existing production issue. Legacy window screenshot provided.
14 | 2026-10-23 | Both | Functionality | Minor | No Action | Transfer | Multiple calendar source to single target w/ROC | When multiple usrs are transferring a same large calendar source to single target courtroom/date, then ROC deletion error displays. |  | 2026-10-23 | Fail | Existing production issue. Calendar deletion procedure is currently only in ROC. Legacy window screenshot provided.
15 | 2026-10-19 |  |  | Minor | Resolved |  | [UAT #1] When transferring a whole calendar (W11 to W7 - 161 cases, W12 to W1 - 72 cases, W3 to W4-89... | When transferring a whole calendar (W11 to W7 - 161 cases, W12 to W1 - 72 cases, W3 to W4-89 cases), received an error message. After closing the error message, the calendars did end up transferring still. I transferred a smaller calendar of 17 cases (W3->W4) and it did not give an error. | From UAT Defect Log - CALENDAR TRANSFER #1 (Operations; reporter Katrina; tester Eliza, Rebecca, Katrina). | 2026-10-23 | Pass | 10/21/2026, C5 (813 cases) transferred to 10/21/2026, C1. 10/21/2026, C1 (151 cases) transferred to 10/21/2026, C3. 10/21/026, C6 (184 cases) transferred to 10/21/2026, C7
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action