## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-07-20 | Both | Functionality | Major | New | N/A | Missing Complaints do not appear | Missing complaint searches by person name do not appear in the simple case search results
2 | 2026-07-22 | Web Only | Functionality | Minor | New | Case | No typing delimiter | Typing in the search field backtracks while you are typing or deleting characters. | UI Guideline 38
3 | 2026-07-22 | Web Only | UI | Minor | New | OC Pay# | OC Pay# commas | OC Pay# formatting includes commas
4 | 2026-07-22 | Web Only | UI | Minor | New | N/A | Title | Simple Case Search
5 | 2026-07-22 | Web Only | Functionality | Major | New | Business, Enterprise Name | Business check box does not show "Enterprise Name" | 1. Open window with case search 2. Select Business check box - Enterprise Name field does not appear
6 | 2026-07-22 | Web Only | UI | Minor | New | Search Button | Search Button disappears while search is loading | While clicking the search button or pressing enter, the Search button changes to a grey button with 3 dots until the load finishes. This causes all search fields to shift right and resize during the load
7 | 2026-07-22 | Web Only | Functionality | Major | New | Adv Search button | Adv Search button does not work | Adv Search button does not open Advanced Case Search PB window. Expect to see the Under Construction message.
8 | 2026-07-22 | Web Only | Functionality | Minor | New | N/A | Case Search with no results loads the window | 1. Open window with case search 2. Click enter, or search before typing in values 3. Close the "No rows retrieved message" - window loads without data. Expected result is the window closes
9 | 2026-07-22 | Web Only | Functionality | Minor | New | Rows Retrieved | Search without criteria shows no results | Search without criteria should show first 500 rows
10 | 2026-07-22 | Web Only | UI | Minor | New | Case, OC Pay# Last, First, Middle, Suffix, Enterprise Name | Character limit does not match PB | Character limits do not match PB. Since the PB window has character limits based on the width of the field, use DB character limits. | UI Guideline 19, should match DB character limits
11 | 2026-07-22 | Web Only | Functionality | Minor | New | Rows Retrieved | Max row count does not match PB | NG max row count is 200. PB is 500.
12 | 2026-07-22 | Web Only | Functionality | Minor | New | Last, First, Middle, Suffix | Search fields use fuzzy search | typing names in the search field show fuzzy search results rather than exact search results
13 | 2026-07-23 | Web Only | UI | Major | New | N/A | No results message appears during search | While the search is processing, the "No records to display" message appears. | Show loading wheel while results are pending
14 | 2026-07-23 | Web Only | Functionality | Major | New | Page Up/ Down/ F7/ F8/ arrow keys | Scroll navigation arrow keys don't work | Page Up, Page Down, F7, F8 short keys do not work. Arrow keys move the scroll bar until a row is selected | Needs discussion with devs. F7/F8/F10/F11 are configured at a window level. These may not be availble for search windows
15 | 2026-07-23 | Web Only | Functionality | Minor | New | N/A | Top row is not selected when result loads
16 | 2026-07-23 | Web Only | Functionality | Minor | New | N/A | Enter keypress changes the selected row | Enter keypress changes the selected row. Expected result is that "Select" functionality opens the selected row
17 | 2026-07-23 | Web Only | UI | Minor | New | All Columns | White column header border is missing |  | UI Guideline 9
18 | 2026-07-23 | Web Only | UI | Minor | New | OC Pay# | Sort is to the left of column label | OC Pay# column sort icon is to the left of the column label. This makes it difficult to tell which column is being sorted | Needs discussion. It might be better to expand the OC Pay # column and shift it left to see the sort appear on the right
19 | 2026-07-23 | Web Only | Functionality | Major | New | N/A | Sealed cases appear | When user does not have sealed case access, Seal 1-3 cases appear in the search results. User can view sealed case information Seal 1 - Shows no results Seal 2 - Shows Public Case, Sealed under the deft name, does not let you select Seal 3 - Public Case and Name, does not let you select | Sample case: QA-72622A and Q-72522A in CRMQ
20 | 2026-07-23 | Web Only | UI | Minor | New | Case Status | Case Status should be left aligned |  | UI Guideline 23
21 | 2026-07-23 | Web Only | Functionality | Minor | New | OC Pay#, Business Checkbox | Enter keypress does not work with OC Pay# | While cursor is in OC Pay# search field or the Business checkbox is highlighted, the enter keypress does not work. Tabbing out then selecting enter works
22 | 2026-07-23 | Web Only | Functionality | Major | New | Search Button | Load Time | Search results take at least 4 seconds to load. PB is instant for most results | See Defect 13 testing comments
23 | 2026-09-15 | Web Only | Functionality | Major | New | N/A | Duplicate Rows appear | Duplicate rows sometimes appear in case search for the same defendant | See screenshot 23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49

## Screenshots
ID | Screenshot
23

## Summary
QA Cycle 1: 5:00
Count of Status | Column Labels
Row Labels | New | Grand Total
Functionality
Major | 6 | 6
Minor | 8 | 8
UI
Major | 1 | 1
Minor | 7 | 7
Grand Total | 22 | 22

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action