## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-05-22 | Both | UI | Minor | No Action | HUMCNV - Applications | Incorrect Column Label | HUMCNV dropdown column label should be "Applications". Currently reads "Xref1" | Relates to Defect 2. The column says "BYTEST Parm 1 Label" after the test XRef was created.
2 | 2026-05-22 | Both | UI | Minor | No Action | Varies | Columns without XREFDE Definition | Columns without XREFDE Definition are labeled "Xref(column number)". PB window leaves the column header blank with the exception of dropdown HUMCNV column 1
3 | 2026-05-22 | Both | UI | Minor | No Action | N/A | Missing "No Records to Display" message | Initial load is missing the "No records to display" message in the grid | Added UI Guideline 111 for this.
4 | 2026-05-22 | Both | Functionality | Minor | No Action | N/A | Insert Row is missing | Insert row is missing from NG window. PB "Edit" configuration does not include this, but the PB right click includes "Insert". | BSAs or devs can add the "Insert Row" option to "Edit" menu. NG window follows UI guidelines, but this is a PB config issue.
5 | 2026-05-22 | Both | UI | Minor | Resolved | Varies | Tooltip display - Grid | Tooltip appears when you hover over the code text, but PB version appears when you hover over the cell. | Needs discussion. This happens in job error log too. | 2026-05-27 | Pass
6 | 2026-05-26 | Both | UI | Minor | No Action | Column Headers | Tooltip display - Column Headers | Tooltip appears when you hover over column header cell.
7 | 2026-05-26 | Both | UI | Minor | Resolved | Varies | Focus on window | Window loses focus on the grid after dropdown selection | This is the first window with a dropdown opening a grid without a search/ retrieve button. | 2026-05-27 | Pass | Ctrl + Shift + F works in dev, but arrows do not. This is fine
8 | 2026-05-26 | Both | UI | Minor | Resolved | Varies | Flashing occurs on resort | Sort causes flashing on save |  | 2026-05-27 | Pass
9 | 2026-05-26 | Both | Functionality | Major | Resolved | Varies | Extra Validation | NG window requires Column 1 selection on save and shows fluent validation. PB window allows you to save empty rows. | DB tables match between CRMQ and CRMD. | 2026-05-27 | Pass
10 | 2026-05-26 | Both | Functionality | Major | No Action | Varies | Pending Changes message | 1. Select Dropdown option 2. Add row with valid values 3. Exit edit mode 4. Select a different dropdown option - pending changes message appears | PB window allows you to select another dropdown, but loses the pending changes. Defect corrected with NG
11 | 2026-05-27 | Both | UI | Minor | Resolved | Varies | Tooltip displays square if code description is empty | 1. Remove the code description from an entry that already has 2. Open Codes Xref 3. Hovering cursor over cell with the code created in step 1 - blank tooltip appears |  | 2026-05-27 | Pass
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Summary
QA Cycle 1: 3:00
Count of Status | Column Labels
Row Labels | New | Grand Total
Functionality
Major | 2 | 2
Minor | 2 | 2
UI
Minor | 7 | 7
Grand Total | 11 | 11
QA Cycle 2: 1:00
Count of Status | Column Labels
Row Labels | No Action | Resolved | Grand Total
Functionality
Major | 1 | 1 | 2
Minor | 1 |  | 1
UI
Minor | 4 | 4 | 8
Grand Total | 6 | 5 | 11

## Screenshots
Defect ID | Screenshot
1

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action