## DEFECTS
ID | Date Reported | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | BSA Test Scenario Comments | Date Retest | Retest Pass/Fail | BSA Comments | DEV Comments
1 | 2026-01-30 | PB Only | UI | Minor | Resolved | General | Window Load | Is it possible to display the loading wheel first? Currently the window flashes between white/gray then displays the loading wheel, then the window | Might have been introduced with Tab Flash issue that was recently implemented | 2026-04-30 | Pass | 03/18: see ID #29 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - Jorge might have addressed this issue
2 | 2026-01-30 | Both | Functionality | Minor | Resolved | General | F7/F8 Delay in loading | 1. User selects F8 2. Next row is higlighted in middle of field 3. Row then moves to top | Next row is always at top in current window | 2026-04-30 | Pass | 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/10/26 SM - modified rows in view to 27. Next row being displayed at the top was a result of adding virtualization
3 | 2026-01-30 | Both | Functionality | Major | Resolved | General | F3 Refresh | F3 does not clear column filters; sorting and placement remain. If user's view is the last page and F3 to refresh executed, the view remains the same rather than displaying the first row as if the window was first opened | UI Guidelines #40; ID does not state that sorting/window view should be cleared, should it be? Might need to define Reset v. Refresh if terms are different | 2026-04-30 | Pass | 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - filters are now reset when refreshing and saving
4 | 2026-01-30 | Both | Functionality | Minor | Resolved | General | F3 Refresh | Can Refresh also reset column widths to default display? |  | 2026-04-30 | Pass | 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/9/26 SM - Reset the column width when refreshing the window.
5 | 2026-01-30 | Both | Functionality | Major | Resolved | General | F3 Refresh | If user clicks on grid then refreshes, loading window does not appear - only a small loading circle in the grid; should be the 100% opacity view | UI Guidelines #87; user clicks outside of grid then 100% opacitiy view appears; should be consistent regardless of where user clicks | 2026-04-30 | Pass | 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - loading screen has been added on refresh & save
6 | 2026-01-30 | Both | Functionality | Minor | Resolved | Control Code, Dt. Updated, Updated By | Read-only values when row is in edit mode | Is there a way to "disable" these fields when row is in edit mode? Currently cells open up in a view that looks like they can be modified |  | 2026-04-30 | Pass | 04/22: regression retest & pass 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - ct code, dt updated, updated by are now disabled.
7 | 2026-01-30 | Both | Functionality | Major | Resolved | Court Control, Description, Value | Character Limits | Court Control NG window limits to 12, Existing window varies based on width of characters entered Data base limit is 12 Description Does not have limit, however, fluent validation appears if >255 Existing window varies based on width of characters entered Database limit is 255 Value Does not have limit, however, fluent validation appears if >255 Existing window varies based on width of characters entered Database limit is 255 | UI Guidelines ID #57; Current rule is to match front end limits; however, when it varies based on the character width, should no limit apply and only leave FluentValidation or use database limits? | 2026-04-30 | Pass | 03/18: cannot validate due to ID #30 04/22: Court Control field resolved, Description & Value fields still allow user to enter >255 characters; FluentValidation does not appear until user attempts to leave row (ENTER keypress) (see ID #35) 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - NG is currently using the database limit of control_code = 12, value = 255, descrip = 255 4/23/26 SM - set a character limit on the razor page instead of the fluent validation file Description=255, Value=255, Nbr=10, amount=15
8 | 2026-01-30 | Both | Functionality | Major | Resolved | Nbr | Character Limits | Does not have limit, no fluent validation appears if user exceeds 38 characters, data overrides to "9223372036854775807" Existing window limits to 10 numbers Data base limit is 38 | Issue previously occurred in Error Codes (ID #'s 6-7); Current rule is to match front end limits; however, when it varies based on the character width, should no limit apply and only leave FluentValidation or use database limits? | 2026-04-30 | Pass | 03/18: No FluentValidation displays when number >38 characters in field; if entered, all data is removed when user tabs out of field 04/22: Override with other numbers no longer occurs; Nbr field allows more than 10 characters, if >38 numbers are entered, field is cleared and cell turns red; field should not clear field and should display FV 04/28: FE limit is 9 digits, failing for 1234567890 04/30: retest test & pass, saves for 1234567890 | 4/23/26 SM - removed fluent validation. Added Nbr character limit is now 10
9 | 2026-01-30 | Both | Functionality | Major | Resolved | Amount | Character Limits | Does not have limit, no fluent validation appears Existing window allows for 999,999,999.99 Data base limit is (15,2) | User can attempt to save but errors out. Since it's not a required field, window should have character limit on front end. | 2026-04-30 | Pass | 04/22: regression bug (see ID 37) 04/28: see ID 42 04/30: retest & pass; can enter -1234567890123.45 successfully as this is DB limit | 4/23/26 SM - removed fluent validation. Added Amount character limit is now 15
10 | 2026-01-30 | Both | UI | Minor | Resolved | Description | Tooltip Placement | Can this be dynamic and appear where cursor is? If not, can we right justify the tooltip so it's within the description section |  | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/6/26 SM - tooltip placement has been set to Top Center. Entries that have less than 89 characters will not display tooltip when hovered.
11 | 2026-01-30 | Both | UI | Minor | Resolved | Value | Add Tooltip | Can we add a tooltip to this column? |  | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - added tooltip to value. Entries that have less than 35 characters will not display tooltip when hovered.
12 | 2026-01-30 | Both | UI | Minor | Resolved | Description | Tooltip Placement | Current location is on the bottom right of the cell so it overlaps with the Dt. Effective column. Can this be dynamic and appear where cursor is? If not, can we right justify the tooltip so it's within the description section |  | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/6/26 SM - tooltip placement has been set to Top Center.
13 | 2026-01-30 | Both | Functionality | Major | Resolved | Dt. Effective | Date FluentValidation missing | Able to save date prior to 01/01/1900 |  | 2026-04-30 | Pass | 03/18: retest pending until Add Row functionality fixed 04/22: retest and pass 04/28: see ID 43 04/30: see ID 45 | 3/19/26 SM - Added Fluent Validation to prevent dates from exceeding 12/31/1899. Need to revisit later Also need to discuss about strict mode. For example, the user enters 12/31/2124, before the fluent validation message appears, strict mode changes it to 12/31/2099. This might not be good to the user. Maybe we should get rid of it or discuss this? x
14 | 2026-01-30 | Both | Functionality | Major | Resolved | Dt. Invalid | Date FluentValidation missing | Able to save date past 12/31/2099 |  | 2026-04-30 | Pass | 03/18: retest pending until Add Row functionality fixed 04/22: retest and pass 04/28: see ID 43 04/30: see ID 45 | 3/19/26 SM - Added Fluent Validation to prevent dates from exceeding 01/01/2100. Need to revisit later x
15 | 2026-01-30 | Both | Functionality | Major | Resolved | Description | Latency in words appearing in field | Both windows experience latency when typing Description | UI Guidelines #8 | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/10/26 SM - issue addressed by turning on virtualization.
16 | 2026-01-30 | Both | UI | Minor | Resolved | Description | Bolded font missing after edit | Description field is the only row missing when exiting edit mode | UI Guidelines #31 | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - issue addressed. This occured because we had a new flavor (tooltips inside editable rows). CSS added globally for when row has visionchanged applies & is tooltip
17 | 2026-01-30 | Both | UI | Minor | Resolved | Description | After edit, ENTER key does not work to exit row | Current PB version allows for enter to be used to move curser to subsequent line within Description. If | UI Guidelines #55; workaround is that user must tab to a different field or click to exit edit mode | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/6/26 SM - removed textarea in favor for textbox
18 | 2026-01-30 | Both | UI | Major | Resolved | General | FluentValidation Messages appearing | 1. Enter New row with data, attempt to click out, the following messages appear: Court Control: Please enter Control Code. Description: Please enter Description. Dt. Effective: Please enter Dt. Effective. Nbr: Either Nbr, Amount, or Value column must be entered. 2. Enter value in Amount then tab: Either Nbr, Amount, or Value column must be entered. FluentValidation message remains and others disappear | FluentValidation messages that have not been addressed should remain and one(s) that have been addressed should be removed. Note: if I click away from row after fixing, the correct messages appear | 2026-04-30 | Pass | 03/18: retest pending until Add Row functionality fixed 04/22: retest and pass 04/28: see ID 43 04/30: see ID 46 | 2/10/26 SM - updated the fluent validation order validation messages as displayed.
19 | 2026-01-30 | Both | UI | Major | Resolved | General | FluentValidation Messages appearing in wrong Field | Enter Control Code with same value as existing row, message appears in Dt. Effective column "Record already exists. Please select different values for Court Control and Dt. Effective." | Validation should appear in Control Code cell, also not sure why the validation takes place at the Dt. Effective Cell | 2026-04-30 | Pass | 03/18: retest pending until Add Row functionality fixed 04/22: retest and pass 04/28: see ID 44 04/30: retest and pass | 2/5/26 SM - added validation to control code. Validation previously occured in dt effective because the validation needs both control code and dt. effective but fluent validation only can place it in one spot.
20 | 2026-01-30 | Both | Functionality | Major | Resolved | General | Edit Mode then Filter column abandons pending changes | 1. Open window with no filters applied 2. Open existing row in edit mode and make changes 3. Apply sorting filter on a column - pending changes should commit and row should be bolded. User can then open subsequent row in edit mode | Issue previously occurred in Error Codes (ID # 53); current NG window is abandoning pending changes when filter is applied | 2026-04-30 | Pass | 03/18: per daily NG meet, QA on pause until defects addressed 04/22: retest and pass; once leave exist mode and filter applied, pending changes remain 04/28: regression retest & pass 04/30: regression test and pass | 2/6/26 SM - added the helper.
21 | 2026-01-30 | Both | Functionality | Major | Resolved | General | Prevent Concurrent Updates missing on editing rows | 1. Update Description in Vision App. Save 2. Update Description of same row in Vision Web. Save - success | Issue occurs on all updateable fields when editing existing rows | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - concurrency issue has been addressed. Will throw an error now if you try saving same record.
22 | 2026-01-30 | Both | Functionality | Major | Resolved | Dt. Effective | Concurrent Update for Dt. Effective creates Duplicate Row | 1. Update Dt. Effective in Vision App. Save 2. Update Dt. Effective of same row in Vision Web. Save - success 3. Refresh - duplicate Control Code/row created with new Dt. Effective | Duplicate created while testing concurrent updates | 2026-04-30 | Pass | 04/22: user can make concurrent update on Dt. Effective and second row appears 04/28: retest & pass 04/30: regression retest & pass | 2/5/26 SM - concurrency issue addressed above. Please let me know if this still creates another record.
23 | 2026-01-30 | Both | Functionality | Major | Resolved | Nbr. | Cannot enter value less than 0 | PB window allows for "-20" but NG window displays "Nbr. must be 0 or greater" | Not clear why validation was added; see existing row AWSSPENDCNT with "-20" Nbr. Value | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/6/2026 SM - Fluent Validation has been added to Nbr column. FV now accepts negative Nbr and Amount
24 | 2026-01-30 | Both | Functionality | Major | Resolved | Amount | Cannot enter value less than 0 | PB window prevents "0.00" from being entered in the field but we have CRMP rows where the value for AMOUNT is "0" rather than NULL | See existing row DAYSERRLOG with "0" Amount value | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/5/26 SM - removed validation to prevent 0. Also see previous defect #24. Same wrong validation message/logic
25 | 2026-01-30 | Both | Functionality | Major | Resolved | Nbr., Amount | Disable Mouse Scrolling on Fields | Scrolling up increases value, scrolling down decreases value | Should not be enabled | 2026-04-30 | Pass | 04/22: see ID 39 04/30: regression retest & pass | 2/5/26 SM - numeric fields like amount, nbr are no longer allowed to use the mouse wheel.
26 | 2026-01-30 | Web Only | UI | Major | Resolved | Menu | Grouping | New grouping introduced on 01/30 where folders are labeled as different paths that are in Vision. Adding as line item to discuss |  | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/10/26 SM - Issue has been addressed. Grouping similar to vision
27 | 2026-01-30 | Web Only | UI | Major | Resolved | General | Profile | Determine LOE of adding profile and build number to web version, would help BSAs when testing other profiles and indicate when new releases have been completed |  | 2026-04-30 | Pass | 04/28: regression retest & pass 04/30: regression retest & pass | 2/10/26 SM - Issue addressed. Current web=5.02/API=5.02
28 | 2026-01-30 | Both | Functionality | Major | Resolved | General | Read-only profiles should not have access to launch MOCS Dfn. | PB window does not display button at all. Is there a way to remove for read-only profiles? If not, it needs to be disabled | Web version launches the "Under Construction" message, however, button should be removed. If cannot remove, it needs to be disabled | 2026-04-30 | Pass | 04/22: read only profiles (impact) can view and launch MOCS (VISSEC/MCDEFN) | 2/5/26 SM - removed MOCS button for readonly profiles
29 | 2026-03-18 | Both | UI | Minor | Resolved | General | Window Load | 1. Remove image from window load 2. Missing "Court Control Setup" before "Loading…" text 3. A smaller loading wheel is displaying ontop of the existing one. Screeshot attached for reference | The flash was fixed and now displays a white screen before displaying the window load page #3 only occurs in Vision app | 2026-04-30 | Pass | 04/28: regression retest & pass | 3/19 SM - has been addressed. Window name appears on load
30 | 2026-03-18 | Both | Functionality | Major | Resolved | Add Row | Add Row Functionality failing | Window freezes in both Vision and web when trying to add row |  | 2026-04-30 | Pass | 04/28: regression retest & pass | 3/19 SM - has been addressed. Incorrect data type caused crashing
31 | 2026-03-18 | Both | Functionality | Major | Resolved | Description, Amount | FluentValidation remaining after correcting value | 1. Value entered is > limit, tab 2. Green box highlights cell and FluentValidation displays 3. Correct issue and tab out of cell, red box highlights corrected cell and fluent validation remains | Should be removed once corrected | 2026-04-30 | Pass | 04/28: no longer occurrs as field character limits are implemented | 3/19 SM - validation now occurs whenever the user immediately changes focus from their column to another
32 | 2026-03-18 | Both | UI | Major | Resolved | General | Font size increases briefly when scrolling in rows | 1. Scroll slowly through rows until "ATP_ACT" Control Code is the first row 2. User sees font size temporarily enlarge then return to esmall size in various columns in window |  | 2026-04-30 | Pass | 04/28: regression retest & pass | 3/20 SM - has been addressed. Rendering issues caused a layout shift
33 | 2026-03-18 | Both | Functionality | Major | Resolved | Dt. Effective | Modifying field triggers delete message | After editing Dt.Effective date, user saves and save loading wheel displays over Validation Error "One or more validation errors occurred: - Only newly added rows can be deleted." | Validation does not make sense as I was not deleting row | 2026-04-30 | Pass | 04/28: regression retest & pass | 3/19 SM - has been addressed. Occured bcz in backend we delete and add new row for modifications on compositite keys.
34 | 2026-03-18 | Both | UI | Minor | No Action | Value, Dt. Updated | Cells missing highlight | 1. Edit Row with Value and delete Value 2. Tab out of field triggers FV 3. Click Nbr cell and enter valid number. 4. Tab out of Nbr cell to Value cell 5. ENTER keypress 6. F3 Refresh - select No 7. Repeat Steps 1-5 | Cosistently able to replicate missing Value and Dt. Updated highlights; occassionally can get all highlights to disappear except for Updated By - having trouble recreating this scenario | 4/22/026 | Pass with Comments |  | 3/19 SM - I believe this is the same bug we identified in code entry that we were going to disregard 3/20 SM - leave as it
35 | 2026-04-22 | Both | Functionality | Major | Resolved | Description, Value | Character Limits | 1. User enters >255 characters and tabs/clicks next field 2. Cell turns red but Fluent Validation does not appear | If ENTER keypress is used, then then FV is triggered. Shouldn't the FV be triggered upon leaving the field? | 2026-04-30 | Pass | 04/22: limit front end to 255 characters 04/28: see ID 40, 41 | 4/23/26 SM - limited description/value to 255 characters
36 | 2026-04-22 | Both | UI | Minor | Resolved | Control Code, Description, Dt. Effective | Missing Underline on required value column headers | Fields are required and should be identified with underline in column headers | UI Guidelines #96; recently added guideline from decision made in Bail Schedule QA | 2026-04-30 | Pass | 04/30: regression test & pass | 4/23/26 SM - added underlining to the grid columns that are required. (control code, description, dt. effective)
37 | 2026-04-22 | Both | Functionality | Regression | Resolved | Amount | Character Limits | Does not have limit, no fluent validation appears Existing window allows for 999,999,999.99 Data base limit is (15,2) | Previously corrected to allow for FV to limit to (15,2) 9,999,999,999,999.99 see image right on 02/06/26. User can now only enter (12,2) 123,456,789,012.34 | 2026-04-30 | Pass | 04/28: see ID 42 | 4/23/26 SM - removed fluent validation. Added Amount character limit is now 15
38 | 2026-04-22 | Both | Functionality | Minor | Resolved | Date Fields | Values are overriding | Invalid dates are being overridden with min/max dates so user never sees FV entry | Can we leave the invalid dates in the fields so that user has the chance to go back and fix entry? | 2026-04-30 | Pass | 04/28: see ID 40, 41 | 4/23/26 SM - removed StrictMode for date inputs in vision date component. Will be reflected across all windows currently using vision date components
39 | 2026-04-22 | Both | Functionality | Major | Resolved | Nbr, Amount | Disable Arrow Keys on Fields | Arrow up keypress increases value, arrow down keypress decreases value | Should not be enabled | 2026-04-30 | Pass |  | 4/23/26 SM - added step='0' to disable arrow up/down
40 | 2026-04-28 | Both | Functionality | Regression | Resolved | Dt. Effective/ Dt. Expires | FluentValidation not appearing for invalid values | 1. Enter invalid date value for Dt. Effective or Dt. Invalid 2. Use TAB keypress to move to next cell | Cell highlights to green which is incorrect since the values are invalid Once ENTER keypress is used, then then FVs are triggered Expected behavior is when user leaves cell (tab, clicks, enter keypress), the FV should appear; this was previously reported in ID 35 | 2026-04-30 | Pass | 04/30: see ID 43 | 04/29/26 SM - has been addressed
41 | 2026-04-28 | Both | Functionality | Regression | Resolved | Nbr | FluentValidation incorrectly appearing | 1. Enter 10 digits for Nbr (e.g., 1234567890) | Cell highlights to green which is incorrect since the values are invalid Once ENTER keypress is used, then then FVs are triggered Unclear why FV is triggered when 1234567890 is 10 digits | 2026-04-30 | Pass |  | 04/29/26 SM - has been addressed
42 | 2026-04-28 | Both | Functionality | Regression | Resolved | Amount | FluentValidation incorrectly appearing | If 15 digits are entered (123456789012345), format updates to add ".00" at end totalling 17 digits (123456789012345.00) therefore input fails If user tries to format with decimal, they are shorted 1 number and can only enter 14 (1234567890123.4) | Seems that decimal is counted towards FE limit - can this be fixed? Issue occurs if negative symbol or decimal used | 2026-04-30 | Pass |  | 04/29/ SM - added max length to 17 characters + added Fluent validation that only permits 13 whole numbers and 2 decimal as per database limit.
43 | 2026-04-28 | Both | Functionality | Regression | Resolved | Dt.Effective | FluentValidation displaying wrong message | If invalid value entered in Dt. Effective field, message says "Invalid date must be between 12/31/1899 and 01/01/2100." | 1. Dt. Effective should have a different message 2. Shouldn’t min/max dates be 01/01/1900 and 12/31/2099"? | 2026-04-30 | Pass |  | 04/26/26 SM - modified FV message for Dt. Effective and Dt. Invalid
44 | 2026-04-28 | Both | Functionality | Regression | Resolved | Control Code | FluentValidation appearing late | If user enters existing value in Control Code, it doesn't appear until the rest of the values are entered | Shouldn't this be first? | 2026-04-30 | Pass |  | 04/29/26 SM - has been addressed
45 | 2026-04-30 | Both | Functionality | Major | Resolved | Dt. Effective | FluentValidation disappearing when existing Court Control value is entered | 1. User enters existing Court Control value (e.g., ZTEST8) 2. User enters Description, then enters invalid Dt. Effective 3. TAB keypress used - FV briefly appears, disappears, cell turns green, and user can continue | 1. FV should remain until Dt. Effective fixed and FV for Court Control should appear, or 2. FV should remain until Dt. Effective fixed, then display FV for Court Control as that needs to be fixed | 2026-04-30 | Pass | 04/30: fixed in PM build, retest and pass
46 | 2026-04-30 | Both | Functionality | Major | Resolved | Nbr. | Cannot enter 10 digit negative value | User can only enter "-123456789" in field - should they be able to enter additional digit? Seems to be similar issue to ID #42 | User can tab through all fields without FVs appearing | 2026-04-30 | Pass | 04/30: fixed in PM build, retest and pass
47
48
49
50
51
52
53
54

## SUMMARY
|  | Count of Scenario Type | Column Labels
|  | Row Labels | Resolved | No Action | Grand Total
1 | 8:00 | 2026-01-30 | 28 |  | 28 | Row Labels | Count of Bug Type | Row Labels | Count of Status
|  | Functionality | 18 |  | 18 | Major | 27 | Resolved | 45
|  | Major | 15 |  | 15 | Minor | 13 | No Action | 1
|  | Minor | 3 |  | 3 | Regression | 6 | Grand Total | 46
|  | UI | 10 |  | 10 | Grand Total | 46
|  | Major | 4 |  | 4
|  | Minor | 6 |  | 6
2 | 4:00 | 2026-03-18 | 5 | 1 | 6
|  | Functionality | 3 |  | 3
|  | Major | 3 |  | 3
|  | UI | 2 | 1 | 3
|  | Major | 1 |  | 1
|  | Minor | 1 | 1 | 2
3 | 4:00 | 2026-04-22 | 5 |  | 5
|  | Functionality | 4 |  | 4
|  | Major | 2 |  | 2
|  | Minor | 1 |  | 1
|  | Regression | 1 |  | 1
|  | UI | 1 |  | 1
|  | Minor | 1 |  | 1
4 | 2:00 | 2026-04-28 | 5 |  | 5
|  | Functionality | 5 |  | 5
|  | Regression | 5 |  | 5
5 | 1:00 | 2026-04-30 | 2 |  | 2
|  | Functionality | 2 |  | 2
|  | Major | 2 |  | 2
|  | Grand Total | 45 | 1 | 46

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action