## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-09-30 | Both | Functionality | Minor | No Action | Field Input | Field Input data do not register | When type into a data field and tab, it deletes the entry. It must be selected by using a mouse click.
2 | 2026-10-05 | Both | UI | Minor | No Action | Input Field | Field data input by keystroke | Typing the data directly instead of using the filter selection will not be recognized.
3 | 2026-10-05 | Both | UI | Minor | Resolved | Row highlight | Row selection highlight | When a row is selected in the grid, the entire row highlights in blue instead of the checkbox being checked. |  | 2026-10-07 | Pass |  | Fixed
4 | 2026-10-05 | Both | UI | Minor | Resolved | Hearing/ROC | Code showing for hearing/ROC type | The Hearing/ROC column is displaying codes instead of descriptions. May be retrieving the data from the Code Entries table instead of the Event Code table. | H14-09/16/2025 Displaying "AAC" for "Arraignment and Court Trial". | 2026-10-07 | Pass |  | Fixed
5 | 2026-10-05 | Both | UI | Minor | Resolved | Hearing Date | TO section's Hearing Date selection | In the TO section, after selecting the Court and tab, the system automatically selects and highlights “Hearing Date.” Since this field is not configurable, it should not be selected or highlighted. Tab to Move button instead. |  | 2026-10-07 | Pass |  | Fixed
6 | 2026-10-05 | Both | UI | Minor | Resolved | F3-Refresh | Inconsistent refresh(F3) behavior | When REFRESH (F3) is used, the search fields should clear, consistent with the behavior in Calendar Transfer. Additionally, F3 does not function when a grid row is selected. And creates black border. Remove the black border. To replicate: Select any row in the grid and press F3. |  | 2026-10-07 | Pass |  | Fixed
7 | 2026-10-05 | Both | UI | Minor | No Action | Microhelper | No microhelper status | Microhelper isn't displaying the progress. Legacy Status: Moving case xxxxxxxxx When COURT field is selected from FROM section, then the status displays as "From Court". When HEARING DATE fiels is selected from FROM section, then the status displays as "Hearing Date". When COURT field is selected from TO section, then the status displays as "To Court". |  | 2026-10-07 | Pass with Comments | The NG window processes too quickly to be seen. | Not fixed
8 | 2026-10-05 | Web Only | Functionality | Minor | Resolved | Close button | Close button won't close | Remove CLOSE button from Web only. |  | 2026-10-07 | Pass |  | Fixed
9 | 2026-10-05 | Both | Functionality | Minor | Resolved | Error | Fluid UI Error Display | When no input is selected and the MOVE button is clicked, the first error displayed appears in the TO section instead of the FROM section. Additionally, when REFRESH (F3) is used, the FROM section’s COURT field is automatically selected and the error is displayed. F3 REFRESH also does not clear the existing error tooltips. Expected results: 1) If RETRIEVE button is used, it should display the fluid UI error messages for any fields that are mandatory in FROM section. 2) If MOVE button is used, it should display the fluid UI error messages for any fields that are mandatory in both FROM & TO sections. 3) Fluid UI error message only works on COURT fields, all other fields use red border instead. Make all other areas display the same fluid UI errors. | It appears that the F3 is using the validation prior to actually refreshing the screen and it locks the window until you correct the field. | 2026-10-07 | Pass | Additional defects listed #12, 13, 14
10 | 2026-10-05 | Both | UI | Minor | Resolved | TO section | Expand the width | Expand the width of the TO section to display all the columns. |  | 2026-10-07 | Pass | Need additional width expansion. #14 | Fixed
11 | 2026-10-05 | Both | UI | Minor | Resolved | Window rows | Expand the height | Expand the height to display more rows. |  | 2026-10-08 | Pass | Bottom margin needs expanded to match the top & side for PB window, Web is ok. | Fixed
12 | 2026-10-07 | PB Only | UI | Minor | Resolved | Error msg | Multiple error msgs | MOVE >>> F3 >>> MOVE Generates multiple errors. If MOVE button is used and Hearing Date field is null in TO section, then multiple error msgs display. This results in multiple error msgs. Expected result: Single 1st error to display. |  | 2026-10-08 | Pass |  | Fixed
13 | 2026-10-07 | Both | UI | Minor | Resolved | Hearing Date | TO section's Hearing Date Field | When F3 is used, Hearing Date field behaves differently each time. It appears that it cycles from default sysdate to null. |  | 2026-10-08 | Pass |  | Fixed
14 | 2026-10-07 | Both | UI | Minor | Resolved | Column Widths | Hearing/ROC column width | Hearing/ROC column width should be expanded on both FROM/TO sections. Expand the entire window width or reduce other columns to accommodate. |  | 2026-10-08 | Pass
15 | 2026-10-07 | Both | Functionality | Minor | Resolved | CLTRAN2 docket code time format | Time format issue | When MOVE button is used, CLTRAN2 docket code enters using the HH:MM time format, 01:30 PM. Remove leading zero to be consistent with other NG windows. |  | 2026-10-08 | Pass
16 | 2026-10-08 | Both | UI | Minor | Resolved | Error msg | Data field error msgs | Date field errors are displaying beyond the window height, so they are hidden. |  | 2026-10-08 | Pass
17 | 2026-10-26 |  |  | Minor | New |  | [UAT #1] I receive an error message when transferring cases. | I receive an error message when transferring cases. | From UAT Defect Log - COURT TRIAL TRANSFER #1 (Operations; reporter Katrina; tester Katrina).
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action