## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-02-26 | Both | UI | Minor | Resolved | Window | White bar on top of window | Gradient background begins at the blue border. Expected result is the gradient background appears at the top of the window | Appears when Blazor courtroom is not the first window opened for the day. This white space is not visible, and the blue border is at the top of the window during the first open. | 2026-04-15 | Pass |  | 3/23 SM - has been addressed.
2 | 2026-02-26 | Both | UI | Minor | Resolved | Window | No space top of window | During first window open of the day, the blue border is at the top of the window. | This behavior does not match ID 1 behavior. | 2026-04-15 | Pass |  | 3/26 SM - has been addressed.
3 | 2026-02-26 | Both | UI | Minor | No action | Courtroom field | Dropdown Order | Dropdown order is alphabetic | Dropdown order is alphabetic by capital letters, then lowercase letters. For example, CJC displays before Central |  |  | 3/17/26 - leave as is | 3/18 SM - leaving as is
4 | 2026-02-26 | Both | Functionality | Minor | Resolved | Reporter field | Blank display | If reporter field displays the person_nbr in database, the new window displays blank. See Collections - Newport Beach in QA | The old window displays the person_nbr instead of the reporter name. This issue may occur for other fields if the number is retrieved instead of the name. This behavior should not occur often | 2026-04-15 | Pass |  | 4/13 SM - has been addressed
5 | 2026-02-26 | Both | UI | Minor | Resolved | Save button | Save button selectable | When Courtroom field is selected, Save button is selectable | Save button becomes selectable once a change is made. | 2026-04-15 | Pass with Comments | 4/15 BY: See defect 23 | 3/17 SM - modified. Now save button is active once courtroom is selected
6 | 2026-02-26 | Both | UI | Minor | Resolved | Cause Type | Cause Type blank option | Cause type has a blank option field available | PB window has the 3 cause types only | 2026-04-15 | Pass |  | 3/16 SM - has been addressed. Removed blank option
7 | 2026-02-26 | Both | UI | Minor | Resolved | Window | Field Height | Field height for Clerk and Bailiff does not match other fields | May relate to Defect 15. Field height appears to increase once courtroom field is selected | 2026-04-15 | Pass |  | 3/16 SM - has been addressed. Clerk and Bailiff are custom dropdown because. Styling has been adjusted to match the rest
8 | 2026-03-02 | Both | Functionality | Major | Resolved | Print Button | Print Button does not work | Print button and File > Print in web version do not print |  | 2026-04-15 | Pass |  | 3/26 SM - printing has been removed
9 | 2026-03-02 | Web Only | UI | Minor | Resolved | Ctrl + P Layout | Layout excludes fields | The left hand menu bar, along with some but not all of the Courtroom Setup fields display in 1 page of the print preview. |  | 2026-04-15 | Pass with Comments | 4/15 BY: See defect 21 | 3/26 SM - printing has been removed
10 | 2026-03-02 | PB Only | UI | Major | Resolved | Ctrl + P Layout | Layout excludes fields | Some but not all fields display in the print preview. | View appears to be a zoomed in Version of the NG window rather than the view from Vision. | 2026-04-15 | Pass with Comments | 4/15 BY: See defect 21 | 3/26 SM - printing has been removed
11 | 2026-03-02 | Both | UI | Major | Resolved | Print Button and Ctrl + P | Watermark is missing | After printing with Print button or Ctrl + P, watermark is missing. | Watermark will appear if WMPRINT court control is 'Y'. This value is 'Y' in all regions except production. | 2026-04-15 | Pass with Comments | 4/15 BY: See defect 21 | 3/26 SM - printing has been removed
12 | 2026-03-02 | Both | UI | Minor | Resolved | Window | Read only field visibility | Grey read only fields are hard to differentiate with the lighter gradient in the background | May be helpful to add more space between each field, or a slightly darker grey border around the fields | 2026-04-15 | Pass |  | 3/16 SM - replaced enabled=false to readonly=true. Previous styling was before UI Guideline
13 | 2026-03-02 | Both | UI | Major | Resolved | Window | Resizing window causes field alignment issues | Minimizing vision window and adjust width or height causes sections to overlap |  | 2026-04-15 | Pass |  | 3/17 SM - has been addressed. window is now responsive
14 | 2026-03-06 | Both | UI | Minor | Resolved | F3 Refresh | F3 Refresh Courtroom field | F3 refresh does not clear the Courtroom field |  | 2026-04-21 | Pass | 4/15 BY: Defect still exists. Defect 22 is related. | 4/16 SM - refresh F3 clears out the courtroom field and all other fields + disables save button
15 | 2026-03-06 | Both | UI | Minor | Resolved | Courtroom field | Grid expands | When Courtroom field is selected, the bottom edge of the form expands | This may relate to Defect 7. These two fields match the height of other fields before courtroom is selected | 2026-04-15 | Pass |  | 3/17 SM - has been addressed. Layout shift occoured bcz height would change due to incoming data. Fields now have a minimum set height to avoid this.
16 | 2026-03-06 | Both | UI | Minor | Resolved | Field Labels | Field labels have inconsistent alignment with field | Field labels should be middle aligned with the field per UI Guideline 88 | UI Guideline 88 was added after template was created/ updated. | 2026-04-15 | Pass |  | 3/16 SM - has been addressed. Field labels have been center aligned.
17 | 2026-03-17 | Both | UI | Minor | Resolved | Button | Button type | Button type should be Primary button type - Blue with white text | UI Guideline 7 | 2026-04-15 | Pass |  | 3/17 SM - has been addressed. Buttons are blue. Reset button is grey until user can reset the form
18 | 2026-03-18 | Both | UI | Minor | Resolved | Window border | Window border thickness does not match other windows | Window border height/ width should match the smaller sections, and other window sections | UI Guideline 90 was added after issue was identified | 2026-04-15 | Pass |  | 3/26 SM - has been addressed.
19 | 2026-04-15 | Both | Functionality | Minor | Resolved | Window | Data loads at different times | The 'Courtroom' field selection updates before the rest of the fields. This causes the data to temporarily mismatch if a courtroom was selected. |  | 2026-04-23 | Pass | 4/16 BY: Devs will add a loading wheel. The window will have 65% opacity while the loading wheel is present. | 4/16 SM - loading screen has been applied for when user modifies courtroom drop down menu. It is 65% (Partial) opacity
20 | 2026-04-15 | PB Only | UI | Minor | Resolved | Updated and By fields | Text size does not match other window areas | Value font size is larger than the field label font size. The value should match the font size. |  | 2026-05-08 | Pass | 4/21: Defect still exists | 4/23 SM - targeted the body element to set size to 13px globally.
21 | 2026-04-15 | Both | Functionality | Regression | Resolved | Print Feature | Printing is enabled | Ctrl + P short key works for blazor window. Previous decision was to remove the print functionality. |  | 2026-05-08 | Pass | 4/15: Print was enabled in all windows to test print functionality. Devs will remove this in the next QA iteration. 4/21: Ctrl + P is not disabled in latest QA version | 4/23 SM - used stopImmediatePropogation to prevent javascript default event from triggering default print. Need to reload JS to fix
22 | 2026-04-15 | Both | UI | Regression | Resolved | Save button | Save button is selectable on window open | Save button is selectable on window open. Save button should not be selectable until the Courtroom option is selected | This definition was not clear in Defect ID 5. BSA error. | 2026-04-21 | Pass |  | 4/16 SM - saving button becomes interactable after initial courtroom selection
23 | 2026-04-15 | Both | UI | Major | No Action | All field and search values | Bottom right shift | All field values and search values are bottom aligned. These should be middle aligned | This issue occurs across blazor windows, including windows in production. |  |  | 4/15: Alignment will remain as is | 4/16 SM - leave as is
24 | 2026-04-15 | Both | Functionality | Regression | Resolved | F3 Refresh | F3 Refresh Courtroom field - no pending changes | F3 refresh does not work if Courtroom is selected, and there are no pending changes. |  | 2026-04-21 | Pass |  | 4/16 SM - refresh F3 now works when courtroom is/is not selected and when there is/is not pending changes
25 | 2026-04-15 | Both | UI | Minor | Resolved | Updated Field | Updated field label alignment | Updated field label should be aligned with the other labels. By field can be moved right if needed. |  | 2026-04-21 | Pass |  | 4/16 SM - update label has been vertically aligned with other labels
26 | 2026-04-21 | Both | Functionality | Major | Resolved | Courtroom field | Dropdown Options remain after search | 1. Click Courtroom Field 2. Type Search criteria like 'Z1' 3. Press Enter - Courtroom Field is empty 4. Click Courtroom Field again - Dropdown only displays results related to 'Z1'. |  | 2026-05-08 | Pass | 4/23: Syncfusion issue. Previously addressed in Event Codes 4/27: Syncfusion ticket #830463 expected rollout for 5/5/26 | 4/23 SM - removed Syncfusion workaround for ticket #828779 | ticket
27 | 2026-05-08 | Both | Functionality | Major | Resolved | Multiple Fields | Unit Codes updates | 1. Add unit code for clerk, judicial officer, etc. 2. Open Courtroom Setup, and select applicable dropdown - newly added staff appears 3. Remove unit code for applicable staff 4. Refresh Courtroom Setup, or reopen courtroom setup - staff appears until cache is cleared | PB window shows updates after closing and reopening the window since refresh is not available | 2026-05-13 | Pass |  | 5/8/26 SM - has been addressed
28 | 2026-05-08 | Both | UI | Minor | Resolved | Courtroom field | Courtroom field and label alignment | Courtroom field and label should be middle aligned with the section. Currently, the field label and field are slightly towards the top of the section |  | 2026-05-13 | Pass |  | 5/8/26 SM - has been addressed, removed bottom margin.
29 | 2026-05-13 | Both | UI | Minor | Resolved | Fields with Names | Full name flashes before applicable format | 1. Open Courtroom Setup 2. Select a courtroom with clerk or bailiff - Courtroom flashes after the loading wheel dissapears | Expected result is the correct format appears when the loading wheel disappears | 2026-05-15 | Pass | 5/14: Upcoming QA fix for this issue results in the dropdowns appearing in the disabled fields. See Screenshots tab ID 29 - before fix, and 29 - after fix | 5/14/26 SM - has been addressed
30 | 2026-06-29 | Both | UI | Minor | Resolved | Various Fields | Courtroom name updates before child record | When a user changes the courtroom by typing and selecting it from the search field, only the courtroom name updates while the remaining courtroom details continue to display information from the previously selected courtroom. This issue does not occur when the courtroom is selected by scrolling through the list. |  | 2026-07-07 | Pass | UAT Defect
31 | 2026-07-02 | Both | UI | Minor | Resolved | Various Fields | Incorrect dropdown value appears | When selecting a field, such as "Judicial Officer" or "Clerk," the initial attempt does not update the selection, resulting in a blank field. However, on the second attempt, the field updates correctly after being left blank. |  | 2026-07-07 | Pass | UAT Defect
32 | 2026-07-07 | Both | UI | Regression | Resolved | Courtroom field | Starts with search | Courtroom field uses "contains" search instead of "Starts with" updates from VisionDropdownList |  | 2026-07-09 | Pass
33
34
35
36
37
38
39
40
41
42
43
44
45
46

## Screenshots
Defect ID | Screenshots
29 - before fix
29 - after fix

## Test Scenarios
ID | Type | Test Scenario | Expected Result | Test Date - QA 1 | PF - QA 1 | Comments
1 | Functionality | Window load time close to PB load time |  | 2026-02-26 | Pass
2 | UI | Courtroom field dropdown is editable on window load |  | 2026-02-26 | Pass
3 | UI | Save and Reset buttons are greyed out on window load |  | 2026-02-26 | Pass
4 | UI | Fields below Courtroom are read only before window load |  | 2026-02-26 | Pass
5 | UI | Active courtrooms appear in Courtroom dropdown with black |  | 2026-02-26 | Pass
6 | UI | Inactive courtrooms appear in Courtroom dropdown with light grey text |  | 2026-02-26 | Pass
7 | Functionality | When Courtroom field is selected, all remaining fields except for location unit are editable |  | 2026-02-26 | Pass
8 | Functionality | When Courtroom field is selected, Location Unit is read only |  | 2026-02-26 | Pass
9 | Functionality | 2nd row menu options are Print and Close |  | 2026-04-15 | Pass | Removed 'Print' option
10 | Functionality | Edit and Action top level menus are not available |  | 2026-02-26 | Pass
11 | UI | Updated field displays MM/DD/YYYY HH:MM AM format |  | 2026-02-26 | Pass
12 | UI | By field displays Last Name, First Name format |  | 2026-02-26 | Pass
13 | Functionality | Courtroom field selection loads instantly |  | 2026-02-26 | Pass with Comments | 1-3 seconds in Blazor
14 | Functionality | Courtroom field is selected | Judicial Officer field populates data when expected | 2026-04-15 | Pass
15 | Functionality | Courtroom field is selected | Clerk field populates data when expected | 2026-04-15 | Pass
16 | Functionality | Courtroom field is selected | Bailiff field populates data when expected | 2026-04-15 | Pass
17 | Functionality | Courtroom field is selected | Reporter field populates data when expected | 2026-04-15 | Pass | See defect 3
18 | Functionality | Courtroom field is selected | DA field populates data when expected | 2026-04-15 | Pass
19 | Functionality | Courtroom field is selected | PD field populates data when expected | 2026-04-15 | Pass
20 | Functionality | Courtroom field is selected | Interpreter field populates data when expected | 2026-04-15 | Pass
21 | Functionality | Courtroom field is selected | Cause Type field populates data when expected | 2026-04-15 | Pass
22 | Functionality | Courtroom field is selected | all fields update with the new data | 2026-04-15 | Pass
23 | Functionality | Courtroom field is selected | all fields can be blank | 2026-04-15 | Pass
24 | UI | Courtroom field is selected | Save button is selectable | 2026-04-15 | Fail | See defect 4 23
25 | UI | Location Unit field matches location_unit data exactly without formatting |  | 2026-04-15 | Pass
26 | UI | Judicial Officer field is formatted First Initial Last Name |  | 2026-04-15 | Pass
27 | UI | Bailiff field is formatted First Initial Last Name |  | 2026-04-15 | Pass
28 | UI | Reporter field is formatted Last Name, First Name |  | 2026-04-15 | Pass
29 | UI | DA field is formatted Last Name, First Name |  | 2026-04-15 | Pass
30 | UI | PD field is formatted Last Name, First Name |  | 2026-04-15 | Pass
31 | UI | Interpreter field is formatted Last Name, First Name |  | 2026-04-15 | Pass
32 | UI | Cause type field retrieves descriptions from CAUSTP code entry table |  | 2026-04-15 | Pass
33 | Functionality | All fields, except Cause Type and Courtroom, have a blank selectable row |  | 2026-04-15 | Pass | See defect 5
34 | Functionality | Close window with pending changes | PB pending changes message appears | 2026-02-26 | Pass
35 | Functionality | New Courtroom added with Courtroom unit qualifier | New courtroom appears in Courtroom dropdown | 2026-02-26 | Pass
36 | Functionality | Select PB print button | Print preview appears | 2026-03-02 | Fail | See defect 8
37 | Functionality | Ctrl + P | Print preview appears | 2026-03-02 | Pass
38 | UI | Printed image layout is similar to PB layout |  | 2026-03-02 | Fail | See defect 9 and 10
39 | UI | Print with Ctrl + P or Print button, then return to Vision window | Watermark appears on notices if WMPRINT court control variable is 'Y'. Watermark does not appear otherwise | 2026-03-02 | Fail | See defect 11
40 | UI | Window is left aligned |  | 2026-03-02 | Pass
41 | Functionality | Modify field | Reset button is selectable | 2026-03-02 | Pass
42 | Functionality | Modify field, then select Reset | All modified values are reverted | 2026-03-02 | Pass
43 | Functionality | Modify field, then select Save | All modified values save, Updated field fields reflects new date and time for update, By: field display the name of the person saving changes | 2026-03-02 | Pass
44 | UI | Field widths match PB |  | 2026-03-03 | Pass
45 | UI | Field heights match Blazor UI Guidelines |  | 2026-04-15 | Pass | See defect 7
46 | Functionality | Courtroom setups display in Calendar List defaults tab |  | 2026-03-06 | Pass
47 | Functionality | F3 refresh with no pending changes | Courtroom search is cleared | 2026-03-06 | Fail | See defect 14
48 | Functionality | F3 refresh with pending changes, select No | Pending changes message appears. When no is selected, old data appears | 2026-03-06 | Pass
49 | Functionality | F3 refresh with pending changes, select Yes | Pending changes message appears. When yes is selected, changes save, and Updated: / By: fields are updated | 2026-03-06 | Pass
50 | Functionality | Modify field, then switch courtroom | Pending changes message appears | 2026-03-06 | Pass
51 | Functionality | Modify field, switch courtroom, select No, switch courtroom to the original | Courtroom setup data refreshes | 2026-03-06 | Pass
52 | Functionality | Select Save button | Changes save, Save toast message appears | 2026-03-09 | Pass
53 | Cache Issue | Cache Issue
54
55
56
57
58
59
60
61
62
63

## Summary
QA Round 1 - 4.5 Hr
Date Tested | (All)
Count of Status |  | Status
Scenario Type | Bug Type | New | No action | Grand Total
Functionality | Major | 1 |  | 1
| Minor | 1 |  | 1
Functionality Total |  | 2 |  | 2
UI | Major | 3 |  | 3
| Minor | 12 | 1 | 13
UI Total |  | 15 | 1 | 16
Grand Total |  | 17 | 1 | 18
QA Round 2 - 2.5 Hr* | [5 empty] | *Below QA Round 2 counts are more accurate than pivot table on the left. Table data refreshed during QA Round 3
Count of Status |  | Status |  |  |  | #QA Bug Major | #QA Bug Minor | #QA Bug Regression | #QA Cycle | Open Defects | No Action Defects | Resolved Defects
Scenario Type | Bug Type | New | No action | Resolved | Grand Total | 5 | 17 | 3 | 2 | 8 | 1 | 16
Functionality | Major | 1 |  | 2 | 3
| Minor |  |  | 2 | 2
| Regression |  |  | 2 | 2
UI | Major |  | 1 | 3 | 4
| Minor | 1 | 1 | 14 | 16
| Regression |  |  | 1 | 1
Grand Total |  | 2 | 2 | 24 | 28
QA Round 3 - 2 Hr | [5 empty] | *Below QA Round 3 counts are more accurate than pivot table on the left. Table data refreshed during QA Round 4
Count of Status |  | Column Labels |  |  |  | #QA Bug Major | #QA Bug Minor | #QA Bug Regression | #QA Cycle | Open Defects | No Action Defects | Resolved Defects
Row Labels | Bug Type | New | No action | Resolved | Grand Total | 6 | 17 | 3 | 3 | 3 | 2 | 21
Functionality | Major | 1 |  | 2 | 3
| Minor |  |  | 2 | 2
| Regression |  |  | 2 | 2
UI | Major |  | 1 | 3 | 4
| Minor | 1 | 1 | 14 | 16
| Regression |  |  | 1 | 1
Grand Total |  | 2 | 2 | 24 | 28
QA Round 4 - 1.5 Hr
Count of Status |  | Status
Scenario Type | Bug Type | New | No action | Resolved | Grand Total
Functionality | Major | 1 |  | 2 | 3
| Minor |  |  | 2 | 2
| Regression |  |  | 2 | 2
UI | Major |  | 1 | 3 | 4
| Minor | 1 | 1 | 14 | 16
| Regression |  |  | 1 | 1
Grand Total |  | 2 | 2 | 24 | 28
QA Round 5 - 1.5 Hr
Count of Status |  | Status
Scenario Type | Bug Type | No action | Resolved | Grand Total
Functionality | Major |  | 3 | 3
| Minor |  | 2 | 2
| Regression |  | 2 | 2
UI | Major | 1 | 3 | 4
| Minor | 1 | 16 | 17
| Regression |  | 1 | 1
Grand Total |  | 2 | 27 | 29
QA Round 6 - 1.5 Hr
Count of Status |  | Status
Scenario Type | Bug Type | No action | Resolved | Grand Total
Functionality | Major |  | 3 | 3
| Minor |  | 2 | 2
| Regression |  | 2 | 2
UI | Major | 1 | 3 | 4
| Minor | 1 | 18 | 19
| Regression |  | 2 | 2
Grand Total |  | 2 | 30 | 32
QA Round 6 - 1.5 Hr
Count of Status |  | Status
Scenario Type | Bug Type | No action | Resolved | Grand Total
Functionality | Major |  | 3 | 3
| Minor |  | 2 | 2
| Regression |  | 2 | 2
UI | Major | 1 | 3 | 4
| Minor | 1 | 18 | 19
| Regression |  | 2 | 2
Grand Total |  | 2 | 30 | 32

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action