## DEFECTS
ID | QA Cycle | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Section(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 1 | 2026-09-14 | Both | UI | Minor | New | Date results | Top align data in every columns | Date in all columns in "From" and "To" sections to top align. |  | 2026-09-16 | Pass |  | Fixed
2 | 1 | 2026-09-15 | Both | UI | Minor | New | Date Fields | Date input fields does not input correctly | Date input fields do not type properly and it may consult leap year even before inputting the year. When typed "02/29…", it automatically increases to "03/01…" |  | 2026-09-16 | Pass with Comments | This issue appears to be consistent in all date fields. Will bring it up during the NG meeting. This issue is not limited to Date of Action window.
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action