## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | NG Display/Scenario | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2025-10-03 | Both | Functionality | Major | Resolved | Window | Initial loading time | NG window takes about 5 seconds to load | Current window is immediate | 2025-11-24 | Pass | 10/03: ST NG - immediate; QA NG - delay 10/21: Still a delay in CRMD/CRMQ (~5 seconds) 10/29: in progress 11/18: Still a delay in CRMD/CRMQ (~4 seconds) 11/24: ok as is 12/04: still ok as is; noting that web version is faster than Vision app when loading
2 | 2025-10-03 |  | Functionality | Minor | Resolved | Window | Highlighted rows | Blue highlight appears to be behind the cells for a selected row - more difficult to read | Current window highlights entire row blue including cells | 2025-10-21 | Pass | 10/03: Follow-up 10/21: See ID #22
3 | 2025-10-03 |  | Functionality | Major | Resolved | Error Nbr | Entering value less than 40000 | 1. User enters Error Nbr value less than 40000 (e.g., 4001) 2. User tabs/clicks out of field to enter next element > Error Nbr field resets to '0' > Error Number window appears with "Please enter a number higher than 40000!" 3. User selects OK, returns to Error Codes window and fills out remaining elements allowing user to attempt a save 4. After attempt: Validation Error message window appears "One or more validation errors occurred: Error number is required" | Current window prevents user from continuing until valid Error Nbr is entered; if value doesn't meet validations, data remains for user to correct (does not reset) | 2025-10-21 | Pass | 10/03: Retain original value (tab out); highlight first row that is failing
4 | 2025-10-03 |  | Functionality | Major | Resolved | Error Nbr | Entering existing value | 1. User adds new row and uses existing Error Nbr value 2. User tabs/clicks out of field to enter next element > Error Nbr field resets to '0' > Error Number window appears with "Code exists. Please enter another value!" | Current window does not reset Error Nbr value | 2025-10-21 | Pass | 10/03: Retain original value (tab out); highlight first row that is failing
5 | 2025-10-03 |  | Functionality | Minor | Resolved | Error Nbr | Default value for newly added row | When adding new row, default value is "0" | Current window has NULL default value | 2025-10-21 | Pass | 10/03: Fixed
6 | 2025-10-03 |  | Functionality | Major | Resolved | Error Nbr | No character limit, overridden values | No character limit Enter 12345678901234567890 (20 characters), tab out, value udpates with "92233782036854775807" | Current window does not allow user to enter more than 8 numbers; if tab out of field, value remains and does not override with random numbers | 2025-10-21 | Pass | 10/03: Updated to 8 characters 10/21: See #23
7 | 2025-10-03 |  | Functionality | Major | Resolved | Error Nbr | Character Limit | Able to save 19 numbers (92233782036854775807) | After saving, existing Error Codes window fails | 2025-10-21 | Pass | 10/03: Updated to 8 characters
8 | 2025-10-03 |  | Functionality | Minor | Resolved | Msg Rsp Fmt Error Type | Sorting | Sort ascending/descending order by clicking column header Note: column has additional filter that has "Number Filters" even though data is displayed as the description | Seems that these columns should have "Text Filters" instead of number filters | 2025-10-21 | Pass | 10/03: Remove filters, leave asc/descending if it cannot be fixed 10/21: Filters fixed; can apply across multiple columns
9 | 2025-10-03 |  | Functionality | Minor | Resolved | Msg Rsp Fmt Error Type | Drop-down menu options order | Msg Rsp Fmt: Drop-down list is in reverse alphabetical order Error Type: Drop-down list is not in any order | Both drop-downs should be in alphabetical order by description | 2025-10-21 | Pass | 10/03: Correct to alphabetical order
10 | 2025-10-03 |  | Functionality | Major | Resolved | Msg Rsp Fmt | Order of validation | Validations appear to be out of order: 1. Enter Error Nbr > Msg Rsp Fmt, Error Code, Error Message are NULL > Save = Displays Error Code is required 2. Enter Error Code > Msg Rsp Fmt, Error Message are NULL > Save = Displays Error Message is required 3. Enter Error Message > Msg Rsp Fmt is NULL > Save = Displays Severity is required | Current window seems to validate columns left to right; Vision NG seems to start with Error Nbr, skips to Error Code, Error Message, Error Type, then back to Msg Rsp Fmt | 2025-10-21 | Pass | 10/03: To be reviewed 10/21: See #24
11 | 2025-10-03 |  | Functionality | Minor | Resolved | Msg Rsp Fmt | Default display | When adding a new row, default display shows Select Severity | Title and selection don't match; ok with leaving as-is as long as internal team understands what it means | 2025-10-21 | Pass | 10/03: Update to read Select Msg Rsp Fmt
12 | 2025-10-03 |  | Functionality | Minor | Resolved | Error Code Error Message | Column headers change color when sorting | Column header changes from blue to gray when sorting is added | Other columns do not change color | 2025-10-21 | Pass | 10/03: Fixed
13 | 2025-10-03 |  | Functionality | Minor | Resolved | Add New Row | Placement of newly added rows | New row added at top of window | Current window adds to bottom of existing rows; believe NG window is placing them at the top due to the default "0" value | 2025-10-21 | Pass | 10/03: Move to bottom
14 | 2025-10-03 | Both | Functionality | Major | No Action | Delete Row | Deleting blank rows | 1. Add 3 blank rows 2. Right click and delete 3. Deletes all blank rows | Only one row should be deleted (selected row) | 2025-11-18 | Pass with Comments | 10/03: Fixed 10/21: Can only add 1 new row but should be able to add multiple 10/29: for now, leave as-is (move to separate grouping to address later) 11/18: Moved to No Action. Removed ability to add multiple rows at once.
15 | 2025-10-03 |  | UI | Minor | Resolved | Display Border | Missing Border | Blue border is missing around data | If possible, add blue border so window stands out; column headers in NG window blend into background | 2025-10-21 | Pass | 10/03: Fixed
16 | 2025-10-03 |  | UI | Minor | Resolved | All Columns | Column header alignment | Left justified | Should be center justified | 2025-10-21 | Pass | 10/03: Fixed
17 | 2025-10-03 |  | UI | Minor | No Action | Error Nbr | Number of Rows displayed | Displays 23 rows | Current window displays 25 rows | 2025-10-21 | Pass with Comments | 10/03: Leave as-is; need to take in consideration for future windows 10/21: NG now shows 27 rows
18 | 2025-10-03 |  | UI | Minor | Resolved | Error Nbr | Data alignment | Values are left justified | Should be right justified | 2025-10-21 | Pass | 10/03: Fixed
19 | 2025-10-03 | Both | Functionality | Major | Resolved | Window | Page Up/Down Keys vs. Scrolling | Page Up / Page Down vs. scroll in window | Added per 10/03 internal meeting | 2025-11-18 | Pass with Comments | 10/03: address later 10/21: revisit at next meeting 10/29: First, Next, Last implemented; fixed 11/18: Page Up has more lag than page down 12/04: Scroll removed as paging for grids that were virtualized was updated. | 11/10 SM - page up/down added 11/25 SM - I believe this was passed during our 11/24 meeting. Please reach out if it was not
20 | 2025-10-03 | Both | Functionality | Major | Resolved | Window | Shortcut Keys | Shortcut keys not working in Vision NG window; workin current Vision window | Added per 10/03 internal meeting | 2025-11-24 | Pass | 10/03: Address now 10/21: Not working 10/29: in progress still 11/18: Changes work. However, these short keys are not present in Code Entries table. Should this functionality remain or be removed? | 11/10 SM - Save, Close, F7, F8, F10, F11, CTRL+S,Shift+F6, Shift+F7, F3 working 11/24 SM - also added ctrl+shift+f
21 | 2025-10-29 | Both | Functionality | Major | No Action | Window | Pending Changes During Deployment | 1. Open window and update to create pending changes (did not save) 2. Changes deployed 3. Received several pop up messages asking if you would like to continue working on pending changes 4. Close prompts and try to continue working on pending changes, receive "Rejoining the server..." message. |  |  | Pass with Comments | 10/29: devs to send notices of deployment; deployments to be done COB hours
22 | 2025-10-29 | Both | UI | Regression | Resolved | Window | Highlighted rows | Light blue highlight appears but difficult to read row when highlighted as text is white and bolded | 1) Remove the bold format when selected and either 2 or 3 2) Keep text white and darken blue highlight 3) Change text to white and keep light blue highlight | 2025-11-18 | Pass | 10/29: Fixed | 11/10 SM - addressed with gray background styling when row modified
23 | 2025-10-29 | Both | UI | Major | Resolved | Error Code | Message for invalid code | Message is cut off if window is minimized | If possible, can this be dynamic? 11/18 after minimize before row is selected 11/18 after row is selected | 2025-12-04 | Pass | 10/29: Fixed; click out of row will show all validation errors; tab out will only show validation for that column 11/18: Message cuts off. Additionally, if you modify window size while error message appears, the message points to the incorrect cell. If you click to a new row, the message moves to the correct location 11/24: BSA retest 12/04: once row displays fluent validation messages and subsequently resizes window, algignment and messages are cut off. | Other windows do not notify of no data retrieved, we want to keep all windows the same right, also this new modern grid tells you that no data was retrieved as well, image on the right: 11/20 SM - message no longer cuts off. Still working on layout shift issue 11/25 SM - message does not cut off. Layout shift will stay per 11/24's meeting
24 | 2025-10-29 | Both | Functionality | Regression | Resolved | Add New Row | Save icon disabled | 1. Open Error Codes. 2. Add New Row and enter Error Nbr. 3. Update Msg. Rsp Format field > then Save button enabled. | Icon should not be disabled when opening window | 2025-12-04 | Pass | 10/29: Enable for edit and add 12/05: resolved | when saving an edit or saving an add it will trigger changes when deleting a row it will trigger changes
25 | 2025-10-29 | Both | Functionality | Regression | Resolved | Add New Row | Delay in adding row | Takes a couple seconds for empty row to load | Current Vision window is immediate | 2025-12-04 | Pass | 10/29: SyncFusion build to include fix (mid-November) 11/24: BSA retest 12/04: retest and pass; no latency in adding row and appears at top | 11/25 SM - adding rows will appear at the top
26 | 2025-10-29 | Both | Functionality | Major | Resolved | Add New Row | Removed if sorting is applied | 1. Add new row 2. Apply filter on any column - row removed | Current window filters row to the top and all other rows sort asc/desc order | 2025-11-18 | Pass | 10/29: JL to send options of formatting; as of now, look into bolding modified rows | 11/10 SM - modified rows will have a bolded background styling
27 | 2025-10-29 | Both | Functionality | Regression | Resolved | Add New Row | Pending Changes can only be Canceled | Delete option does not work for newly added row - user needs to select Cancel to disregard changes | Current window uses Delete to funcation as cancel/delete | 2025-11-18 | Pass | 10/29: Virtualization, leave as-is; JL to set meeting with CC and MU to review edit modes | 11/10 SM - only cancel will be available when in edit mode.
28 | 2025-10-29 | Both | UI | Minor | Resolved | Update Row | Pending changes highlight color | Green border around cells | Bail Schedule used orange border; need to be consistent across all windows for pending changes | 2025-11-18 | Pass | 10/29: address during edit mode meeting | I have this sample with image on right, tell me what you think
29 | 2025-10-29 | Both | Functionality | Major | Resolved | Update Row | Pending changes look like saved changes | 1. User right click > Edit Row 2. Updates value(s) 3. Clicks out of row to different row 4. User right click > Edit Row - no visible indicator that (#1) was modified | 1) Find a way to identify rows that have been modified or 2) Prevent user from modifying other rows when changes are pending | 2025-11-18 | Pass | 10/29: JL to send options of formatting; as of now, look into bolding modified rows | image on right to prevent modifying other rows by disabling menu 11/10 SM - modified rows will have a bolded background styling
30 | 2025-10-29 | Both | Functionality | Major | Resolved | Window | Add/Update/Delete Row then Close window prompts Pending changes Message | 1. User adds, edits, and/or deletes row. 2. Changes saved 3. PowerBuilder SAVE message appears (You have pending changes Do you still want to close? Yes/No/Cancel) | Message should not appear | 2025-11-18 | Pass | 10/29: devs to fix 11/18: The message appears if save is loading, but this is not an issue. | 11/10 SM - could not replicate. I think this as been addressed.
31 | 2025-10-29 | Both | Functionality | Major | Resolved | Window | Vision level "x" closes Blazor window | Close button closes Blazor window rather than application |  | 2025-11-18 | Pass | 10/29: devs to fix | 10/30 SM - has been addressed
32 | 2025-11-18 | Both | Functionality | Minor | Resolved | Add New Row | Flashing | 1. Click out 2. Scroll Up 3. Scroll Down 4. Show Loading sign 5. Displays newly added row | In general, selecting out of a newly added row visually shows a lot of changes. Is it possible to reduce the number of changes occuring when you are done editting a row? | 2025-12-04 | Pass with Comments | 11/24: lazy loading. unable to fix 12/04: no longer can recreate as paging was implemented | 11/21 SM - Please rephrase 11/25 SM - unable to fix
33 | 2025-11-18 | Both | Functionality | Major | Resolved | Update Row | Click out of row | 1. Right click then select edit, or double click an existing row 2. Modify a cell value 3. Click outside of cell - expected result is pending changes update. this does not occur 4. right click and select update row - expected result is pending changes update. receive "Warning! You are currently modifying a record" message. Only way to exit is to cancel the changes. | This issue also sometimes, but not always occurs if you attempt to modify the row without select outside of the cell. It is difficult to replicate a scenario where updates save. | 2025-12-04 | Pass with Comments | 11/24: BSA retest 12/04: MU - could not replicate | 11/20 SM - defect fixed in dev. Never made it to QA build
34 | 2025-11-18 | Both | Functionality | Minor | Resolved | Error Type | Column is sortable | Sort descending displays - User Error, Information, Warning, Application Error, Validation Error, DataStore Error, DataWindow Error, Database Error, Unknown Error Type | Existing window does not sort on this column | 2025-12-04 | Pass | 11/24: BSA retest 12/04: retest and pass | 11/21 SM - has been addressed. Error type now sorts A-Z and Z-A.
35 | 2025-12-04 | Both | Functionality | Minor | Resolved | General | Updates from multiple VisionNG Tabs | 1. User adds new row in TAB 1 with unique Error Nbr. 2. User adds new row in TAB 2 with same Error Nbr as step 1. 3. User returs to TAB 1 and saves - row successfully saves. 4. User returns to TAB 2 and attempts to save - error message correctly appears, no fluent validations Note: also occurs when test scenario against Vision app/web | Since window wasn't refreshed, fluent validations appear to be done at the window level rather than against the database. Adding as item for discussion to see if this needs to be resolved. | 2025-12-22 | Pass | 12/15: devs to fix | 12/18 SM - fixed concurrency issue
36 | 2025-12-04 | Both | Functionality | Minor | No Action | All Columns | Fluent validation cell colors | 1. Add new row (cells do not have colored borders) 2. Enter valid Error Nbr then tab/click out of field Result: Error Nbr turns green; other required fields except for Msg Rsp Fmt turn red Alternate scenario for same issue: add new row then click out of row, only Error Nbr turns red and other cells do not have color (only fluent validation messages appear). | Should cells remain uncolored until user tries to click out of row? As a user it's indicating there are errors befor I even have the chance to add values. Seems like color should appear when fluent validation messages appear. |  | Pass with Comments | 12/15: Leave as-is
37 | 2025-12-04 | Both | UI | Minor | Resolved | Error Code | Field Height | Update Field Height to match other columns | Not sure if this existed in previous QA versions; based on previous screenshots seems more noticable now. | 2025-12-22 | Pass | 12/15: devs to fix | 12/18 SM - updated the field height. Rows have a minimum 30px height
38 | 2025-12-04 | Both | UI | Minor | No Action | All Columns | Column Alignment in "edit" mode (non-4k monitor) | When in edit mode, columns should align with exisitng data; NG window shifts cells slightly to the left misaligning them from column header (e.g., Error Message and Error Type) | Should be in aligmnent with header; noticed issue seems to not exist when using larger monitor although it does creat alignment issues when moving between small/large monitors |  | Pass with Comments | 12/15: no action as requires different effort
39 | 2025-12-04 | Web Only | Functionality | Minor | Resolved | General | Update Row | Update Row icon is same as save icon, however, changes are not saved until user uses SAVE | Recommend to remove option as user can use ENTER on keyboard or click out of row | 2025-12-22 | Pass | 12/15: devs to fix - remove Update Row option | 12/16 SM - removed the update option
40 | 2025-12-04 | Both | Functionality | Major | Resolved | General | Refresh doesn't detect pending changes when Add/Update/Delete | Current Vision app window will prompt message before user refreshes advising there are pending changes; current window does not advise user In Vision App, if window is closed PB message still catches the pending changes | User should be advised of pending changes before refresh | 2025-12-22 | Pass with Comments | 12/15: devs to fix - standardize on all windows 12/22: See ID #42 | 12/17 SM - added popup to confirm user changes on event code, error code, and court control.
41 | 2025-12-04 | Both | UI | Minor | No Action | General | Move Paging arrows/numbers down closer to section border | If able to, reduce space between page numbers/arrows and blue section border so it is closer to the bottom of the section |  |  | Pass with Comments | 12/15: address later as spacing is different effort
42 | 2025-12-04 | Web Only | UI | Major | Resolved | General | Tab name | 1. After logging in, tab name is VisionNG 2. Select Code Entry, execute Description "warrant" search, tab name udpated to Code Entry Table: EXCLDS 3. Select Error Codes, tab name remains as "Code Entry Table: EXCLDS" | Should the tab name be static "VisionNG" or update to the window opened? | 2025-12-22 | Pass | 12/15: devs to fix - web tab to be VisionNG regardless of window selected | 12/17 SM - error code is not causing the page title change. This issue comes from code entry component.
43 | 2025-12-04 | Web Only | Functionality | Major | No Action | General | Open Multiple NG Windows | In the web version, user can only open one window at a time compared to Vision application where user can have multiple windows open simultaneously. | Is this something that will be addressed later? Or are users expected to have multiple sessions/browser tabs open for Vision NG? |  | Pass with Comments | 12/15: let devs know but leave leave as-is; to address when testing web browser
44 | 2025-12-22 | Both | Functionality | Major | Resolved | General | Add/Update/Delete Row then Close window prompts Pending changes Message | 1. User adds, edits, and/or deletes row. 2. Changes saved 3. Vision NG window (Pending Changes; The Data which is modified is not saved Do you wish to save the Data? Yes/No/Cancel) | Should not trigger if no pending changes exist. Regression bug as it was previously reported in ID #30 |  | Pass with Comments | 01/14/26: see 47 | 12/30 SM - this issue has been addressed.
45 | 2025-12-22 | Both | Functionality | Regression | Resolved | General | F3 Refresh | Short key does not work unless user clicks again within window. |  |  | Pass with Comments | 12/24: Leave as is 01/14: retest and pass for Edit and Add; see 48 | 12/30 SM - added key down method at window level. This may address the issue.
46 | 2025-12-22 | Both | Functionality | Minor | Resolved | F3 Refresh | Column filters remain after F3 refresh | 1. apply column filter 2. F3 refresh -column filter remains |  |  | Pass |  | 12/30 SM - cleared the filter when user refreshes for event and error codes
47 | 2026-01-14 | Both | UI | Minor | Resolved | F3 Refresh | Refresh | Pending Changes: The Data which is modified is not saved Yes/No/Cancel buttons Missing question about saving data | Update to: Pending Changes You have unsaved changes. Do you want to save before you continue? |  | Pass | 01/15: Refresh/Pending Changes message to be updated to be generic enough to cover both scenarios. | 01/21 SM - pending changes message has been modified.
48 | 2026-01-14 | Both | Functionality | Regression | Resolved | F3 Refresh | F3 Refresh Ctrl + S | Short key does not work if user deletes last row and attempts to refresh as I believe key down method (ID #45) doesn't work for this scenario | Workaround is user clicks on window to refocus |  | Pass |  | 01/21 SM - reset focus back to the grid when user deletes last entry. Works with F3 and CTRL+S
49 | 2026-01-14 | Both | Functionality | Minor | Resolved |  | Newly added row | 1. User adds new row on page 2 2. Leaving exit mode sends new row to Page 1 | Is there a way to have new row remain on top of page where it's added rather than page 1? | 2026-01-23 | Pass | 01/23: all added rows will appear on page 1; after save will resort | 01/21 SM - user is now directed to page 1 when adding a new entry
50 | 2026-01-14 | Both | UI | Minor | Resolved | General | Success save message | Saved Successfully. | Saved successfully. | 2026-01-23 | Pass | 01/15: devs to update save message; message format to be updated to toast 01/23: lowercase s in successfully 01/23: updated in afternoon, passed | 01/21 SM - save message has been converted to a toast
51 | 2026-01-23 | PB Only | UI | Regression | Resolved | General | Scroll Bar | Scroll bar appears even though window is using paging | Scroll bar never appeared prior to last change | 2026-01-23 | Pass | 01/23: updated in afternoon, passed
52 | 2026-01-23 | Both | Functionality | Minor | Resolved | General | Refresh | 1. User adds new row on page 2 2. User redirected to pending changes on page 1. 3. Window loses focus - keyboard shortucts fail F3/Ctrl +S | Workaround is user clicks on window to refocus | 2026-01-23 | Pass | 01/23: updated in afternoon, passed
53 | 2026-01-23 | Both | UI | Major | Resolved | General | Edit Mode on Multiple | 1. Open window with no filters applied 2. Open existing row in edit mode and make changes 2. Apply sorting filter on a column 3. Open 2nd row in edit mode | The following occur: 1. Editable fields appear to be overriden with data from subsequent row opened in edit mode 2. User is able to edit both rows 3. However, upon exiting edit mode, updates appear to only apply to one row. Is there a way to disable multiple edits as the updated data is not correct? | 2026-01-23 | Pass |  | 1/26 SM - issue has been addressed. User's changes are committed to the grid when they try to filter mitigating multiple edit rows.
54 | 2026-01-23 | PB Only | UI | Minor | Resolved | General | Black Border around data sections | User clicks out of window then back in NG screen > Black border appears around window |  | 2026-01-23 | Pass |  | 1/26 SM - issue has been addressed. Black outline removed.
55 | 2026-01-27 | PB Only | UI | Major | Resolved | General | Window grid disappears if user clicks out of Vision application | User clicks out of window - data grid goes missing User then clicks back in NG screen > data grid reappears |  | 2026-01-26 | Pass | 01/26: fixed in QA2029y
56 | 2026-01-27 | Both | Functionality | Major | Resolved | General | Latency for saving data | Transparent loading wheel doesn't display |  | 2026-02-02 | Pass | 01/30: waiting for update for 65% opacity to retest
57 | 2026-01-27 | Both | UI | Minor | Resolved | General | Filter Icon Color | Filter icon should be red when applied; color to be removed when filter removed |  | 2026-01-29 | Pass
58 | 2026-01-30 | Both | Functionality | Minor | Resolved | General | Disable Mouse Scrolling on fields | Scrolling up increases value, scrolling down decreases value for number fields; To recreate, user needs to leave field blank, select different field, return back to Error Nbr field and then use scroll on mouse. | Should not be enabled | 2026-02-02 | Pass | 01/30: identified during Court Control QA; missed in previous QA as issue does not occur when number field is first cell.

## SUMMARY
|  | Scenario | Status
QA # | HH:MM | Row Labels | No Action | Resolved | Grand Total
1 | 4:00 | 2025-10-03 | 2 | 18 | 20 | Row Labels | Count of Bug Type | Row Labels | Count of Status
|  | Functionality | 1 | 15 | 16 | Major | 23 | No Action | 7
|  | Major | 1 | 8 | 9 | Minor | 28 | Resolved | 51
|  | Minor |  | 7 | 7 | Regression | 7 | Grand Total | 58
|  | UI | 1 | 3 | 4 | Grand Total | 58
|  | Minor | 1 | 3 | 4
2 | 5:00 | 2025-10-29 | 1 | 10 | 11
|  | Functionality | 1 | 7 | 8
|  | Major | 1 | 4 | 5
|  | Regression |  | 3 | 3
|  | UI |  | 3 | 3
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
|  | Regression |  | 1 | 1
3 | 4:00 | 2025-11-18 |  | 3 | 3
|  | Functionality |  | 3 | 3
|  | Major |  | 1 | 1
|  | Minor |  | 2 | 2
4 | 4:00 | 2025-12-04 | 4 | 5 | 9
|  | Functionality | 2 | 3 | 5
|  | Major | 1 | 1 | 2
|  | Minor | 1 | 2 | 3
|  | UI | 2 | 2 | 4
|  | Major |  | 1 | 1
|  | Minor | 2 | 1 | 3
5 | 2:00 | 2025-12-22 |  | 3 | 3
|  | Functionality |  | 3 | 3
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
|  | Regression |  | 1 | 1
6 | 1:00 | 2026-01-14 |  | 4 | 4
|  | Functionality |  | 2 | 2
|  | Minor |  | 1 | 1
|  | Regression |  | 1 | 1
|  | UI |  | 2 | 2
|  | Minor |  | 2 | 2
7 | 1:00 | 2026-01-23 |  | 4 | 4
|  | Functionality |  | 1 | 1
|  | Minor |  | 1 | 1
|  | UI |  | 3 | 3
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
|  | Regression |  | 1 | 1
8 | 0:45 | 2026-01-27 |  | 3 | 3
|  | Functionality |  | 1 | 1
|  | Major |  | 1 | 1
|  | UI |  | 2 | 2
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
9 | 0:45 | 2026-01-30 |  | 1 | 1
|  | Functionality |  | 1 | 1
|  | Minor |  | 1 | 1
|  | Grand Total | 7 | 51 | 58
10 | 0:30 | 2/3/2026 QA Completed

## 52
1. Error Codes Opened | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Information | AAA | ATEST | Application Error
| 40006 | Warning | AAB | BTEST | Warning
2. User opens 40005 in Edit Mode and updates. | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Question | AAA1 | ATEST - Update 1 | Database Error
| 40006 | Warning | AAB | BTEST | Warning
3. While 40005 is still in Edit Mode, filter on Error Code column is applied sorting Error Codes asc. Updates made in Step 2 remain. | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Question | AAA1 | ATEST - Update 1 | Database Error
| 40006 | Warning | AAB | BTEST | Warning
4. User opens 40006 in Edit Mode. Data in 40005 overridden with data from 40006 | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Warning | AAA1 | BTEST | Warning
| 40006 | Warning | AAB | BTEST | Warning
5. User attempts to edit Msg Rsp Fmt for 40006 however, Msg Rsp Fmt for 40005 is selected. User updates selection and 40006 updates to selected item | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Warning | AAA1 | BTEST | Warning
| 40006 | STOP Sign | AAB2 | BTEST - Update 2 | Validation Error
5. User returns to 40005, updates data | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Stop | AAA3 | BTEST - Update 3 | DataWindow Error
| 40006 | STOP Sign | AAB2 | BTEST - Update 2 | Validation Error
6. User exits edit mode. All updated fields except for Error Code is updated in 40006 with data entered for 40005. 40005 abandoned chagnes | Error Number | Msg Rsp Fmt | Error Code | Error Message | Error Type
| 40005 | Information | AAA | ATEST | Application Error
| 40006 | Stop | AAB2 | BTEST - Update 3 | DataWindow Error

## Sheet2 (hidden)
Pass | Reported | Regression
Fail | Retest In Progress | Major
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action