## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | NG Display/Scenario | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Loading Time | Takes ~8 seconds to load | Current window is immediate | 2025-12-05 | Pass | 11/03: devs working on issue per 10/29 meeting 11/18: Same defect exists. 11/24: BSA retest | 10/31 SM - added virtualization. Please retest 11/26 SM - removed virtualization
2 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Save button on initial load | Disabled, current window leaves 2nd row icons enabled |  | 2025-11-19 | Pass | 11/03: enable for edit and add per 10/29 meeting | 11/4 SM - save button enabled for edits
3 | 2025-10-27 |  | UI | Minor | Resolved | Search Criteria | Search Criteria Font | "Event Type" and "Owner Agency" appear to be different font from rest of window | Current window has same font throughout window | 2025-11-19 | Pass | 11/03: BSA retest; devs to review application level CSS | 10/31 SM - has been addressed
4 | 2025-10-27 |  | UI | Minor | No Action | Retrieve button | Color | Blue button, white font; current window has gray button, black font | Need consistency on buttons |  | Pass with Comments | 11/03: leave as-is
5 | 2025-10-27 |  | UI | Minor | Resolved | Search Criteria | Missing section grouping of search criteria | No border/color difference to section out Search Criteria; current window has search criteria in gray box | Need consistency on search fields | 2025-11-19 | Pass | 11/03: color to remain; remove loading spinner after initial load (only show on main load) | 10/31 SM - has been addressed. removed spinner on fetching data.
6 | 2025-10-27 |  | Functionality | Major | Resolved | Search Criteria | Owner Agency Search | No longer can type multiple letters in field to direct user down to section; typed value of "Orange" results in Ecitation AOC CMMS V4 as the value rather than "Orange..." agencies "ora" > Orange City Attorney "n" > Newport Beach City Attorney "g" > Garden Grove City Attorney "e" Ecitation AOC CMMS V4" | Current window searches based on entirety of typed value | 2025-11-19 | Pass | 11/03: JL to follow up with SyncFusion to see if there is a fix per 10/29 meeting; use filter for this window | 10/31 SM - has been addressed. Added filtering option
7 | 2025-10-27 |  | UI | Minor | Resolved | Event Codes, ROC Codes | Header Formatting | 1. Event Code, Description; ROC, Description: titles are missing underline 2. Invalid: format should be MM/DD/YY black 3. Title font appears to be different than column headers 4. Alignment of titles seems to be a few pixels indented (might be due to font difference) |  | 2025-11-19 | Pass | 11/03: leave date format as-is per 10/31 meeting; #1 leave as-is (no underline); 3, 4 to be addressed by devs 11/19: Alignment is close to aligned. Difference cannot be seen unless you zoom in. Passing. | 11/6 SM - 3, 4 addressed
8 | 2025-10-27 |  | UI | Minor | Resolved | Event Codes | Existing Event Code/ROC Code message | Fix format: 1. Event Code already exists. Please enter another value! 2. ROC Code already exists. Please enter another value! |  | 2025-11-19 | Pass | 11/03: BSA retest in next QA cycle | 111/4 SM - addressed w/ fluent validation
9 | 2025-10-27 |  | Functionality | Major | Resolved | Event Codes | Event Code (NULL) | 1. Add new row, Tab out of Event Code (NULL value) > does not display validation message 2. Save NULL Event Code: Event code required. and yellow "Warning! Event Code record is not valid" | 1. Tab out should display validation message 2. Fix format in message "Event Code is required." & Warning message "Event Code record is not valid." 3. Fix format in message "ROC Code is required." & Warning message "ROC Code record is not valid." | 2025-11-19 | Pass | 11/03: BSA retest in next QA cycle 11/19: Tab out does not display validation message. 11/24: leave as-is | 111/4 SM - addressed w/ fluent validation 2,3
10 | 2025-10-27 |  | Functionality | Major | Resolved | Event Codes | No Character Limit on Event Code/ROC Code fields | User enters 12+ characters then valdiation "Event code cannot exceed 12 characters" | 1. Field should be updated to limit to 12 charcters 2. Fix format "Event Code cannot exceed 12 characters." 3. Fix format "ROC Code cannot exceed 12 characters." | 2025-11-19 | Pass | 11/03: BSA retest in next QA cycle 11/19: Event Code and ROC format does not allow more than 12 characters. No validation message needed. | 11/4 SM - addressed w/ fluent validation and edit template
11 | 2025-10-27 |  | Functionality | Major | Resolved | Event Codes | No Character Limit on Event Code/ROC Description fields | User enters 255+ characters then valdiation "Description cannot exceed 255 characters" | 1. Field should be updated to limit to 255 characters 2. Fix format "Description cannot exceed 255 characters." | 2025-11-19 | Pass | 11/03: BSA retest in next QA cycle 11/19: Event Code description and ROC description format does not allow more than 255 characters. No validation message needed. | 10/31 SM - will be addressed w/ fluent validation and edit template
12 | 2025-10-27 |  | Functionality | Major | No Action | Invalid Date | Can enter letters into date field | Should only be able to enter numbers in field | Non-number values do not save but field shouldn't allow for non-number format |  | Pass with Comments | 11/03: leave as-is; only occurs in month field per 10/31 meeting | 10/31 SM - has been addressed w/ date mask
13 | 2025-10-27 |  | Functionality | Major | Resolved | Invalid Date | Field format | Must select from calendar to enter date Current version allows to type in numbers "102725" and field is automatically formatted to 10/27/25 | Need to determine if there is a way where users can enter numbers and have the window format as MM/DD/YY instead of having users enter "/" between month, day, and year | 2025-11-24 | Pass | 11/03: BSA retest in next QA cycle and valdiate column width in web version 11/19: User can type month, but Job Error Log defects 45-49 apply here as well. 11/24: leave as-is | 10/31 SM - has been addressed w/ date mask
14 | 2025-10-27 |  | UI | Minor | Resolved | Pending Updates | Border Color | Updated field(s) show green border; Bail Schedule showed orange border | Need consistency across windows | 2025-11-19 | Pass | 11/03: tied with fluent validations | 11/5 SM - now have grey background for edited records
15 | 2025-10-27 |  | UI | Major | Resolved | Adding Row | Added row not visible | When adding row, user has to do an additional step to scroll down to view new row | Should display immediately after adding new row (no scrolling) | 2025-12-05 | Pass | 11/03: ticket with SyncFusion 11/19: Not tested. Pending SyncFusion deployment 11/25. Leaving in Reported status. 12/05: New row added to top; issue no longer occurs | 10/31 SM - SyncFusion to include in next build Nov 25 12/2 SM - rows are now added to the top
16 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Deleting New Row | Delete no longer works on newly added rows; user has to use "Cancel" to remove row |  | 2025-11-19 | Pass | 11/03: devs to fix; Edit mode = Cancel only; exit Edit mode = Add Row, Edit, Delete options | 10/31 SM - users only have Cancel in edit; Add, Edit, Delete outside of edit mode (context menu)
17 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Cannot add multiple empty rows | Only one row can be added at a time; user has to save changes in 1 row then add for additional row; current window allows for multiple rows to be entered | Should have way of adding multiple rows | 2025-11-19 | Pass | 11/03: separate discussion with stakeholders - devs to update functionality (single click opens row in edit mode) | 11/6 SM - single click on hold. Using double-click per meeting on 11/3
18 | 2025-10-27 |  | Functionality | Minor | Resolved | Window | No Sorting | Should asc/desc sorting be added to the window? Current window does not have |  | 2025-11-19 | Pass | 11/03: add sorting and filtering | 11/4 SM - added sorting and filtering
19 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Page Up/Down Keys vs. Scrolling | Page Up / Page Down vs. scroll in window |  | 2025-12-05 | Pass | 11/03: BSA retest in next QA cycle 11/19: Page Up/ Page Down works, but the scroll happens in 3 parts: scroll bar moves, page updates, highlight changes. For the scroll, but 11/24: lazy loading - Devs to remove virtualization to see if this resolves issue 12/05: retest and pass | 10/31 SM - addressed 11/21 SM - is laggy because of amount of data being loaded 11/24 SM - removed virtualization
20 | 2025-10-27 | Vision | Functionality | Major | Resolved | Window | Shortcut Keys | Shortcut keys not working in Vision NG window; work in current Vision window |  | 2025-12-23 | Pass | 11/03: BSA retest in next QA cycle 11/19: Vision shortkeys Shift F7, Shift F6, Ctrl S, etc do not work. Are we including vision shortkeys in blazor windows? 11/24: BSA retest 12/05: F3, F6 (Add) work; F7 does not | 10/31 SM - addressed 11/24 SM - vision shortcut keys shift+F6/F7, ctrl+s, f3, have been added 12/17 SM - F3, SHIFT+F6, SHIFT+F7, F7, F8, F10, F11, Page Up, Page down, Ctrl+S, SHIFT+CTRL+F all work for both event code and roc code in vision/visionNG
21 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Vision level "X" Close Button | When used, only closes Blazor window rather than entire application |  | 2025-11-19 | Pass | 11/03: BSA retest in next QA cycle | 10/31 SM - addressed via vision update
22 | 2025-10-27 |  | Functionality | Major | Resolved | Window | Profile Access | All profiles can edit window | Users in PROFIL/EVENT_CODES should only be able to add/edit/delete in window. All other profiles are read only | 2025-11-19 | Pass | 11/03: devs to fix | 11/5 SM - added read only for Profiles
23 | 2025-11-19 |  | Functionality | Minor | Resolved | Event Codes | Adding row with no search | If no search fields are entered, you can add a row. You are not able to save the row but it can be added. | Rows should only be added if event type and agency are selected. | 2025-12-05 | Pass | 12/05: Retest and pass | 11/21 SM - has been addressed. rows are only added when user has selected event type and owner agency
24 | 2025-11-19 |  | UI | Major | No Action | Search Criteria | Dropdown | 1. Select option in Event Type 2. Select dropdown option in Owner Agency 3. Click Enter key multiple times to modify the selected option 4. Select Retrieve - latest dropdown freezes and remains as you are trying to use the window | This scenario is unrealistic but not sure if it should be addressed |  | Pass with Comments | 11/24: leave as is
25 | 2025-12-05 |  | UI | Minor | No Action | Invalid | Column header and data alignment | Update column header so that "Invalid" column title is centered above data values. |  |  | Pass with Comments | 12/15: leave as-is
26 | 2025-12-05 | Both | Functionality | Minor | Resolved | General | Updates from multiple VisionNG Tabs | 1. User adds new row in TAB 1 with unique Error Nbr. 2. User adds new row in TAB 2 with same Error Nbr as step 1. 3. User returs to TAB 1 and saves - row successfully saves. 4. User returns to TAB 2 and attempts to save - error message correctly appears, no fluent validations Note: also occurs when test scenario against Vision app/web | Since window wasn't refreshed, fluent validations appear to be done at the window level rather than against the database. Adding as item for discussion to see if this needs to be resolved. | 2025-12-23 | Pass | 12/15: devs to fix | 12/18 SM - concurrency issue has been resolved.
27 | 2025-12-05 | Both | Functionality | Major | Resolved | Invalid Date (Event and ROC Code sections) | Future Date Range | 1. Enter "01/01/2125" then click out of field 2. Date automatically updates to 12/31/2099 | Current Vision app window has 2-digit year format so cannot create in current window. Not sure if we should have invalid dates for "Invalid" field as they can be either past or future dates. | 2026-01-23 | Pass | 12/15: devs to look into removing max date 01/14: issue still occurring on subsequent updates when a date exists 01/23: issue resolved for clicking out of field | 12/17 SM - Syncfusion has a default max and minimum for the date picker. I need to manually specify the max date range. See image to the right. 01/21 SM - issue has been addressed. Maximum date is 12/31/2099 and Minimum is 01/01/1900
28 | 2025-12-05 | Both | Functionality | Major | Resolved | Invalid Date (Event and ROC Code sections) | Future Date Range | 1. Enter "01/01/2125" then use "Enter" on keyboard 2. Date does not automatically update and user can successfully save date in #1 Note: If user goes into row to edit, the date auto updates to "12/31/2099" | Conflicting functionality between ID 26, 27. | 2026-01-23 | Pass with Comments | 12/15: devs to look into removing max date 01/14: issue still occurring on subsequent updates when a date exists 01/23: see ID 36 | 12/17 SM - Syncfusion has a default max and minimum for the date picker. I need to manually specify the max date range. See image to the right. 01/21 SM - issue has been addressed. Maximum date is 12/31/2099 and Minimum is 01/01/1900
29 | 2025-12-05 | Both | Functionality | Minor | No Action | Invalid Date (Event and ROC Code sections) | Highlighting Field | 1. User highlights date 2. User re-highlights date and date digits end up in Description field | Adding as item to see if there can be anything done |  | Pass with Comments | 12/15: leave as-is
30 | 2025-12-23 | Both | Functionality | Regression | Resolved | General | F3 Refresh | Short key does not work unless user clicks again within window. |  |  | Pass with Comments | 12/24: Leave as is, may be JS fix | 12/30 SM - added key down method at window level. This may address the issue.
31 | 2025-12-23 | Both | Functionality | Major | No Action | General | F7 Delete (new row) | Short key only works for existing row, should this work for new row | User can cancel to delete new row |  | Pass with Comments | 12/24: Leave as is
32 | 2025-12-23 | Both | Functionality | Minor | Resolved |  |  | 1. apply column filter 2. F3 refresh - error message appears: "Unhandled exception during interop call" | Column filters will refresh in this window |  | Pass | 01/14: retest and pass - issue no longer occurring | 12/30 SM - rendering issue has been addressed
33 | 2026-01-14 | Both | Functionality | Regression | Resolved | F3 Refresh | F3 Refresh Ctrl + S | Short key does not work if user deletes last row and attempts to refresh as I believe key down method (ID #45) doesn't work for this scenario | Workaround is user clicks on window to refocus | 2026-01-23 | Pass |  | 01/21 SM - reset focus back to the grid on delete. Works for CTRL+S and F3
34 | 2026-01-14 | Both | UI | Minor | Resolved | General | Success save message | Saved Successfully | Saved successfully. | 2026-01-23 | Pass | 01/15: devs to update save message; message format to be updated to toast 01/23: lowercase s in successfully 01/23: fixed in afternoon, retest and passed | 01/27 SM - save message converted to a toast.
35 | 2026-01-14 | Both | UI | Minor | Resolved | F3 Refresh | Refresh | Pending Changes: The Data which is modified is not saved Yes/No/Cancel buttons Missing question about saving data | Update to: Pending Changes You have unsaved changes. Do you want to save before you continue? | 2026-01-23 | Pass | 01/15: Refresh/Pending Changes message to be updated to be generic enough to cover both scenarios. | 01/27 SM - pending changes message has been updated to "You have unsaved changes. Do you want to save before you continue?" As provided by Chris.
36 | 2026-01-23 | Both | Functionality | Major | Resolved | Invalid Date (Event and ROC Code sections) | Future Date Range | 1. Enter "01/01/2125" then use "Enter" on keyboard 2. Date does not automatically update and user can successfully save date in #1 | This occurs when the invalid date is subsequently updated; scenario on first attempt automatically updates to max dat 12/31/2099 | 2026-01-23 | Pass | 01/26: fix implemented to use FluentValidation on date field. Cannot enter 01/01/2125 and date resets to max date; same occurs for min date
37 | 2026-01-23 | Both | UI | Major | Resolved | General | Edit Mode on Multiple | 1. Open window with no filters applied 2. Open existing row in edit mode and make changes 2. Apply sorting filter on a column 3. Open 2nd row in edit mode | The following occur: 1. User is able to edit both rows 2. However, upon exiting edit mode, updates appear to only apply to one row. Is there a way to disable multiple edits as the updated data is not correct? | 2026-01-26 | Pass |  | 1/26 SM - issue has been addressed. User's changes are committed to the grid when they try to filter mitigating multiple edit rows.
38 | 2026-01-23 | Both | Functionality | Minor | Resolved | General | F6 Shortcut to add new row when no data exists | 1. Event Code with no ROCs selected 2. User clicks in ROC Codes section, Shift + F6 to add row 3. Added row appears in Event Codes section | Is there a way to focus on ROC section when user clicks so shortcut key works? | 2026-01-26 | Pass |  | 1/26 SM issue has been addressed. User can now click on empty ROC grid and use shift+F6
39 | 2026-01-23 | PB Only | UI | Minor | Resolved | General | Black Border around data sections | User clicks out of window then back in NG screen > Black border appears around window |  | 2026-01-26 | Pass |  | 1/26 SM - issue has been addressed. Black outline removed.
40 | 2026-01-27 | PB Only | UI | Major | Resolved | General | Window grid disappears if user clicks out of Vision application | User clicks out of window - data grid goes missing User then clicks back in NG screen > data grid reappears |  | 2026-01-26 | Pass | 01/26: fixed in QA2029y
41 | 2026-01-27 | Both | Functionality | Major | Resolved | General | Latency for saving data | Transparent loading wheel doesn't display |  | 2026-02-02 | Pass | 01/30: waiting for update for 65% opacity to retest
42 | 2026-01-27 | Both | UI | Minor | Resolved | General | Filter Icon Color | Filter icon should be red when applied; color to be removed when filter removed |  | 2026-01-29 | Pass
43 | 2026-01-29 | Both | Functionality | Minor | Resolved | General | ROC Filter box | OK/Cancel buttons cut off |  | 2026-02-02 | Pass
44 | 2026-01-29 | Both | Functionality | Major | Resolved | General | Filter applied that excludes highligted row | 1. Highlight row with child records (e.g., ARGN) 2. Remove ARGN from Event Codes by applying filter 3. Apply filter - no parent rows are highlighted and ARGN child records still remain in view | If filter(s) are applied, refocus highlight in parent data so that first row is highlighted and correct child record(s) display | 2026-02-02 | Pass

## SUMMARY
|  | Scenario | Column Labels
QA # | HH:MM | Row Labels | No Action | Resolved | Grand Total
1 | 5:00 | 2025-10-27 | 2 | 20 | 22 | Row Labels | Count of Bug Type | Row Labels | Count of Status
|  | Functionality | 1 | 14 | 15 | Major | 24 | No Action | 6
|  | Major | 1 | 13 | 14 | Minor | 18 | Resolved | 38
|  | Minor |  | 1 | 1 | Regression | 2 | Grand Total | 44
|  | UI | 1 | 6 | 7 | Grand Total | 44
|  | Major |  | 1 | 1
|  | Minor | 1 | 5 | 6
2 | 5:30 | 2025-11-19 | 1 | 1 | 2
|  | Functionality |  | 1 | 1
|  | Minor |  | 1 | 1
|  | UI | 1 |  | 1
|  | Major | 1 |  | 1
3 | 5:30 | 2025-12-05 | 2 | 3 | 5
|  | Functionality | 1 | 3 | 4
|  | Major |  | 2 | 2
|  | Minor | 1 | 1 | 2
|  | UI | 1 |  | 1
|  | Minor | 1 |  | 1
4 | 1:00 | 2025-12-23 | 1 | 2 | 3
|  | Functionality | 1 | 2 | 3
|  | Major | 1 |  | 1
|  | Minor |  | 1 | 1
|  | Regression |  | 1 | 1
5 | 1:00 | 2026-01-14 |  | 3 | 3
|  | Functionality |  | 1 | 1
|  | Regression |  | 1 | 1
|  | UI |  | 2 | 2
|  | Minor |  | 2 | 2
6 | 1:00 | 2026-01-23 |  | 4 | 4
|  | Functionality |  | 2 | 2
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
|  | UI |  | 2 | 2
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
7 | 1:00 | 2026-01-27 |  | 3 | 3
|  | Functionality |  | 1 | 1
|  | Major |  | 1 | 1
|  | UI |  | 2 | 2
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
8 | 0:30 | 2026-01-29 |  | 2 | 2
|  | Functionality |  | 2 | 2
|  | Major |  | 1 | 1
|  | Minor |  | 1 | 1
|  | Grand Total | 6 | 38 | 44
9 | 0:30 | 2/3/2026 QA Completed

## 37
1. Event Codes opened | Error Number | Description | Invalid
| MU01 | ROC 1 Test
| MU02 | ROC 2 Test
2. User opens MU01 in Edit Mode and updates. | Error Number | Msg Rsp Fmt
| MU01A | ROC 1 Test - Update 1
| MU02 | ROC 2 Test
3. While MU01 is still in Edit Mode, filter on ROC column is applied sorting ROC asc. Updates made in Step 2 remain. | Error Number | Msg Rsp Fmt
| MU01A | ROC 1 Test - Update 1
| MU02 | ROC 2 Test
4. User opens MU02 in Edit Mode and row | Error Number | Msg Rsp Fmt
| MU01A | ROC 1 Test - Update 1
| MU02A | ROC 2 Test - Update 2
5. User exits edit mode. MU01 changes abandoned | Error Number | Msg Rsp Fmt
| MU01 | ROC 1 Test
| MU02A | ROC 2 Test - Update 2

## Sheet2 (hidden)
Pass | Reported | Regression
Fail | Retest In Progress | Major | Functionality
Pass with Comments | Return to Dev | Minor | UI
Resolved
New
No Action