## SUMMARY
|  | Count of Scenario Type | Column Labels
QA Cycle | Hours | Row Labels | No Action | Resolved | Grand Total
1 | 0.5 | 1 | 4 | 22 | 26
|  | 2026-08-07 | 1 | 1 | 2
|  | Functionality | 1 |  | 1
|  | UI |  | 1 | 1
|  | 2026-08-10 |  | 1 | 1
|  | UI |  | 1 | 1
|  | 2026-08-11 | 2 | 2 | 4
|  | Functionality |  | 1 | 1
|  | UI | 2 | 1 | 3
|  | 2026-08-12 | 1 | 18 | 19
|  | Functionality | 1 | 2 | 3
|  | UI |  | 16 | 16
|  | Grand Total | 4 | 22 | 26
|  | Row Labels | No Action | Resolved | Grand Total
QA Cycle 2 |  |  |  | 8:00
Row Labels | New | No Action | Resolved | Grand Total
Functionality | 2 | 2 | 3 | 7
Major |  | 1 | 2 | 3
Minor | 2 | 1 | 1 | 4
UI | 1 | 2 | 19 | 22
Minor | 1 | 2 | 19 | 22
Grand Total | 3 | 4 | 22 | 29
QA Cycle 3 |  |  |  | 1:00
Count of Status | Column Labels
Row Labels | No Action | Resolved | Grand Total
Functionality | 2 | 5 | 7
Major | 1 | 2 | 3
Minor | 1 | 3 | 4
UI | 2 | 21 | 23
Minor | 2 | 21 | 23
Grand Total | 4 | 26 | 30

## DEFECTS
ID | QA Cycle | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Section(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 1 | 2026-08-07 | PB Only | Functionality | Minor | No Action | General | NG Exhibit List Search dialog box allows user to interact with PB menu/2nd row icons | Opening the Exhibit List window displays the Exhibit List Search dialog box, which locks the rest of the application until the user enters a value or closes the dialog. PB then releases the lock and restores normal application interaction. NG Exhibit List Search does not lock the rest of the Vision application | 06HF0973 - Lavoie, Shaine Joseph (Jury Trial) |  |  | Confirmed with Melanie that this issue was previously discussed. The initial impact is minimal to none, so the defect is being logged for tracking and future review. | tabled
2 | 1 | 2026-08-07 | Both | UI | Minor | Resolved | General | Exhibit List Search dialog box scaling disabled after position adjustment | 1. Open Exhibit List window 2. Move Exhibit List Search dialog box 3. Minimize window - scaling stops working when the dialog’s initial position is moved. Note: This defect does not occur when the window remains locked, as in the legacy version. If user does not move Exhibit List Search dialog box, issue does not occur | 11CF1199 - Gana, Annamaria Magno | 2026-08-30 | Pass with Comments | If the window locks when the Exhibit List Search dialog is displayed, then no issues. 08/30/26: Window locks, but scaling issue persists. Not an issue. No action needed. | fixed
3 | 1 | 2026-08-10 | Both | UI | Minor | Resolved | Exhibit List window - Header | Clerk Name field sequence order does not match the PB. | Clerk Name field sequence order does not match the PB. | 08ZF0025 - Dickson, Roy Chester (Jury Trial 06/08/2012) | 2026-08-30 | Pass | Not a show stopper. | skipping, it goes in alphabetical order now, before it had no order i can see
4 | 1 | 2026-08-11 | PB Only | UI | Minor | No Action | General | Window freezing during scaling. | PB window becomes unresponsive when resized. It appears that there a significant delay in response Note: this occurs for all NG windows | 19WF1735 - Holguin, Andrew Isaiah |  |  | This defect appears to be existing in the current NG windows. | tabled
5 | 1 | 2026-08-11 | Both | Functionality | Minor | Resolved | General | Window fails to load a new case number when Select button is clicked before case data loads. | In the Exhibit List Search dialog, when a user enters a new case number and clicks Select, the application continues displaying the previous case number instead of the newly selected one. The legacy version behaved by automatically selecting the first hearing dt_event and updating the window to show the new case. If possible, dealy enabling Select button until data for case in Case Number field is loaded? | 14CF0243 - Hoffman, Sim Carlisle Dr 07NF2178 - Murtaza, Iftekhar | 2026-08-30 | Pass |  | fixed
6 | 1 | 2026-08-11 | Both | UI | Minor | Resolved | Exhibit List Search | Exhibit List Search error msg on the bottom left corner. | Exhibit List Search error msg on the bottom left corner is not displaying correctly. | Replicate by not using the full case #: 23WF0096 - Shahin, Amro Mahmoud Abdelfattah PB window does not display this message - is there a need for it? Seems redundant as Hearings section already has 'No records to display' message | 2026-08-28 | Pass | Legacy version do not use error msg. | fixed
7 | 1 | 2026-08-11 | Web Only | UI | Minor | No Action | Column Seq | For Web/NG version of Exhibit History for the selected exhibit is not in the Defendant ascending order. | The Web/NG version of the Exhibit History page does not display the defendants in ascending order for the selected exhibit. The current ordering appears to be DT_ACTIVITY ascending order. This makes it harder for users to quickly scan, compare, or verify defendant-related information for that exhibit. Expected sequence order would be Defendant (ASC) and DT_ACTIVITY(ASC). | Reserved for Exhibit History window testing
8 | 1 | 2026-08-12 | Both | Functionality | Major | No Action | Exhibit List Search | Case Number field keystroke speed allowing override of text if typing too fast | UI Guidelines #38: should be set to 250ms to address issue |  |  |  |  | tabled - only searches when on 'Enter' or click away
9 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List Search | Date format should me MM/DD/YYYY | Missing leading '0' for single-digit months; see Court Control window for reference in formatting | 16WF0127 - Bynum | 2028-08-28 | Pass |  | fixed
10 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List Search | Defendant section filters for columns are cut off | Issue previously reported but fix was to add a scroll bar to view filter box that stretches past section - not sure if this can be implemented into search window | 16WF0128 - Garcia; Martinez 24ZF0004 | 2028-08-28 | Pass |  | fixed
11 | 1 | 2026-08-12 | PB Only | Functionality | Major | Resolved | Exhibit List Search | Cancel button closes window, leaves Exhibit List window open in background | Should window close as well? In Minutes, if Case Search is closed the Minutes window also closes. |  | 2028-08-28 | Pass |  | fixed
12 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List Search | Highlight missing from top row in Hearings Section | 1. Enter 16WF0127 > window displays 4 rows 2. Press Select button 3. Window opens 09/07/16 date but was not highlighted in Exhibit Search window | PB uses hand/pointer icon to indicate selected case; might be related to ID #5 | 2028-08-28 | Pass |  | fixed
13 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List Search | Defendants section 'Selected' column - indicators should be bolded | Missing bold format on 'X' indicator; appears to be correctly formatted on Exhibit List window (ID, Rcvd columns) | 21CF1868 - Hernandez | 2028-08-28 | Pass |  | fixed
14 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | General | Minimized view of window misaligns data | Fix Breakpoints so that labels align with orresponding fields |  | 2026-08-30 | Pass |  | fixed
15 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - Binocular Icon/ tooltip | Binocular Icon launches Exhibit List Search but tooltip reads 'Case Search' | Adding to see if we should replace with different icon; binocular typically used for Case Search and/or to remove tooltip as it's misleading | Adding for discussion | 2026-08-30 | Pass |  | fixed
16 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - Date of Hearing Field | Update format to MM/DD/YYYY | UI Guidelines #18 |  | 2026-08-30 | Pass with Comments | Printed Exhibit List needs updated format, ID #27 | fixed
17 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - Header | Fix alignment of labels/corresponding fields |  |  | 2026-08-30 | Pass |  | fixed
18 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - Header Case Name | Align label to 'People VS.' field; appears to be center aligned with defendant name |  |  | 2026-08-30 | Pass |  | fixed
19 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - Header | Highlighting data | User is able to highlight defendant name (when clicked cell gets blue border) but is disabled in other fields - should this be applied to all fields in header? | Adding for discussion | 2026-08-30 | Pass |  | fixed
20 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Exhibit List - column borders | Column borders appear to be thicker than other windows; size should match the right border of Court Location column |  |  | 2026-08-30 | Pass |  | fixed
21 | 1 | 2026-08-12 | Both | Functionality | Major | Resolved | Filter discrepancies with 'X' indicator | ID and Rcvd columns do not have filter Sealed has filter - once filter is selected True/False are available for selection in that column | Remove filter for Sealed as other indicator columns do not have filter |  | 2026-08-30 | Pass |  | fixed
22 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Printed Exhibit List | Fix page margins to match PB: - Header/footer are too close to page edge - Footer - Received by line is cut off |  |  | 2026-08-30 | Pass |  | fixed
23 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Printed Exhibit List | Change font on printed document to Arial |  |  | 2026-08-30 | Pass |  | tabled
24 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Printed Exhibit List | Top/Center Justify column labels |  |  | 2026-08-30 | Pass |  | fixed
25 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Printed Exhibit List | Make bottom border same weight as other borders in column headers (current version appears to be smaller) |  |  | 2026-08-30 | Pass |  | tabled
26 | 1 | 2026-08-12 | Both | UI | Minor | Resolved | Printed Exhibit List | Center align data in all columns except for Description (remain as left justified) |  |  | 2026-08-30 | Pass |  | fixed
27 | 2 | 2026-08-30 | Both | UI | Minor | Resolved | Printed Exhibit List | Update Exhibit List (Date of Hearing Field & Report Date) format to MM/DD/YYYY | UI Guidelines #18 |  | 2026-09-04 | Pass | Footer date format is not in MM/DD/YYYY, instead shows in M/D/YYYY. | fixed
28 | 2 | 2026-08-30 | Both | Functionality | Minor | Resolved | Filter discrepancies with 'X' indicator | Remove filter for columns with indicators | Remove filter for "Returned", "Replaced By Photo", "Prior Exbt#" as other indicator columns do not have filter |  | 2026-09-04 | Pass |  | fixed
29 | 2 | 2026-08-30 | Both | Functionality | Minor | Resolved | Exhibit Number column filter | Exhibit Number column filter displays incorrectly for any alpha letters. | Exhibit Number column filter only filters for numerical values. Text values are also used for the numbering system for exhibits. | 10SF1040 - Pappas, John. Check "Defense" list or "Court" list with texts. | 2026-09-04 | Pass with Comments | Filter display has been corrected, however, it displays in wrong order. For example, 1, 10, 100, 101… and not 1, 2, 3, 4…. | fixed
30 | 3 | 2026-09-04 | Both | UI | Minor | Resolved | Bionocular alignment | Align bionocular button | Bionocular button is misaligned. Align the height with "Case #" field. |  | 2026-09-04 | Pass
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action