## DEFECTS
ID | QA Cycle | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Section(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 1 | 2026-09-08 | Both | Functionality | Major | New | Hearings Add Button | New hearings won't display when selected. | When using the Hearing Add (green) button, the ‘New Hearings List for Exhibit’ dialog box appears. When a hearing date is selected, it should be added to the ‘Hearings with Exhibits’ section (top‑right) on the main screen. However, the selected hearing is not appearing as expected. | 14CF0243 - Hoffman, Sim Carlisle | 2026-09-16 | Pass |  | 09/11 SM - has been addressed. Double clicking on new hearing row now applies onto hearings grid.
2 | 1 | 2026-09-08 | Both | UI | Minor | New | Hearings Add Button | Increase the plus sign font size to make it clear. | The plus sign appears too small and unclear. Please increase its size to improve visibility. | 14CF0243 - Hoffman, Sim Carlisle | 2026-09-16 | Pass |  | 09/11 SM - increased label to font-size 16px
3 | 1 | 2026-09-08 | Both | Functionality | Major | New | Exhibit To section | "Exhibit To" section default display should be empty. | The ‘Exhibit To’ section currently displays exhibits associated with the selected row in ‘Hearings with Exhibits’ by default. PB requires double-click to display them. Default view should be blank, and when double-clicked then display them. | 14CF0243 - Hoffman, Sim Carlisle | 2026-09-16 | Pass |  | 09/14 SM - double clicking in hearings grid now populates the exhibit to grid
4 | 1 | 2026-09-08 | Both | UI | Minor | New | Hearings with Exhibits | Column center align content. | Center-align the content in the Court Location column. |  | 2026-09-16 | Pass |  | 09/11 SM - Leaving as-is. Text should be left aligned UI Guideline ID#23
5 | 1 | 2026-09-08 | Both | UI | Minor | New | Exhibits From | Column center align content. | Center-align the content in these columns - Exhibit Number - Court Location |  | 2026-09-16 | Pass |  | 09/11 SM - Leaving as-is. Text should be left aligned UI Guideline ID#23
6 | 1 | 2026-09-08 | Both | UI | Minor | New | Exhibits To | Column center align content. | Center-align the content in these columns - Exhibit Number - Court Location |  | 2026-09-16 | Pass |  | 09/11 SM - Leaving as-is. Text should be left aligned UI Guideline ID#23
7 | 1 | 2026-09-08 | Both | UI | Minor | New | Hearings with Exhibits | Column center align content. | Center-align the content in the Court Location column. |  | 2026-09-16 | Pass |  | 09/11 SM - Leaving as-is. Text should be left aligned UI Guideline ID#23
8 | 1 | 2026-09-08 | Web Only | UI | Minor | New | Window status | Window status does not reflect correctly. | The bottom‑left corner displays the status of current transactions. The default status shows ‘Ready’ when the window is first opened. After a row is moved and saved, the status changes to ‘No pending changes found.’ and remains that way. In PB, the default status is ‘Ready,’ and after a move, it changes to ‘Update Successful,’ where it remains. In the Web version, the default status is ‘Ready,’ and after a move, it changes to ‘Saving,’ and remains at that status. |  | 2026-09-16 | Pass with Comments | Interface should have been for both. #10 will address the PB changes. | 09/15 SM - has been addressed
9 | 1 | 2026-09-08 | Both | UI | Minor | New | Entire window | Flashing issue | When opening a new window, the Exhibit Maintenance window flashes and shows multiple layers and disappears. |  |  |  | No validation needed as it is a known PB issue. | 09/11 SM - known powerbuilder issue. Waiting on Sameer
10 | 2 | 2026-09-16 | PB Only | UI | Minor | New | Window status | Window status does not reflect correctly. | The bottom‑left corner displays the status of current transactions. The default status shows ‘Ready’ when the window is first opened. After a row is moved and saved, the status changes to ‘No pending changes found.’ and remains that way. |  | 2026-09-18 | Pass | This change is a baseline change impacting multiple windows.
11 | 2 | 2026-09-16 | Both | UI | Minor | New | Case Info section | Defendant name field missing | Defendant name field should be between Adult/Juvy indicator and bionocular button. |  | 2026-09-17 | Pass
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action