## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-10-12 | Both | UI | Minor | New | Filter | Disable filtering from all columns | Remove column filters and keep sorting Filtering is not needed for this window since user will be extracting the data to an excel file. Also, it is not working when a row contains blank data in some of the columns. | 10-15-26: Per BSAs input See new UI #115 - Column filters shall be disabled if the grid is converted into an official report |  |  |  | Fixed
2 | 2026-10-13 | Both | UI | Minor | No Action | Grid column header | Columns - Hearing Date - Time | In old window the Hearing title is for both Date and Time In NG we are putting the Hearing title above the Date column | Should we just leave as is or also add the title Hearing over the Time column? See screen view #2 |  |  | 10/19/26 - BSAs leave as is It is noted the extract of the report contains more columns and some of the header titles are different than the printed window. NG is displaying the same and downloads as "xlxs" whereas in old PB window it downloads as "xls" file. | No Action
3 | 2026-10-13 | Both | UI | Major | New | Notice of Packaged Hearings | Printing to PDF | Time column is wrap (PB print out is not wrap) Violation column is cutting violations Print out to PDF footer is displaying "12:00 AM" (PB print out is showing actual time of printing to PDF) | The "Name" column width might need to be adjusted for the other columns to display in print out to PDF |  |  | See screen view #3 | Fixed
4 | 2026-10-14 | Both | UI | Minor | New | Header Field "Cases For - From:" | Open window Focus/Cursor | On window open, the cursor should land on the "Cases For - From:" | You should not have to do multiple tabbing (x3) to get to the first selection field in the window. |  |  |  | Fixed
5 | 2026-10-19 | Both | UI | Major | New | Retrieve | Data grid focus/cursor after retrieval | After a retieval the focus should be on the first row for this window so user can use the keyboard to navigate | In the data grid we should highlight the first row so user can use the keyboard to navigate between rows |  |  | See new UI #113 | Fixed
6 | 2026-10-19 | Both | UI | Major | New | Tab keypress | Buttons - Retrieve - Extract | - Tab keypress is not taking you to the "Retrieve" or "Extract" button - The focus/cursor should be on the button you are at For example: Tabbing from "Defense Counsel" is not taking you to "Retrieve" button. | Tabbing should always go from left to right and down regardless of where it is to the next selectable item to the right. Old PB window allows for tabbing to the Retireve and Extract buttons |  |  |  | Fixed
7 | 2026-10-19 | Both | UI | Major | New | Enter keypress | Buttons - Retrieve - Extract | Enter keypress is not working for the "Retrieve" or "Extract" button. | You should be able to use "Enter" keypress on the "Retrieve" button to retrieve data to the grid. You should be able to use "Enter" keypress on the "Extract" button to export the report to an excel file |  |  | Enter keypress is working on these buttons in the old PB window. | Fixed
8 | 2026-10-19 | Both | UI | Minor | New | Keyboard - Arrow pointer | Calendar Extract Pop Up Yes and No buttons | The left and right arrow pointer on the keyboard is not working and you cannot move between the Yes or No button | In old PB window it is working |  |  | In both NG and old PB window you have to use the mouse to click on the [X] to exit out of the pop up Enter keypress is working as expected for the Yes or No button | Fixed
9 | 2026-10-19 | Both | UI | Minor | New | Sorting in data grid columns | Print to PDF | The printed PDFdoes not reflect the sorting on the columns in the data grid | See screen view #9 |  |  | Per Team - We only need to fix the defect on the Sorting of the data grid so the printing to PDF matches the sorting. Please note no action need on the sorting as to the extract to excel file | Fixed
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## NG Links
ST | https://visionngst.occourts.org/Account/login
QA | https://visionngqa.occourts.org/Account/login
D2 | https://visionngpreprod.occourts.org/account/login

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action

## Screen View
#1 | Filtering on columns |  | Old window does not have filtering functionality
Example: Defense is blank for case 20HM06526 and contains data in other columns. When you filter on the blank in the Defense row the NG window should still row data
#2
#3
#9
Extract to excel file