## DEFECTS
ID | Date Reported | Interface | Scenario Type | Bug Type | Status | Window Tab | Window Section | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-07-30 | Both | UI | Minor | Resolved | Person Search | Person Search | Search Criteria alignment | Fix alignment issues as follows: 1. Add space between labels and search fields (see Bail Schedule window for reference) 2. Move 'Name' search fields to the left so that search fields are aligned with below fields (e.g., DLN, DOB, Case#) 3. Move OC Pay# and Person# fields up so that the spacing matches DLN/DOB fields | See linked mockup for requested changes | 2026-09-08 | Pass | 08/19: all fixed except for spacing reported in #3 (red text) 09/02: retest and pass 09/08: regression test and pass | Done NV: Good 8/28/2026 bullet point 3
2 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Person Search | Character Limits - DLN | DLN: character limit 15 (database limit 30, court.PERSON_INDICIES, IDENTIFIER) CRMQ sample DLN, State: L516-457-74-185-0, FL CRMP sample DLN, State: A236-724-79-600-0, FL | PB window errors if user attempts to search DL > 15 characters; should be able to enter more than 15 characters since DB limit is 30 and there are DL's that have >15 characters | 2026-09-08 | Pass | 08/19: character limit is still 15 09/02: retest and pass 09/08: regression test and pass | Done NV: Good 8/28/2026 made it 30
3 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Person Search | Character Limit & cursor alignment - OC Pay# | (1) OC Pay#: no character limit (database limit 38, court.CASE_DEF_ID, CASE_DEF_ID) - if user enters >20 numbers then tabs/clicks out of field, data overridden with '9223372036854775807' - if user enters >30 numbers then tabs/clicks out of field, data entered is cleared (2) Fix cursor alignment to be left justified to match other search crtieria fields | 40 | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
4 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Person Search | Character Limit & cursor alignment - Person# | (1) Person#: no character limit (database limit 38, court.CASE_DEFENDANT, PERSON_NBR) - if user enters >20 numbers then tabs/clicks out of field, data overridden with '9223372036854775807' - if user enters >30 numbers then tabs/clicks out of field, data entered is cleared (2) Fix cursor alignment to be left justified to match other search crtieria fields | PB character limit on front end is 18 characters | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
5 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Results | Results exceed 500 behavior | When results exceed 500, message displays Failed to load prior person results See Details... An item with the same key has already been added. Key: NULL | PB window displays 'Matching persons exceed the limit of 500, please refine your serach criteria' This message should display instead of 'Failed ot load prior person results' line | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
6 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Results | Column data alignment & DOB Sort filter placement | Adjust alignment of Name/DOB/DLN/OCN # / Person # column headers and subsequent data to be left justified (Sequence # to remain right justified so that number is close to Name) DOB asc/desc filter arrow placement should be on the right of label | Current view is difficult to read | 2026-09-08 | Pass | 08/19: see ID #44 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
7 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Results, Prior Cases for Person# | Column borders are missing | Add column borders around column headers in both Results and Prior Cases for Person# sections (see Purge Duplicate Cases for reference) | Current view is difficult to see column label/filter grouping | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
8 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Results | # value remains assigned to row when additional filters applied | 1. Enter search criteria then Search button 2. In Results section, sort by Name In NG, the # stays assigned to the row while in PB the number remains as the sort is applied. There's no sort on the # column so user has to remove sorting on other columns to return to numerical order | Adding for discussion as I'm not sure if this needs to be fixed. | 2026-09-08 | Pass | 08/28: still occurring, confirmed with BSAs/Sendhi that this needs to be fixed. 09/02: retest and pass 09/08: regression test and pass | Done 8/28/2026 fixed numbering
9 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Results | Matching Persons#:" footer text size | Increase from 11.2px to 13px (see Code Entries footer for reference); bolded text and color of text to remain |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: You are using a div here for the footer, SyncFusion has a built in GridAggregate for footers, should we be using that instead? https://blazor.syncfusion.com/documentation/datagrid/footer-aggregate Fiscal/FiscalCommon/CheckInfo/D_ct_fscl_payment_hist_detail.razor uses it as an example.
10 | 2026-07-30 | Both | UI | Minor | Resolved | Person Search | Prior Cases for Person# | Font Size & alighment of 'All' next to checkbox | Increase from 13px to 14px to match column headers Fix alignment of labels as column names appear higher than "All" text |  | 2026-09-08 | Pass | 08/19: fixed except for alignment reported in red text 09/02: retest and pass 09/08: regression test and pass | Done NV: Done 08/28/2026 made checkbox and ALL go down 2px
11 | 2026-07-30 | Both | UI | Minor | Resolved | Person Search | Prior Cases for Person# | Selecting cases removes blue alternating row highlight | When user selects blue row in section, color is removed and row becomes white | Alternating row color should remain, see Purge Duplicate Cases for reference | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
12 | 2026-07-30 | PB Only | Functionality | Major | Resolved | General |  | Window name updates to selected case scenarios | Scenario 1: 1. Open window - named "Priors" as expected 2. Search for case, select, and move to Selected Cases section 3. Go to Priors Cases Details tab - window name updates to PUBLIC_CASE/Last Name, First Name Scenario 2: 1. After completing steps in Scenario 1, retrun to Person Search and clear Selected Cases and Reset Person Search - window name remains as PUBLIC_CASE/Last Name, First Name from Scenario 1 2. Execute new search and select case 3. Use arrow button to move case to Selected Cases - window name updates to new selected PUBLIC_CASE/Last Name, First Name | Window name should not be updated, should remain labeled as "Priors" | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
13 | 2026-07-30 | Both | Functionality | Major | Resolved | General |  | F3 Refresh fails | Shortkey does not work in window | It's configured under File > Refresh F3 but also doesn't work in PB window | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Good
14 | 2026-07-30 | Both | Functionality | Major | Resolved | Person Search | Selected Cases | Remove button fails for codefendant cases | 1. Move all codefendants of codefendant case to Selected Cases 2. Remove one codefendant from Selected cases section NG incorrectly removes all codefendants; the only one that should be removed is the case/defendant where the remove 'X' button is used |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
15 | 2026-07-30 | Both | UI | Minor | Resolved | Person Search, Prior Cases Details | Person Search Tab, Selected Cases, Defendant/ case section | Modify icon next to defendant name and Person Search tab | Typically 2 person icon in Vision is associated with codefendant cases. For NG window can we use SyncFusion Office Fabric icon 'user' (PUA: e9db) instead? |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
16 | 2026-07-30 | Both | UI | Minor | Resolved | Person Search, Prior Cases Details | Person Search Tab, Selected Cases, Defendant/ case section | Defendant Name (person_nbr) font color | Defendant name should be #00008b, currently is black and blends in with case numbers |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
17 | 2026-07-30 | Both | UI | Major | Resolved | Selected Cases, Prior Cases Details | Defendant/ case section | Highlight appears on both codefendant case | In Prior Cases Details, both codefendants are highlighted when the first selected case is a codefendant case. This needs to be updated to only highlight the case/defendant that is selected/displaying case defendant data |  | 2026-09-08 | Pass | 08/19: see ID #45 09/02: retest and pass 09/08: regression test and pass | Done NV: Done
18 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Header, Probation section | Red text coloring | Red text in section (Status: Warrant, Collections/Collab. Court/ATP Pending indicators) should be #CC0000 Probation (Active) should be #CC0000 | Fiscal section red text color to remain as it is already #CC0000 | 2026-09-08 | Pass | 08/19: see ID #46 09/02: retest and pass 09/08: regression test and pass | 8/28/2026 done
19 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Scheduled Hearings | Padding on section header | Add 2px padding on header to match other section headers (e.g., Fiscal, Charges, and Sentences) |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
20 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Scheduled Hearings - Date column | Hearing date format | Update to use 4-digit year |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
21 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Scheduled Hearings, Charges, Sentences | Column borders are missing in sections | Add column borders around column headers in Scheduled Hearings, Charges, and Sentences sections (see Purge Duplicate Cases for reference) | Current view is difficult to see column label/sorting | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
22 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Charges | Viol Dt format | Update to use 4-digit year |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
23 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Charges | Placement of sorting arrows | Adjust so that asc/desc arrows appear to right of column header; Cnt, Viol Dt are incorrectly placed on the left and OL filter overlaps with text |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
24 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Sentences | Date | Update to use 4-digit year |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
25 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Sentences | Placement of sorting arrows | Adjust so that asc/desc arrows appear to right of column header; Seq. and Date are incorrectly placed on the left |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
26 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Probation | End Dt and left justify text | Update to use 4-digit year and move data to be left justified (currently right justified) |  | 2026-09-08 | Pass | 08/19: see ID #46, 47 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
27 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | Booking | Dt Booked | Update to use 4-digit year; placeholder view is 00/00/00 but after moving cursor into filed, format updates to 00/00/0000 |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
28 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Booking | Character Limit - Booking # | Booking #: character limit 13 (database limit 15, court.ARREST, BOOKING_NUM) | PB window field limits to 13 characters in all places where booking number is entered (Case Maintenance, Priors) but seems to be limited to sizing limitations of old window With NG, should we update this field to match database limit? | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
29 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Booking | Booking # and Dt Booked fields clear after saving | After saving Booking # and Dt Booked fields, Vision NG window clears fields where PB windows keep entered data on window | Data should be retained in window 09/02: when record does not exist in court.arrest table, NG is allowing to save PWCHG but fails to update table; PB throws an error message for this scenario; per discussion with JL going to fix to display error message for scenario | 2026-09-08 | Pass | 08/19: retested and issue resolved itself, no longer occurring 09/02: retested and issue reoccurring; PM - retest and pass 09/08: regression test and pass | cannot replicate
30 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Booking | Dt Booked - min/max date | User can save dates before 01/01/1900 and after 12/31/2099 in field. Should this field have min/max validations like our other date fields? | Adding for discussion as I'm not sure if this needs to be fixed; current PB version uses 2-digit year so cannot compare | 2026-09-08 | Pass | 08/19: validation added 'Dt Booked must be between 01/01/1900 and 12/31/2099.' 09/02: regression test and pass 09/08: regression test and pass | Done NV: Fine if BSAs ok with no date range validation
31 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Time field | Change from dropdown selection to input as there are scenarios where user needs to be able to enter minutes other than 15 second increments Default value to remain at 08:30 AM |  | 2026-09-08 | Pass | 08/28: remove dropdown and have user input data, confirmed with BSAs/Sendhi that this needs to be fixed 09/02: retest and pass 09/08: regression test and pass | Done NV Fine if BSAs ok with allowing any input 8/28/2026 REMOVED DROP DOWN although it was set to 1 minute interval
32 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Courtroom dropdown missing search field | List is missing search bar; see Courtroom Setup for reference |  | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
33 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Hearing dropdown missing search field | List is missing search bar; see Courtroom Setup for reference |  | 2026-09-08 | Pass | 08/19: see ID #48 09/02: retest and pass 09/08: regression test and pass | Done NV: Done
34 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Hearing Date/Time FluentValidation | Appear Date: 07/20/26 Time: 08:30 AM Courtroom, Hearing, Requested By filled out At 09:50AM, window fails to save docket code as time is after 08:30 AM | PB window allows for this same scenario to save; FV should be removed | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
35 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | PKG/JC - missing dropdown when Y is selected | NG incorrectly allows user to save and saves without the location PB provides error message if dropdown is NULL | Docket code should have failed without the location parameter | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
36 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Time and Courtroom clear after saving | NG - after saving a hearing, window resets Time field to 08:30 AM and clears courtroom selected PB - window retains these fields of what was previously saved so that user does not have to reenter values |  | 2026-09-08 | Pass | 08/19: see ID #54 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
37 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Admin Min. | Defendant name missing in Admin Min window | Admin Min button used to open window, defendant name missing from window title and header section in Admin Min window | Same scenario in PB window does not cause issue; might be out of scope but adding for discussion/review | 2026-09-08 | Pass | 08/28: still occurring, confirmed with BSAs/Sendhi that this needs to be fixed. 09/02: retest and pass 09/08: regression test and pass | 8/28/2026 Admin Min passes name now
38 | 2026-07-30 | Web Only | Functionality | Major | No Action | Prior Cases Details | CIS, Min & Other button | Does not work in web | Not sure if this is going to be addressed now or later? |  | 2026-08-19 | Pass with Comments | 08/19: web printing does not work | This is not a migrated to Blazor. Keep on side note for "future"
39 | 2026-07-30 | Web Only | Functionality | Major | Resolved | Prior Cases Details | Copies button | Does not work in web | Not sure if this is going to be addressed now or later? This is the Print - Copies Spec. window |  | 2026-08-19 | Pass with Comments | 08/19: migrated and tested changing defaults and passed; actual printing does not work | This is not a migrated to Blazor. Keep on side note for "future"
40 | 2026-07-30 | Both | UI | Minor | Resolved | Prior Cases Details | General | Reduce window size causes docket codes to overlap with data | When window is reduced, docket code section overlaps with data rather than resizing like Person Search. | Person Search tab seems to resize/not overlap so adding | 2026-09-08 | Pass | 09/02: regression test and pass 09/08: regression test and pass | Done NV: Done
41 | 2026-07-30 | PB Only | Functionality | Major | Resolved | Prior Cases Details | CIS, Min & Other button | Missing Print - Copies Spec. dialog on first instance of click in window | In PB, Print - Copies Spec. window appears when CIS, Min & Other button is used for the first time in the window to set the # of copies to print. Once set, it maintains the copies until the window is closed or Copies button is used to reconfigure values. NG is missing this initial window and goes straight to printing | PB Scenario/behavior 1. Open window 2. CIS, Min & Other - Print Spec Copies dialog opens 3. OK 4. Prints silently 5. CIS, Min & Other 6. Prints silently | 2026-09-08 | Pass | 08/19: see ID #51 09/02: regression test and pass 09/08: regression test and pass | Done NV: Exists, but might want to check stylings with BSA, they might want to use pre-existing stylings we have like visiongridheader or visionsearch.
42 | 2026-07-30 | PB Only | UI | Minor | Resolved | Prior Cases Details | CIS, Min & Other button | Minutes printout appears to be larger page size compared to other printed docs | See screnshot for reference | Adding as not sure if this is going to cause issues when physically printed 09/02: Sameer/Santiago to address | 2026-09-08 | Pass | 08/19: issue still occurring 09/03: resolved from Santiago's changes 09/08: regression test and pass | Refer to Sameer
43 | 2026-07-30 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Concurrent updates allowed for schedling | Able to calendar same date, time, courtroom, hearing type for case when using web app and Vision app | Should be prevented, concurrent updates should not be allowed | 2026-09-08 | Pass | 09/08: regression test and pass | Done NV: Done
44 | 2026-08-20 | Both | UI | Regression | Resolved | Person Search | Results | Align data to top of row | Data should be aligned to the top of the row Current NG shows #, DOB, DLN, OCN #, and Person # as centered in the row if defendant has multiple associated names | Regression bug as the top alignment was correct in QA Cycle 1 (see screenshot for reference) | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 fixed with item8
45 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Case Details | Selected Cases | Highlight should revert to top/first case when toggling between tabs | 1. In Person Search tab, search for codefendant case and move all codefendants to Selected Cases section. 2. Select Prior Cases Details - highlight is on first case/row as expected 3. While in Prior Cases Details tab, select/highlight the third row 4. Select Person Search tab 5. Select Prior Cases Details tab At step 5, highlight should revert to first case/row as this is the current PB logic. Currently, the highlight remains on the case last selected | Sample CRMQ Case: 00086 Marshall, Daubney, Reola Not sure if this was introduced with the fix for ID #17 | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 fixed
46 | 2026-08-20 | Both | UI | Regression | Resolved | Prior Cases Details | Probation | Red text coloring is missing from certain probation statuses | Active, Re-activated, and Revoked statuses should be red (#CC0000) as stated in ID #19. Colored formatting was inadvertently removed from these statuses | Regression bug as the color was correct in QA Cycle 1. | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 fixed with item 46
47 | 2026-08-20 | Both | UI | Regression | Resolved | Prior Cases Details | Probation | Font size of Probation Data | Data for Type, Status, and End Dt were updated to 14 px. Should be 12px to match display in other sections | Regression bug as this was the correct font size in QA Cycle 1 09/02: 13px to match other non-grid text in window | 2026-09-08 | Pass | 09/08: regression test and pass | I DONT SEE THIS SCREEN SHOT SHOWS 13px like the rest
48 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Hearing and ROC field dropdowns search by Description | 1. Open case in Prior Cases Details tab and go to Scheduling section. 2. Select Courtroom 3. In Hearing field, use search bar to enter 'ARGN' for Arraignment NG displays No Records Found message as the search is filtered out due to description spelling even though the code is spelled 'ARGN' | Same issue occurs in ROC field Fix this dropdown to search by code as this is how PB window behaves. PB window does not filter but instead navigates user to first matching results based on code | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 done
49 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Time field cursor adds characters to the front of time rather than overriding time | Place cursor in time field then start typing new time - NG window displays the newly added digits in front of the existing time in the field | In PB, user can type and it overrides the default HH:MM | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 Overwrite text
50 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Time field cursor flickers when entering too fast | Fix keystroke speed so that it is 250MS; user can see cursor flicker when typing in field | UI Guidelines #38 | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 no debouncer exists on timepikcer - regardless we removed popup
51 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Cases Details | CIS, Min & Other button | Two print dialog windows occurring | Initial click opens Print - Copies Spec. window as expected. Once values set, 1. 'Save Print Output As' window (Vision default printer set to PDF) appears - attempt to save file 2. then the Batch Printing Window - save file At Step 1 it appears file saves but it just creates a 0 KB file and then errors when attempting to open in Adobe. The Batch Print one saves successfully and can view | PB only displays 'Save Print Output As' window as that is the default printer setup. With the change to BP window, not sure if this should still be appearing? 09/02: Sameer/Santiago to address | 2026-09-08 | Pass | 09/08: SS implemented fix to use court control; passed with N configuration | 8/28/2026 Refer to Sameer
52 | 2026-08-20 | PB Only | Functionality | Major | Resolved | Prior Cases Details | Copies button |  | Fails to launch Print - Copies Spec. window; appears to be treated as a direct print button instead In NG when selected, it goes straight to batch print |  | 2026-09-02 | Pass with Comments | 09/02: issue resolved itself | 8/28/2026 can't replicate
53 | 2026-08-20 | PB Only | Functionality | Major | No Action | Prior Cases Details | CIS, Min & Other button | Batch Printing dialog opens in different window | When Vision app is on secondary monitor and button is used, Batch Print opens in primary monitor If Vision app is on primary monity and button is used, issue does not occur |  | 2026-09-02 | Pass with Comments | 09/02: issue occurs in legacy app | 8/28/2026 same thing happens on legacy window - probably a microsoft default thing
54 | 2026-08-20 | Both | Functionality | Major | Resolved | Prior Cases Details | Scheduling | Time and Courtroom clear after saving and moving to new case | 1. In Person Search tab, select cases and move to Selected Cases section. 2. On first case, calendar hearing and save. 3. Select next case: in NG, Appear Dt, Time, and Courtroom all reset to defalut values. In PB - window retains what was previously saved in these fields so that user does not have to reenter values when selecting other cases Alternate Scenario: 1. Complete above steps and return to Person Search, clear previously selected cases and perform new search. 2. Select cases and go to Prior Cases Details 3. In NG, the Appear Dt, Time, and Courtroom all reset to default values while PB maintains the values in the scenario. Until the window is closed the values then reset to defaults as it appears Reset button does not work for this section in PB | Fix for ID #36 retains defaults on saved case but resest when selecting another case | 2026-09-08 | Pass | 09/08: regression test and pass | 8/28/2026 fixed
55 | 2026-08-20 | Both | Functionality | Minor | Resolved | Person Search | Person Search | Character Limits - OCN | OCN: character limit 38 (database limit 30, court.PERSON_INDICIES, IDENTIFIER); search field allows more characters than DB limit | UI Guidelines #19 | 2026-09-08 | Pass |  | 8/28/2026 - fixed
56 | 2026-09-02 | Both | UI | Minor | Resolved | Prior Cases Details | Scheduling | Long text in Minutes |  |  | 2026-09-08 | Pass
57 | 2026-09-02 | Both | UI | Minor | Resolved | Prior Cases Details | Probation | Bolded weight | Status weight is currently 1000px - can this be updated to 700px to match bolded weight in header |  | 2026-09-08 | Pass
58 | 2026-09-22 |  |  | Major | Resolved | Person Search |  | [UAT #1] Failed to load case booking message keeps triggering for all users except for KA + PDC | Person Search - Failed to load case booking message keeps triggering for all users except for KA + PDC | From UAT Defect Log - PRIORS #1 (Operations; tester All; severity High). | 2026-09-23 | Pass | 26WM09320, 26WM08899 - Sierra, Angel Luis Pass courtroomsu profile - able to save Scheduling changes in the window Pass bail schedule profile - able to save Scheduling changes in the window
59 | 2026-09-22 |  |  | Major | Resolved | Prior Case Details |  | [UAT #2] Hearing drop down failing for users except for KA + PDC | Prior Case Details - Hearing drop down failing for users except for KA + PDC | From UAT Defect Log - PRIORS #2 (Operations; tester All; severity High). | 2026-09-23 | Pass | 26WM09320, 26WM08899 - Sierra, Angel Luis Pass courtroomsu profile - able to save Scheduling changes in the window Pass bail schedule profile - able to save Scheduling changes in the window
60 | 2026-09-22 |  |  | Major | Resolved |  |  | [UAT #3] 1. Add hearing using Admin Min. and Save 2. Close Admin Min 3. Select Person Search then Prior... | 1. Add hearing using Admin Min. and Save 2. Close Admin Min 3. Select Person Search then Prior Cases Details: PB window refreshes with added hearing but NG window does not refresh | From UAT Defect Log - PRIORS #3 (Operations; tester MJ; severity High). | 2026-09-23 | Pass | Courtroomsu profile: Admin minutes entry, F3 refresh on tab 2 displays updates.

## SUMMARY
|  | Count of Scenario Type | Column Labels
QA Cycle | Hours | Row Labels | Resolved | No Action | Grand Total | Row Labels | Count of Bug Type | Row Labels | Count of Status
1 | 0.83333 | 2026-07-30 | 42 | 1 | 43 | Major | 34 | Resolved | 55
|  | Functionality | 24 | 1 | 25 | Minor | 20 | No Action | 2
|  | UI | 18 |  | 18 | Regression | 3 | Grand Total | 57
2 | 0.41667 | 2026-08-20 | 11 | 1 | 12 | Grand Total | 57
|  | Functionality | 8 | 1 | 9
|  | UI | 3 |  | 3
3 | 0.41667 | 2026-09-02 | 2 |  | 2
|  | UI | 2 |  | 2
|  | Grand Total | 55 | 2 | 57

## Generated Rules
ID | Tab | Field | Scenario | Result | Pass/Fail | ID # | Restest Date | Pass/Fail | ID #
1 | Person Search | Name | Bus. / Last only used | Search executed | Pass with Comments | 5 | 2026-09-02 | Pass
2 | Person Search | Name | First only used | No results, last name required (Please enter Last name) | Pass |  | 2026-09-02 | Pass
3 | Person Search | Name | Middle only used | No results, last name required (Please enter Last name) | Pass |  | 2026-09-02 | Pass
4 | Person Search | Name | First & Middle only used | No results, last name required (Please enter Last name) | Pass |  | 2026-09-02 | Pass
5 | Person Search | Name | First/Last used | Search exectued | Pass |  | 2026-09-02 | Pass
6 | Person Search | Name | Middle/Last used | Search exectued | Pass |  | 2026-09-02 | Pass
7 | Person Search | Name | First/Middle/Last used | Search executed | Pass |  | 2026-09-02 | Pass
8 | Person Search | Name | NULL all fields (No Additional Serach Criteria) | Please enter a search criteria. | Pass |  | 2026-09-02 | Pass
9 | Person Search | Additional Search Criteria | DLN CA | Search executed | Pass |  | 2026-09-02 | Pass
10 | Person Search | Additional Search Criteria | DLN Other State (FL) | Search executed | Pass |  | 2026-09-02 | Pass
11 | Person Search | Additional Search Criteria | DOB | Search executed | Pass |  | 2026-09-02 | Pass
12 | Person Search | Additional Search Criteria | OCN | Search executed | Pass |  | 2026-09-02 | Pass
13 | Person Search | Additional Search Criteria | Case # | Search executed | Pass |  | 2026-09-02 | Pass
14 | Person Search | Additional Search Criteria | OC Pay # | Search executed | Pass with Comments | 3 | 2026-09-02 | Pass
15 | Person Search | Additional Search Criteria | OC Pay # (Enterprise) | Search executed | Pass with Comments | 3 | 2026-09-02 | Pass
16 | Person Search | Additional Search Criteria | Person # | Search executed | Pass with Comments | 3 | 2026-09-02 | Pass
17 | Person Search | Additional Search Criteria | Person # (Enterprise) | Search executed | Pass with Comments | 3 | 2026-09-02 | Pass
18 | Person Search | General | Search Button | Executes per search criteria | Pass |  | 2026-09-02 | Pass
19 | Person Search | General | Reset Button | Clears Person Search, Results, and Prior Cases sections and unchecks Select All checkbox | Pass |  | 2026-09-02 | Pass
20 | Person Search | General | Search with no match | Create new record message displays | Pass |  | 2026-09-02 | Pass
21 | Results | General | Single Click | Loads Prior Cases for Person # section and updates header with person_nbr | Pass |  | 2026-09-02 | Pass
22 | Results | General | Double Click | Person Information Select window launches for row | Pass |  | 2026-09-02 | Pass
23 | Prior Cases | General | Single Click | Checkbox marked; selects row | Pass |  | 2026-09-02 | Pass
24 | Prior Cases | General | All checkbox | Selects/deselects all cases associated to selected person_nbr | Pass |  | 2026-09-02 | Pass
25 | Prior Cases/Selected Case | Arrow button | No cases selected in Prior Cases | Message: Please select a case. | Pass |  | 2026-09-02 | Pass
26 | Selected Cases | General | X Button next to case number | Deletes case/defendant row only | Fail | 14 | 2026-09-02 | Pass
27 | Selected Cases | General | Clear All button | Asks for confirmation | Pass |  | 2026-09-02 | Pass
28 | Selected Cases/Prior Cases Details | General | Details Button | If no cases in Selected Cases, shows "Please select a case to view details" | Pass |  | 2026-09-02 | Pass
29 | Prior Cases Details | Booking | Booking # and Dt Booked both required | Adds PWCHG if both are entered; fails if one is missing | Pass with Comments | 27 | 2026-09-02 | Pass
30 | Prior Cases Details | Scheduling | Hearing | Adds CLADD | Pass |  | 2026-09-02 | Pass
31 | Prior Cases Details | Scheduling | Hearing/ROC | Adds CLADD | Pass |  | 2026-09-02 | Pass
32 | Prior Cases Details | Scheduling | Hearing with PKG/JC Y selected | Dropdown with JC appears for selection, adds CLPKG | Pass with Comments | 33 | 2026-09-02 | Pass
33 | Prior Cases Details | Scheduling | Hearing/ROC with PKG/JC Y selected | Dropdown with JC appears for selection, adds CLPKG2 | Pass with Comments | 33 | 2026-09-02 | Pass
34 | Prior Cases Details | Scheduling | Calendaring | Weekend and Court Holiday dates should fail | Pass |  | 2026-09-02 | Pass
35 | Prior Cases Details | Scheduling | Calendaring | Duplicate date/time/hearing type fails | Pass with Comments | 29 | 2026-09-02 | Pass
36 | Prior Cases Details | NTCWI | All parameters filled | Docket code saves | Pass |  | 2026-09-02 | Pass
37 | Prior Cases Details | JLBAIL | All parameters filled | Docket code saves | Pass |  | 2026-09-02 | Pass
38 | Prior Cases Details | DSTUP | All parameters filled | Docket code saves | Pass |  | 2026-09-02 | Pass
39 | Prior Cases Details | FIFCI | All parameters filled | Docket code saves | Pass |  | 2026-09-02 | Pass
40 | Prior Cases Details | Scheduled Hearings | X Button next to hearing | Do you want to vacate '07/20/26 08:30 AM' hearing at W7? With Yes/No buttons | Pass |  | 2026-09-02 | Pass

## 1
Current View | Expected View

## 6
Current PB version has all fields (except for #) left justified column header and corresponding text

## 10
All' text alignment is slightly lower than column headers.

## 12
SCENARIO 1: window correctly opens as 'Priors'
Window remains labeled as 'Priors' after initial search, select, and case moved to Selected Cases
After selecting Details button OR Prior Cases Details tab, window name updates to PUBLIC_CASE/Last Name, First Name
Returning to Person Search tab retains incorrect window name
SCENARIO 2: After clearing Selected Cases and Results, incorrect name still displays; after new search executed and arrow (>) button is used to move case, window name gets updated again

## 15
Request to update to use 'user' icon
Appears to be using 'people' icon

## 17
MUGCCODEF2 - Underwood, Linda should be the only one selected as that is the case in view
MUGCCODEF2 - Underwood, James should not be highlighted in display; highlight should display when user selects case number for this defendant

## 44
QA CYCLE 2
QA CYCLE 1

## 46
|  | INFORMAL 100569 | person_nbr | FORMAL 100568 | person_nbr
ACTIVE | 15828 | 26NF0928 | 8928307 | 26HF0153 | 2305479
REACTIVATED | 15829 | 19NM06987 | 98015544 | 26NF2759 | 9468774
REVOKED | 15830 | 25WM06366 | 3102042 | 22CF3258 | 98015263
TERMINATED | 15831 | 26NM03209 | 98014189 | 24WF2785 | 97874326
COMPLETED | 110639 | 13NM04838 | 9010579 | 09WF1438 | 8091552
VACATED | 110736 | 14WM00617 | 9144583 | 25HF1151 | 7621305
ACTIVE | 111189 | MUCLF01 | 97884355 | CC26NF2231 | 9688626
EXPIRED | 118726 | 24NF0327 | 2309714 | 23HF0447 | 5682955

## Dropdowns
NG |  | PB
CT1 | CJC Remote Court Trial 1 | CR1 | CJC Remote Courtroom 1
CR1 | CJC Remote Courtroom 1 | CT1 | CJC Remote Court Trial 1
CCOL | Collections - Central | CCOL | Collections - Central
HLHCOL | Collections - Laguna Hills | HLHCOL | Collections - Laguna Hills
HNBCOL | Collections - Newport Beach | HNBCOL | Collections - Newport Beach
NCOL | Collections - North | NCOL | Collections - North
WCOL | Collections - West | WCOL | Collections - West
CCB1 | Community Court Building 1 | CCB1 | Community Court Building 1
C1 | Department C1 | C1 | Department C1
C2 | Department C2 | C2 | Department C2
C3 | Department C3 | C3 | Department C3
C4 | Department C4 | C4 | Department C4
C5 | Department C5 | C5 | Department C5
C6 | Department C6 | C6 | Department C6
C7 | Department C7 | C7 | Department C7
C8 | Department C8 | C8 | Department C8
C9 | Department C9 | C9 | Department C9
C10 | Department C10 | C10 | Department C10
C11 | Department C11 | C11 | Department C11
C12 | Department C12 | C12 | Department C12
C13 | Department C13 | C13 | Department C13
C14 | Department C14 | C14 | Department C14
C15 | Department C15 | C15 | Department C15
C16 | Department C16 | C16 | Department C16
C17 | Department C17 | C17 | Department C17
C18 | Department C18 | C18 | Department C18
C19 | Department C19 | C19 | Department C19
C20 | Department C20 | C20 | Department C20
C21 | Department C21 | C21 | Department C21
C22 | Department C22 | C22 | Department C22
C23 | Department C23 | C23 | Department C23
C24 | Department C24 | C24 | Department C24
C25 | Department C25 | C25 | Department C25
C26 | Department C26 | C26 | Department C26
C27 | Department C27 | C27 | Department C27
C28 | Department C28 | C28 | Department C28
C29 | Department C29 | C29 | Department C29
C30 | Department C30 | C30 | Department C30
C31 | Department C31 | C31 | Department C31
C32 | Department C32 | C32 | Department C32
C33 | Department C33 | C33 | Department C33
C34 | Department C34 | C34 | Department C34
C35 | Department C35 | C35 | Department C35
C36 | Department C36 | C36 | Department C36
C37 | Department C37 | C37 | Department C37
C38 | Department C38 | C38 | Department C38
C39 | Department C39 | C39 | Department C39
C40 | Department C40 | C40 | Department C40
C41 | Department C41 | C41 | Department C41
C42 | Department C42 | C42 | Department C42
C43 | Department C43 | C43 | Department C43
C44 | Department C44 | C44 | Department C44
C45 | Department C45 | C45 | Department C45
C46 | Department C46 | C46 | Department C46
C47 | Department C47 | C47 | Department C47
C48 | Department C48 | C48 | Department C48
C49 | Department C49 | C49 | Department C49
C50 | Department C50 | C50 | Department C50
C51 | Department C51 | C51 | Department C51
C52 | Department C52 | C52 | Department C52
C53 | Department C53 | C53 | Department C53
C54 | Department C54 | C54 | Department C54
C55 | Department C55 | C55 | Department C55
C56 | Department C56 | C56 | Department C56
C57 | Department C57 | C57 | Department C57
C58 | Department C58 | C58 | Department C58
C59 | Department C59 | C59 | Department C59
C60 | Department C60 | C60 | Department C60
C61 | Department C61 | C61 | Department C61
C62 | Department C62 | C62 | Department C62
C63 | Department C63 | C63 | Department C63
C64 | Department C64 | C64 | Department C64
C65 | Department C65 | C65 | Department C65
C66 | Department C66 | C66 | Department C66
C67 | Department C67 | C67 | Department C67
C68 | Department C68 | C68 | Department C68
CJ1 | Department CJ1 | CJ1 | Department CJ1
CJ2 | Department CJ2 | CJ2 | Department CJ2
CX102 | Department CX102 | Z | Department - Conversion
CX103 | Department CX103 | CX102 | Department CX102
CX104 | Department CX104 | CX103 | Department CX103
CX105 | Department CX105 | CX104 | Department CX104
Z | Department - Conversion | CX105 | Department CX105
H1 | Department H1 | H1 | Department H1
H2 | Department H2 | H2 | Department H2
H3 | Department H3 | H3 | Department H3
H4 | Department H4 | H4 | Department H4
H5 | Department H5 | H5 | Department H5
H6 | Department H6 | H6 | Department H6
H7 | Department H7 | H7 | Department H7
H8 | Department H8 | H8 | Department H8
H9 | Department H9 | H9 | Department H9
H10 | Department H10 | H10 | Department H10
H11 | Department H11 | H11 | Department H11
H12 | Department H12 | H12 | Department H12
H13 | Department H13 | H13 | Department H13
H14 | Department H14 | H14 | Department H14
L11 | Department L11 | L11 | Department L11
L21 | Department L21 | L21 | Department L21
L22 | Department L22 | L22 | Department L22
L23 | Department L23 | L23 | Department L23
L31 | Department L31 | L31 | Department L31
L32 | Department L32 | L32 | Department L32
L33 | Department L33 | L33 | Department L33
L34 | Department L34 | L34 | Department L34
L41 | Department L41 | L41 | Department L41
L42 | Department L42 | L42 | Department L42
L43 | Department L43 | L43 | Department L43
L44 | Department L44 | L44 | Department L44
L51 | Department L51 | L51 | Department L51
L52 | Department L52 | L52 | Department L52
L53 | Department L53 | L53 | Department L53
L60 | Department L60 | L60 | Department L60
L61 | Department L61 | L61 | Department L61
L62 | Department L62 | L62 | Department L62
L63 | Department L63 | L63 | Department L63
L64 | Department L64 | L64 | Department L64
L65 | Department L65 | L65 | Department L65
L66 | Department L66 | L66 | Department L66
L67 | Department L67 | L67 | Department L67
L68 | Department L68 | L68 | Department L68
L69 | Department L69 | L69 | Department L69
L71 | Department L71 | L71 | Department L71
L72 | Department L72 | L72 | Department L72
L73 | Department L73 | L73 | Department L73
N1 | Department N1 | N1 | Department N1
N2 | Department N2 | N2 | Department N2
N3 | Department N3 | N3 | Department N3
N4 | Department N4 | N4 | Department N4
N5 | Department N5 | N5 | Department N5
N6 | Department N6 | N6 | Department N6
N7 | Department N7 | N7 | Department N7
N8 | Department N8 | N8 | Department N8
N9 | Department N9 | N9 | Department N9
N10 | Department N10 | N10 | Department N10
N11 | Department N11 | N11 | Department N11
N12 | Department N12 | N12 | Department N12
N13 | Department N13 | N13 | Department N13
N14 | Department N14 | N14 | Department N14
N15 | Department N15 | N15 | Department N15
N16 | Department N16 | N16 | Department N16
N17 | Department N17 | N17 | Department N17
N18 | Department N18 | N18 | Department N18
S1 | Department S1 | S1 | Department S1
S2 | Department S2 | S2 | Department S2
S3 | Department S3 | S3 | Department S3
S4 | Department S4 | S4 | Department S4
S5 | Department S5 | S5 | Department S5
S6 | Department S6 | S6 | Department S6
S7 | Department S7 | S7 | Department S7
S8 | Department S8 | S8 | Department S8
S9 | Department S9 | S9 | Department S9
W1 | Department W1 | W1 | Department W1
W2 | Department W2 | W2 | Department W2
W3 | Department W3 | W3 | Department W3
W4 | Department W4 | W4 | Department W4
W5 | Department W5 | W5 | Department W5
W6 | Department W6 | W6 | Department W6
W7 | Department W7 | W7 | Department W7
W8 | Department W8 | W8 | Department W8
W9 | Department W9 | W9 | Department W9
W10 | Department W10 | W10 | Department W10
W11 | Department W11 | W11 | Department W11
W12 | Department W12 | W12 | Department W12
W13 | Department W13 | W13 | Department W13
W14 | Department W14 | W14 | Department W14
W15 | Department W15 | W15 | Department W15
W16 | Department W16 | W16 | Department W16
W17 | Department W17 | W17 | Department W17
W18 | Department W18 | W18 | Department W18
W20 | Department W20 | W20 | Department W20
W21 | Department W21 | W21 | Department W21
SDVJA | Domestic Violence Judicial Assistant - South | SDVJA | Domestic Violence Judicial Assistant - South
NDTY | Duty Judge - North | NDTY | Duty Judge - North
HR1 | HJC Remote Courtroom 1 | HR1 | HJC Remote Courtroom 1
SJA | Jusicial Assistant - South | SJA | Jusicial Assistant - South
JHO | Judiical Hearing Officer | JHO | Judiical Hearing Officer
NR1 | NJC Remote Courtroom 1 | NR1 | NJC Remote Courtroom 1
OCSC | Orange County Superior Court | OCSC | Orange County Superior Court
OOC | Other - Out of County | OOC | Other - Out of County
Z1 | Test Department Z1 | Z1 | Test Department Z1
VC5 | Virtual Department C5 staging | VC5 | Virtual Department C5 staging
VC57 | Virtual Department C57 staging | VC57 | Virtual Department C57 staging
WR1 | WJC Remote Courtoom 1 | WR1 | WJC Remote Courtoom 1

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action