## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Test Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-03-03 | Both | UI | Minor | Resolved | General | Non-editable windows | Rows shall have alternating light blue / white rows as data is not editable; current view is gradient rows which should be used on editable rows | UI Guidelines #30 | 2026-04-22 | Pass |  | 3/26 SM - rows alternate in color
2 | 2026-03-03 | Both | Functionality | Minor | Resolved | Dt Processed | Duplicate Dates in Filter | Filter shows multiple rows for "02/03/2026"; should show one option and when applied, all applicable row(s) display | Other columns (e.g., Reason, User Name) do not have this behavior, believe date might be tied to a timestamp that is showing multiple rows | 2026-04-22 | Pass |  | 3/18 SM - has been addressed.
3 | 2026-03-03 | Both | Functionality | Minor | Resolved | General | F3 Refresh | Can Refresh also reset column widths to default display? | Apply same fix that was done for Court Control (ID #4) | 2026-04-22 | Pass |  | 3/17 SM - has been addressed. retrofitted old code to use new solution that contains this fix
4 | 2026-03-03 | Both | Functionality | Major | Resolved | General | F3 Refresh | When user selects check box, window loses focus and F3 keypress fails | User has to click on window or highlight row for F3 keypress to work | 2026-04-22 | Pass |  | 3/26 SM - has been addressed
5 | 2026-03-03 | Both | Functionality | Major | Resolved | General | F3 Refresh | When user is at the bottom of the window and executes refresh, scroll bar placement remains the same | Filters appear to reset when the refresh occurs, shouldn't the focus as well? | 2026-04-22 | Pass
6 | 2026-03-03 | Both | UI | Minor | Resolved | General | Loading Wheel during Confirm Delete Message | When "Confirm Delete" message appears, Purge Duplicate Cases Loading… wheel appears and spins indefinitely | Only gray background should display - no loading wheel; should be treated the same as Pending Changes message | 2026-04-22 | Pass |  | 3/17 SM - has been addressed.
7 | 2026-03-03 | Both | UI | Minor | Resolved | General | Confirm Delete - order of cases in message | NG window displays case numbers/defendants(missing complaints) in what appears to be a predetermined order; PB window displays based on sorted order | Adding for discussion since all cases appear in message and want info on display order in current NG message | 2026-04-22 | Pass with Comments | 04/22 - confirmed to leave as is but may need to revisit in future windows | 3/26 SM - leaving as is per meeting
8 | 2026-03-03 | Both | UI | Minor | Resolved | General | Vision logo added to refresh/loading wheel | Please remove as image blocks data when saving | UI Guidelines #5, #80 | 2026-04-22 | Pass |  | 3/26 SM - has been addressed
9 | 2026-03-03 | Web Only | UI | Minor | Resolved | General | Pending Changes | Scroll bar is added to right when Pending Changes message appears | Is there a reason for it? If not can it be removed. | 2026-04-22 | Pass | 04/22 - refresh removed as select box is not counted as editied field | 3/18 SM - has been addressed. Overrroad CSS, this change is applicable for every window that has pending changes
10 | 2026-03-03 | Both | UI | Minor | Resolved | General | Checkbox sizes | Match sizes of checkboxes to Bail Schedule for Sel and Multi-Defts columns | Current display appears to be larger than Bail Schedule | 2026-04-22 | Pass |  | 3/17 SM - has been addressed. Added e-small on both checkboxes.
11 | 2026-03-03 | Both | Functionality | Minor | Resolved | General | Check/Uncheck Sel box triggers Pending Changes message | No pending changes as checkbox was unselected before refresh, should this message appear? | Not sure if check and uncheck boxes count as "editing" row so adding for discussion | 2026-04-22 | Pass | 04/22 - refresh removed as select box is not counted as editied field | 3/26 SM - has been addressed. Removed pending changes. Now user can click/unclick and no pending changes msg appears
12 | 2026-03-03 | Both | UI | Minor | Resolved | General | Missing Window name from loading display | Missing "Purge Duplicate Cases" in front of Loading text when window is opened |  | 2026-04-22 | Pass |  | 3/17 SM - has been addressed.
13 | 2026-03-03 | Web Only | Functionality | Major | Resolved | General | Does not deny access when W_PRGIMM is not included | Does not prevent user from accessing Purge Duplicate Cases window in blazor when the user does not have W_PRGIMM code |  | 2026-04-22 | Pass with Comments | 04/22 - see ID 16 | 4/1 SM - has been addressed
14 | 2026-04-22 | Web Only | Functionality | Major | No Action | General | Deny access when W_PRGIMM is not included | Access Denied message appears however, user is unable to continue to navigate elsewhere in web app Using back arrow on web browser triggers the same message |  | 2026-04-22 | Pass | 04/22 - need to address later
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## SUMMARY
|  | Count of Status | Column Labels
QA # | HH:MM | Row Labels | Resolved | No Action | Grand Total | Row Labels | Count of Scenario Type | Row Labels | Count of Bug Type
1 | 10:00 | 2026-03-03 | 13 |  | 13 | No Action | 1 | Major | 4
|  | Functionality | 6 |  | 6 | Resolved | 13 | Minor | 10
|  | Major | 3 |  | 3 | (blank) |  | Grand Total | 14
|  | Minor | 3 |  | 3 | Grand Total | 14
|  | UI | 7 |  | 7
|  | Minor | 7 |  | 7
2 | 2:00 | 2026-04-22 |  | 1 | 1
|  | Functionality |  | 1 | 1
|  | Major |  | 1 | 1
|  | Grand Total | 13 | 1 | 14

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action