## DEFECTS
ID | Date Tested | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-05-20 | Both | UI | Minor | Resolved | N/A | Tab label does not match PB | NG Tab label and Window title say 'Unlock Case', while PB says 'Case Lock Maintenance' |  | 2026-05-28 | Pass |  | 5/22: Adjusted string passed to OnWindowInitialize.
2 | 2026-05-20 | Both | UI | Minor | Resolved | Lock Date | Date Time Format missing seconds | Date Time format in Lock Date column is missing seconds. | Added UI Guidelines 107 and 108 for this | 2026-05-28 | Pass |  | 5/22: Added seconds to grid column.
3 | 2026-05-21 | Both | UI | Major | Resolved | All Columns | Filters remain after save | 1. Apply Column Filter 2. Delete a row 3. Save changes - Column Filter remains | Needs discussion with Devs before this item is worked on - this happens on all NG windows | 2026-05-28 | Pass |  | 5/22: Remove filter on save.
4 | 2026-05-21 | Both | Functionality | Major | Resolved | N/A | Restore Button | Restore button should be removed | UI Guideline 99 | 2026-05-28 | Pass |  | 5/22: Removed restore.
5 | 2026-05-21 | Both | Functionality | Major | Resolved | N/A | Window Access | PROFIL configurations in CRMD and CRMQ are missing |  | 2026-05-28 | Pass |  | 5/22: Added to code entry PROFIL.
6 | 2026-05-21 | Both | UI | Minor | Resolved | N/A | Left margin | Window left margin is wider than the top margin. Left margin should match top margin | Added UI Guideline 110 for this. Needs dev input for the pixels | 2026-05-28 | Pass |  | 5/22: Fixed padding.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47

## Summary
QA Cycle 1: 3:00
Count of Status | Column Labels
Row Labels | New | Grand Total
Functionality
Major | 2 | 2
UI
Major | 1 | 1
Minor | 3 | 3
Grand Total | 6 | 6
QA Cycle 2: 1:00
Count of Status | Column Labels
Row Labels | Resolved | Grand Total
Functionality
Major | 2 | 2
UI
Major | 1 | 1
Minor | 3 | 3
Grand Total | 6 | 6

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action