## DEFECTS
ID | Date Reported | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-06-17 | Both | UI | Minor | Resolved | Violation tab | "Spec Alleg" Column | Remove period from column header |  | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: Removed period.
2 | 2026-06-17 | Both | UI | Minor | Resolved | Violation tab | Column width adjustments | Increase column width to show more of Description. To accommodate increase, Off Leve, Spec Alleg, and Degree Level columns can be slightly decreased If possible, match updated column widths on Agency tab as well |  | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: Set made Description column wider, shrunk other columns in both grids while tryning not to cutoff their headers.
3 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref Section | Column filters cut off, issue previously reported in other windows where bottom of window has filters (e.g., Code Entries, Event Codes); buttons can be seen but bottom border is cut off |  | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: Can this be excused? Might need a global styling. 6/30: Putting my own border at the bottom to simulate it.
4 | 2026-06-17 | Both | Functionality | Major | Resolved | General | F3 Refresh prevents user from entering search criteria | 1. Open window and execute search 2. Use F3 Refresh 3. Select Statute arrow dropdown - nothing loads (same issue occurs for Off Level field) | Note: Section Code field is disabled, but user can enter text into Descrip field. | 2026-07-13 | Pass | 07/08: resolved, cannot replicate 07/13: regression test and pass | 6/18: Unable to replicate
5 | 2026-06-17 | Both | Functionality | Major | Resolved | General | F3 Refresh prevents user from using Clear button | 1. Open window and execute search 2. Use F3 Refresh 3. Enter Descrip 4. Select Clear button - field entry remains |  | 2026-07-13 | Pass | 07/08: resolved, cannot replicate 07/13: regression test and pass | 6/18: Unable to replicate
6 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref Delete | 1. Add new row to Violation Agency X-Ref section 2. Save 3. Delete row and save In NG, user is able to delete. In PB, user receives "Delete Record; You can only delete newly added records" | Adding as it is unclear what the intended functionality is | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: Added message popup preventing deleting items that already existed. Can only delete items that were just added. 7/1: Switch to fluent validation, copied message from Court Control.
7 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref "Agency" Dropdown | When user types "dep" in search field in dropdown, the results display all statutes containing "dep" rather than starting with "dep" Expected behavior is that results should start with "dep" if entered | Same issue reported in Violations ID 1 | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: VisionDropdownList component default updated to StartsWith.
8 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref FluentValidations Stat Code Section Type | Red highlight around cell is missing when validation fails |  | 2026-07-13 | Pass | 07/08: appears when you click back into cell to edit; leaving for now 07/13: regression test and pass | 6/18: Red highlight shows up for me when trying to commit the entry with my mouse. It does not with just tabbing, this is controlled by SyncFusion so I think this is okay. 7/1: Okay for now, only if brought up by UAT will we address, if we do might need changes to FluentValidation base.
9 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref FluentValidations Stat Code Section | 1. Add row to Violation Agency X-Ref section 2. Tab to Stat Code section 3. Use ENTER keypress to exit edit mode 4. FluentValidation is triggered 5. Enter value in Stat Code section and tab to move to next field FluentValidation remains even though it passes and green highlight is missing from cell | This also occurs in Section column | 2026-07-13 | Pass | 07/08: red cell remains until user enters data in Section then tabs. 07/13: retest and pass | 6/18: Switched binding. There's bind-Value, Value, ValueExpression, ValueChanged. Need to look into these more. 7/8: AI modified the vision dropdown to notify the fluent validation on value select, seems to work across all grids that use vision dropdown list.
10 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Violation Agency X-Ref FluentValidations Type Ident | In PB version, user cannot save NULL but can save a space in these fields as they are required to save In NG, user cannot save NULL nor can save a space in fields therefore no new rows can be added in this section unless user enters alphanumeric values | Adding as it is unclear what the intended functionality is In prod, the viol_agency_xref table appears to store spaces that the user enters in PB version | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: Safe to add empty spaces into required field? Let's discuss. 6/30: Allow spaces.
11 | 2026-06-17 | Both | Functionality | Major | Resolved | General | F3 Refresh | 1. Select Statute: Training Code then Retrieve button 2. Scroll down to violation TEST010 and select/highlight row 3. F3 Refresh "No records to display" appears at the bottom of Violation section and scroll bar remains in bottom position |  | 2026-07-13 | Pass | 07/13: regression test and pass | 6/18: That looks like a SyncFusion issue, especially since it comes from refresh. They are still working on another ticket regarding ResetPersistDataAsync which we use for the refresh. 7/1: Removed a StateHasChanged from my cancel method and so far is working...
12 | 2026-06-17 | Both | Functionality | Major | Resolved | Violation tab | Increase height of Violation section so one more row is visible | Update to view one additional row so that it matches number of rows displayed in PB window |  | 2026-07-08 | Pass | 07/13: regression test and pass | 6/18: Added.
13 | 2026-06-17 | Both | Functionality | Major | Resolved | Agency tab | Review order of data retrieval | When Agency: Department of Motor Vehicles is only used for search criteria, the data returned is in a different order in NG window comparted to PB window | Can this be reviewed to see if there is additional result order on PB that is missing in NG window | 2026-07-08 | Pass | 07/13: regression test and pass | 6/18: Sort by agency like original, I notice when I select all I cannot tell how it decides to sort entries, I think this difference is okay though since I'm guessing most people aren't using search all for anything meaningful anyways. 7/1: Approved.
14 | 2026-06-17 | Both | Functionality | Major | Resolved | General | No Search Criteria messages | If no search criteria is entered on each tab, window should display Yes/No buttons Current NG displays Yes/Cancel | For No button, use same coloring as "No" button in Pending Changes message | 2026-07-08 | Pass | 07/13: regression test and pass | 6/18: Switched to YesNo button type.
15 | 2026-07-08 | Both | Functionality | Major | No Action | General | Delete Violation with Violation Agency Xref config | New functionality added to prevent deleting violations when a child record or bail schedule row exists. Should this be added if Violation Agency Xref exists for violation? | Checking to see if this is needed; current PB windows allows for deletion if Violation Agency Xref exists |  | Pass |  | 7/8: Jorge says Bail Schedule is special and needed more care, says this part is okay.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## SUMMARY
|  | Count of Status | Column Labels
|  | Row Labels | Resolved | No Action | Grand Total | Row Labels | Count of Bug Type | Row Labels | Count of Status
1 | 12:00 | 2026-06-17 | 14 |  | 14 | Major | 13 | Resolved | 14
|  | Functionality | 12 |  | 12 | Minor | 2 | No Action | 1
|  | UI | 2 |  | 2 | Grand Total | 15 | Grand Total | 15
2 | 4:00 | 2026-07-08 |  | 1 | 1
|  | Functionality |  | 1 | 1
3 | 1:00 | Grand Total | 14 | 1 | 15

## Table Structure
AGENCY | VARCHAR2(12 BYTE)
VIOL_ID_NBR | NUMBER(38,0)
WOBBLER | NUMBER(1,0)
STAT_CODE | VARCHAR2(4 BYTE)
SECTION | VARCHAR2(20 BYTE)
TYPE | VARCHAR2(12 BYTE)
IDENT | VARCHAR2(12 BYTE)
DT_INVALID | DATE
DT_EFFECTIVE | DATE
USER_ID | NUMBER(38,0)
DT_UPDATED | DATE
DESCRIP | VARCHAR2(255 BYTE)

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action