## DEFECTS
ID | Date Reported | Interface | Scenario Type | Bug Type | Status | Window Column(s) | Summary | Defect (NG Display, Scenario) | Testing Comments | Date Retest | Retest Pass/Fail | BSA Comments | Dev Comments
1 | 2026-06-04 | Both | Functionality | Major | Resolved | Statute | Dropdown behavior | When user types "t" in search field in dropdown, the results display all statutes containing "t" rather than starting with "t" Expected behavior is that results should start with "t" if entered | See Event Codes for reference regarding expected behavior Note: Violation Detail tab - Violation Detail "Statute" dropdown behaves as expected | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Switch to explicit VisionFilterType.StartsWith
2 | 2026-06-04 | Both | Functionality | Major | Resolved | Search Criteria | Dropdown behavior | When window is opened for the first time, the first row is higlighted in gray If user executes search too quickly (types then uses ENTER keypress), the gray highlighted row gets selected rather than searching for what was typed | Issue might be resolved once ID #1 is addressed; workaround is that user must briefly pause for filter to update then use ENTER keypress | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: I'll change the debounce delay to 0s.
3 | 2026-06-04 | Both | Functionality | Major | Resolved | Search Criteria | ENTER Keypress to execute search | 1. User enters Statute then Section 2. ENTER keypress is used | NG window does not execute search at Step 2 (PB window executes search) - is there a way to configure the ENTER keypress to execute search when used? | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Add "Enter" key handling on section field, cannot add everywhere because it will interfere with SyncFusion default (dropdowns mainly).
4 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Summary | Rows should be in alternating blue/white | User cannot enter edit mode on rows on this tab as edits occur in Violation Detail | UI Guidelines ID #13 | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/12: Changed to alt row
5 | 2026-06-04 | PB Only | Functionality | Major | Resolved | Violation Summary | PgUp/PgDn keys fail to highlight top row | 1. Select "Penal Code" from Statue and click Retrieve - first violation is highlighted as expected 2. Click Violation Detail - violation detail belongs to highlighted row as expected 3. Use PgDn keypress to view next violation 4. Click Violation Detail - violation detail belongs to violation from Step 1 5. Return to Violation Summary and use PgDn keypress a second time 6. Highlight reappears instead of moving to next page; if user selects Violation Detail tab, tab is updated to highlighted row data as expected | Highlight is failing in PB but works fine in web app; same behavior occurs for PgUp keypress | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/10: Unable to replicate. One thing to note, we prevent spamming of nav keys across windows in our base, if you hit the keys too quickly you may not jump as many entries as you think.
6 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Click & Drag of Column Headers Flips view to Violation Detail tab | 1. Hovers over filter icon on either Description, Off Level, Deg, Effective, or Invalid columns 2. Hand cursor appears 3. Click then quickly move cursor up so that the placement is outside of field 4. View flips to Violation detail | Identified while testing column width resizing; view should remain on Violation Summary Not able to replicate in Violation Detail tab - not sure if this is because the column headers are not at the top of the tab? | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Disabled swipe mode.
7 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Click & Drag to Highlight Row Data Flips view to Violation Detail tab | 1. Highlight row 2. Highlight "Off Level" text (e.g., Misdemeanor) of same row 3. View flips to violation detail | Similar issue to ID 6; view should remain on Violation Summary | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Disabled swipe mode.
8 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Click & Drag to Highlight Row Data Flips view to Violation Detail tab | 1. Highlight row 2. Highlight "Off Level" text (e.g., Misdemeanor) of non-highligted row 3. View flips to violation detail of violation in Step 1 | Similar issue to ID 6/7; view should remain on Violation summary | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Disabled swipe mode.
9 | 2026-06-04 | Both | UI | Minor | No Action | General | Column Header/Data Misalignment | 1. Search "Penal Code" and go to Violation Detail 2. In Violation Detail, change to "Training Code" - Retrieve 3. Return to Violation Summary | After step 3, column data appears shifted slightly to the left of column headers - appears to be issue with scroll bar spacing in header | 2026-07-06 | Pass with Comments | 07/06: leave as-is per dev; less noticable now that the rows are read-only but issue still occurs | 6/15: This is a SyncFusion issue. We've seen this on other windows. For now can this be noted as a minor deffect?
10 | 2026-06-04 | Both | UI | Minor | Resolved | General | Add New Row Formatting | After adding new row, row looks like it is in "edit" mode but user cannot modify these fields - is there a way to format the default to not be in edit mode? | If user goes to Violation Detail then back to Violation Summary without entering data, the row displays as expected | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/12: I will make rows add and skip edit mode.
11 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | Add New Row Does not retain view newly added violation information | 1. Select Statute Training Code and Section: NGTEST - Violation Summary filters to expected rows 2. Add new row, update all required fields 3. Save 4. After saving, the Section field in search criteria clears and updates to display first row of Training Code violations 5. Returning to Violation Summary tab shows all Training Code rows as Section filter was removed during save of violation | After saving, window should retain view of newly added violation Search critera should not be cleared | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: No longer reloading data from database on save, use updated concurrency check instead.
12 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | Edit Row Does not retain view of newly added violation information | 1. Select Statute Training Code and Section: NGTEST - Violation Summary filters to expected rows 2. Highlight violation and navigate to Violation Detail 3. Update violation data and save 4. After saving, the Section field in search criteria clears and updates to display first row of Training Code violations 5. Returning to Violation Summary tab shows all Training Code rows as Section filter was removed during save of violation | Related to ID # 11 | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: No longer reloading data from database on save, use updated concurrency check instead.
13 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Delete Row clears Section in Search Criteria | 1. Enter search critera for Statute and Section 2. Select row to delete 3. Save User has to scroll through Statute rows to confirm row was deleted | After saving, window should retain view of filtered data Search critera should not be cleared | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: No longer reloading data from database on save, use updated concurrency check instead.
14 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | Window does not have Min/Max Dates implemented | For all Effective and Invalid dates in the tab, user is able to enter values before 01/01/1900 and after 12/31/2099 successfully. Current PB window does not have restrictions so not sure if this was intentional or inadvertent when initially created. | Should this be restricted to match other NG windows? | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test failed, see ID 32 07/17: retest and pass; strict mode removed from date picker | 6/8: Added min and max values for date fields to match other windows.
15 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | Effective Date Input Error Message | 1. Highlight violation and move to Violation Detail tab 2. Enter date in field that occurs prior to existing date in field 3. Successful save, no Input Error Message In NG, the Input Error is missing. PB window displays the following error: Input Error: New Effective Date must be greater than Old effective Date . Old Effective Date = 01/01/1700 00:00:00 New Effective date = 1/1/1300 00:00:00 OK | Unclear of what behavior should be as PB displays that message but updates the Effective Date… | 2026-07-17 | Pass | 07/06: message now reads "New Effective Date must be greater than old Effective Date" 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: Added fluent validation to enforce, check with Melanie for verbage.
16 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Delete Row Triggers Pending Changes Message | 1. Delete Row 2. Pending Changes message appears | Should message appear? Current PB window allows user to delete row and navigate to other violations | 2026-07-17 | Pass | 07/06: issue resolved as Confirm Delete message now appears 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: It should appear, windows with pending changes checking will behave the same. I will however allow you to delete the parent without deleting the children like the parent.
17 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Summary | Context Menu remains visible when Pending Message appears | 1. Delete last row 2. Pending Changes message appears 3. In background, context menu is still visible | If user clicks in grayed out window, menu disappears; expected result is that context menu shouldn't display as it doesn't appear for other rows (top/middle) if deleted | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/10: Overhauling how we handle deletes on windows with pending changes handling, we will prompt the user to confirm before the delete occurs.
18 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Pending Message "Cancel" flips view to Violation Detail | 1. Delete Row 2. Pending Changes message appears; select Cancel 3. Text temporarily bolds on Violation Summary tab then flips to Violation Detail | View should remain on Violation Summary | 2026-07-17 | Pass | 07/06: issue resolved as Confirm Delete message now appears; if user has pending change, Cancel will redirect user to Violation Detail of row where pending change exists 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: Only switches tabs if "Cancel" selected and NOT a delete.
19 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Cannot save after Pending Message appears | 1. Delete Row 2. Pending Changes message appears; select No 3. User does not see deleted row as expected 4. Save button disabled, Ctrl + S triggers No Changes toast message |  | 2026-07-17 | Pass | 07/06: issue resolved as Confirm Delete message now appears 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: On delete, we will ask if they want to save with the options to save it (Yes), or revert it (Cancel). This is the same as Parm Lookups.
20 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Cannot save after Pending Message appears | 1. Delete Row 2. Pending Changes message appears; select No 3. User does not see deleted row as expected 4. Save button disabled, Ctrl + S triggers No Changes toast message 5. Navigate to new row and update Description 6. Save button disabled, Ctrl + S triggers No Changes toast message | Similar to ID 19 with attempt to add an additional modification to enable save button | 2026-07-17 | Pass | 07/06: issue resolved as Confirm Delete message now appears 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: On delete, we will ask if they want to save with the options to save it (Yes), or revert it (Cancel). This is the same as Parm Lookups.
21 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Summary | Delete row context menu intermittently fails | 1. Select row to delete 2. Right click to trigger context menu or Shift + F7 3. Pending Changes message appears; select Yes 4. No Changes message appears | Deleted violation is not associated to any case; existing window allows for delete In app, I can use Edit > Delete Row to delete but keyboard shortcut and context menu are failing | 2026-07-17 | Pass | 07/06: issue resolved as Confirm Delete message now appears 07/13: regression test and pass 07/16: regression test and pass | 6/8: This may have been related to the .NET 10 update since we saw something similar with Bail Schedule. Added value changed event so change is actually marked by pending changes.
22 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | Editing Field does not save | 1. Select row and update Section 2. Save disabled unable to update, Ctrl + S does not work | Existing PB window allows for update to save | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Added value changed event so change is actually marked by pending changes
23 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Detail | Updated Date field flickers to different format while saving | Issue was present and fixed in Bail Schedule; please refer to this window for reference/fix | Appears to be related to date picker fields; NV to update to use text field for Updated Date (see Bail Schedule Updated section for reference) | 2026-07-17 | Pass | 07/06: issue still occurring; see screenshots of different views during save; font and alignment change, then date format changes before displaying correct font/display 07/13: See ID 31; Updated date fixed but 2 others broke 07/16: retest this and ID 31, pass 07/17: regression test and pass | 6/5: Using Vision Components now. 7/8: Using VisionTextBox now, I don't see the flickering.
24 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail | First Save triggers No Changes message | 1. Select row and update Invalid Date 2. Ctrl + S = No Changes message 3. Ctrl + S = saved | Appears to be related to ID 22; expected behavior is for save to work on first attempt/PB save icon enabled for save | 2026-07-17 | Pass | 07/06: issue still occurring 07/13: pass 07/16: regression test and pass 07/17: regression test and pass | 6/8: This may have been related to the .NET 10 update since we saw something similar with Bail Schedule. Added value changed event so change is actually marked by pending changes. 7/8: Fixed, on grid commit I will handle blurring so the date fields work, this issue was also on the effective date.
25 | 2026-06-04 | Both | Functionality | Major | Resolved | Violation Detail - Violation Sentence Terms | Tab Keypress Failing in section | 1. Right click, Add Row 2. Cursor starts in Min. Field, user enters data then TAB keypress to move to Term/Unit field 3. User fills out Term/Unit field then TAB keypress to move to Mid. Field 4. User fills out Mid. Field than TAB keypress fails to move to next Term.Unit filed. 5. TAB keypress entered again moves the cursor to Max. field; same issue occcurs here when trying to move from Max. field to Term/Unit | TAB keypress should move to next cell to right. | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Unable to replicate
26 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Detail - Violation Qualifiers | Update FluentValidation message | Fix capitalization in FV to: Cannot enter duplicate Qualifier and Effective Date combination |  | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Fixed
27 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Detail | Update FluentValidation message for Effective Date fields | Fix capitalization in FV to: Effective Date is required |  | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Fixed
28 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Detail | Update FluentValidation message for Invalid Date fields | Fix capitalization in FV to: Invalid Date must be greater than or equal to Effective Date |  | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Fixed
29 | 2026-06-04 | Both | UI | Minor | Resolved | Violation Detail | Update FluentValidation messages | Section: Section is required Off Level: Off Level is required Degree: Degree is required Charge: Charge Type is required |  | 2026-07-17 | Pass | 07/13: regression test and pass 07/16: regression test and pass 07/17: regression test and pass | 6/5: Fixed
30 | 2026-07-06 | Both | Functionality | Major | Resolved | Violation Summary | Do not use FluentValidation for message | "Entry has associated Bail Schedule, unable to delete." "Entry has associations, unable to delete." Change these to be a message instead of using FluentValidation to capture error | Originally thought to handle as FV but visually the cell looks like it's in edit mode so don't think this is appropriate for scenario. Needs to be handled as message. | 2026-07-17 | Pass | 07/16: regression test and pass 07/17: regression test and pass | 7/8: Switched to messagebox. Added flag to DataGrid base to stop save too since we aren't using fluent validation here.
31 | 2026-07-13 | Both | UI | Regression | Resolved | Violation Detail | Effective & Invalid Date fields flickers to different format while saving | When user adds Invalid date and saves, both Effective and Invalid date fields flicker to different format while saving. Per ID 23, appears to possibly be related to date picker fields | Note: when Effective Date is used by itself, no flicker occurs; seems to be related to changing the fields to read only view | 2026-07-17 | Pass | 07/17: regression test and pass
32 | 2026-07-16 | Both | Functionality | Regression | Resolved | Violation Detail | Dates entered before/after min/max dates are overridden | When user enters invalid data '01/01/1800' the field overrides date to min 01/01/1900' and passes FluentValidation Invalid data should remain and be caught by FluentValidation advising entry is invalid; overriding data may lead to inadvertent entries | Regression bug related to ID 14; previously dates remained and FV caught invalid date Per 7/16 NG UAT meet, strict mode to be removed | 2026-07-17 | Pass | 07/17: regression test and pass
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## SUMMARY
|  | Count of Scenario Type | Column Labels
QA Cycle | Hours | Row Labels | Resolved | No Action | Grand Total | Row Labels | Count of Bug Type | Row Labels | Count of Status
1 | 16:00 | 2026-06-04 | 28 | 1 | 29 | Major | 21 | Resolved | 31
|  | Functionality | 20 |  | 20 | Minor | 9 | No Action | 1
|  | UI | 8 | 1 | 9 | Regression | 2 | Grand Total | 32
2 | 4:00 | 2026-07-06 | 1 |  | 1 | Grand Total | 32
|  | Functionality | 1 |  | 1
3 | 2:00 | 2026-07-13 | 1 |  | 1
|  | UI | 1 |  | 1
4 | 1:00 | 2026-07-16 | 1 |  | 1
|  | Functionality | 1 |  | 1
5 | 1:00 | Grand Total | 31 | 1 | 32

## Dropdowns
Violation Sentence Terms | VisionNG | Violation Qualifiers | VisionNG
Day(s) |  | Mandatory Appearance
Days and hours |  | Report Violation To Department Of Justice
Dollars |  | Report Violation To Department Of Motor Vehicles
Hours |  | Warrant charges
Hours or Days
Life
Month and days
Months
Months to life
per day
per week
total
weekends
Year(s)
Years and Days
Years and months
Years to life
Years, Months, Days and Hours.

## Sheet2 (hidden)
Pass |  | Regression | Functionality
Fail | Retest In Progress | Major | UI
Pass with Comments | Return to Dev | Minor
Resolved
New
No Action