## Sheet1
VISION NG PROJECT TEAM DASHBOARD
Next Window Group (Business Driven Priority)
SG / Inernal | Priority | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | DEV LOE | QA LOE | Total LOE | Total Usage
| 4 | 9 | 3 - CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | 12 | 6.5 | 18.5 | 13643
|  | 9.1 | 3 - CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | 18 | 8 | 26 | 21740
|  | 9.2 | 3 - CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | 8 | 5 | 13 | 21221
Internal |  | 8 | 3 - CALENDARING | Calendar List | w_ct_m_cal_list | Medium | 12 | 6.5 | 18.5 | 73912
Internal |  | 8.1 | 3 - CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | 12 | 6.5 | 18.5 | 1353
| 5 | 10 | 3 - CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | 8 | 5 | 13 | 8014
Exclude |  | 11 | 3 - CALENDARING | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | Medium | 12 | 6.5 | 18.5 | 10
|  | 13 | 3 - CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | 12 | 6.5 | 18.5 | 243
|  | 14 | 3 - CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | 8 | 5 | 13 | 258
` |  | 109 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium | 12 | 6.5 | 18.5 | 38737
|  | 109.1 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low | 4 | 1.5 | 5.5 | 3 | Go
|  | 110 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium | 12 | 6.5 | 18.5 | 57610
|  | 102 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium | 12 | 6.5 | 18.5 | 126
|  | 103 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium | 12 | 6.5 | 18.5 | 460
|  | 104 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium | 12 | 6.5 | 18.5 | 140
|  | 111 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium | 12 | 6.5 | 18.5 | 0 | Go
|  | 105 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High | 8 | 5 | 13 | 6575
|  | 105.1 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low | 4 | 1.5 | 5.5 | 641
|  | 106 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High | 8 | 5 | 13 | 3406
|  | 107 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low | 4 | 1.5 | 5.5 | 5 | TBD
|  | 108 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High | 8 | 5 | 13 | 3 | TBD
Next Sprint Windows (CTS sizing of Sprint)
Sprint # | Subtask | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | Dev | BSA | DEV LEAD LOE | Previous Days to QA | Notes
SG2 | VISAR-7419 | 8 | CALENDARING | Calendar List | w_ct_m_cal_list | Medium |  |  | 9 | 12 |  | Shared Header 1
SG2 | VISAR-7420 | 8.1 | CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium |  |  | 5 | 12 | New - adding icon to report
SG2 | VISAR-7421 | 9 | CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | NV | CL | 8 | 12
SG2 | VISAR-7422 | 9.1 | CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | NV | CL | 5 | 18 | not doing the batch print functionality
SG2 | VISAR-7423 | 9.2 | CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | NV | CL | 5 | 8
SG2 |  | 9.3 | CALENDARING | Web Browser of generated files | w_ct_c_pdf_viewer | Low High | NV | CL | 5 | 8
SG2 | VISAR-7401 | 10 | CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | CN | DC | 6 | 8
Exclude | VISAR-7424 | 11 | CALENDARING | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | Medium |  |  |  | 12
Exclude | VISAR-7425 | 12 | CALENDARING | Court Closure Transfer | w_ct_m_cal_close_transfer | Low High |  |  |  | 8 |  | Shared Header 1
SG2 | VISAR-7426 | 13 | CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | CN | DC | 6 | 12 |  | Shared Header 1
SG2 | VISAR-7427 | 14 | CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | CN | DC | 8 | 8
SG3 |  | 109 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium
SG3 |  | 109.1 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low
SG3 |  | 110 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium
SG3 |  | 102 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium
SG3 |  | 103 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium
SG3 |  | 104 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium
SG3 |  | 111 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium
SG3 |  | 105 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High
SG3 |  | 105.1 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low
SG3 |  | 106 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High
TBD |  | 107 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low
TBD |  | 108 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High
In Flight / Assigned
Sprint # | Subtask | # | Menu Group | Window / Subscreen Name | Status | Grouping | Dev | BSA | Open Defects | Estimate to QA
Hold | VISAR-6907 | 33 | COLLECTIONS | FTBCOD Interface | On Hold | High | NV | CC
|  | 34 |  | FTBCOD Payment Processor |  | Medium-High |  | CC
Hold | VISAR-7417 | 159 | GENERAL | Simple Case Search | On Hold | Med High | NV
Internal | VISAR-7312 | 1 | ADMIN | Auto Process Schedule | QA 1 - In Mitigation | Low High | JC | BY
Internal | VISAR-7296 | 124 | TABLES | Agency X-Ref Maintenance | QA 2 - In test | Low High | CN | BY
Internal | VISAR-7311 | 131 | TABLES | Court Holidays | QA 1 - In Test | Low High | CN | BY
Internal | VISAR-7382 | 147 | TABLES | Unit Codes | In Development | Medium | SM | CL
Internal | VISAR-7368 | 123 | SECURITY | Agency Codes | In Development | Medium | NV | BY
SG2 | VISAR-7421 | 9 | CALENDARING | Calendar Report | In Development | Medium | NV | CL |  | 8
SG2 | VISAR-7422 | 9.1 | CALENDARING | Calendar Batch Print | In Development | Medium high | NV | CL |  | 5
SG2 | VISAR-7423 | 9.2 | CALENDARING | Web Browser of generated files | In Development | Low High | NV | CL |  | 5
SG2 | VISAR-7475 | 9.3 | CALENDARING | Web Browser of generated files | In Development | Low High | NV | CL |  | 5
SG2 | VISAR-7401 | 10 | CALENDARING | Calendar Transfer | QA 1 - In Test | Low High | CN | DC |  | 6
SG2 | VISAR-7426 | 13 | CALENDARING | Court Trial Transfer | In Development | Medium | CN | DC |  | 6
SG2 | VISAR-7427 | 14 | CALENDARING | Notice of Packaged Hearings | In Development | Low High | CN | DC |  | 8
Committed Delivery Windows (Timer On)
Sprint # | Subtask | # | Target Date to UAT | Window / Subscreen Name | Status | Grouping | Dev | BSA | Open Defects | Defect Log
SG1 Internal | VISAR-7189 | 56 | Deploy with SG1 | Exhibit Maintenance | QA 2 - In Mitigation | High | SM | DC
SG1 Internal |  | 56.1 | Deploy with SG1 | New Exhibit Hearing LIst |  | High
Patch | VISAR-7397 |  | Deploy with SG1 | Code Entries | NV - More fix |  | NV | CL
SG1 | VISAR-6315 | 53 | 2026-10-01 | Minutes | QA 3 - In Test / Parallel Mitigation | Medium High | SM | BY
Sent to UAT
Sprint # | VISAR | # | Subtask to UAT date | Window / Subscreen Name | Actual UAT Start date | Sign off Date | PDC Notes
SG1 | VISAR-7012 | 25 | 2026-09-15 | Priors | 2026-09-22
SG1 | VISAR-7012 | 25 | 2026-09-15 | Print - Copies Spec. | 2026-09-22
SG1 | VISAR-7215 | 90 | 2026-09-15 | JBSIS Maintnenance | 2026-09-18
SG1 | VISAR-7188 | 55 | 2026-09-15 | Exhibit List
|  | 55.1 | 2026-09-15 | Exhibit List Case Search
SG1 | VISAR-7206 | 57.2 | 2026-09-15 | Exhibit History
To Be Deployed (To Build Planning Process)
Sprint # | VISAR | # | Deploy Note | Window / Subscreen Name | Notes |  | Dev | BSA
SG1 Internal | VISAR-7206 | 57.1 | Deploy with SG1 | Exhibit Management Search |  |  | SM | DC
SG1 Internal | VISAR-7206 | 57.3 | Deploy with SG1 | Exhibit Disposition Notice |  |  | SM | DC
SG1 Internal | VISAR-7185 | 57 | Deploy with SG1 | Exhibit Management |  |  | SM | DC
Patch | VISAR-7428 |  | Deploy with SG1 | Bail Schedule Print Watermark |  |  | JL | CC
Internal | VISAR-7332 | 2 |  | Date of Action |  |  | CN | DC
Tracked Metrics | [8 empty] | Dates
Sprint # | Status | # | Menu Group | Window / Subscreen Name | Object Name | Grouping | Dev | BSA | Date Assigned | To 1st QA | Estimate vs Actual | 2 Week start
SG1 | In UAT | 56 | EXHIBITS | Exhibit Maintenance | w_ct_m_case_package_list | High | NV | DC | 2026-09-01 | 2026-09-03 |  | 2026-09-06
Daily Reports
Sprint # | VISAR | # | Menu Group | Window / Subscreen Name | Status | Grouping | Dev | BSA | Activity Report
SG1 | VISAR-7185 | 57 | EXHIBITS | Exhibit Management | QA 2 - In Mitigation | High | NV | DC | - 9/8/2026 09:50 AM: DC logged 4 hours - 9/8/2026 10:00 AM: Moved from QA back to Dev - 9/8/2026 01:00 PM: Moved from Unit test to QA - 9/8/2026 01:05 PM: Assigned to DC - 9/8/2026 04:39 PM: David Chang - we need to discuss defect # 11
SG1 | VISAR-7215 | 90 | JBSIS | JBSIS Maintenance | QA 1 - In Test | Mid | JL | CC | - No Activity
Internal | VISAR-7332 | 2 | ADMIN | Date of Action | In Development | Low | SM | BY | - 9/8/2026 11:00 AM: Subtask Created - 9/8/2026 11:05 AM: Subtask assigned - 9/8/2026 01:00 PM: Subtask moved to in Progress - 9/8/2026 05:00 PM: SM logged 3 hours
Sprint Map
Sprint # | Main AR | #Sub | Overall Status
SG1
SG2
SG3
SG4
| Role | Initial | Name
| BSA | DC | David Chang
| DEV | JC | JinLiang Tony Chen
| DEV | CN | Chris Nguyen
| Lead BSA | CC | Joonho Chris Chang
| Lead DEV | JL | Jorge Lichtenstein
| DEV | MC | Menekou Coulibaly
| PDC | MU | Melanie Uyehara
| DEV | SM | Santiago Morales
| DEV | KH | Kyeng Kenny Hwang
| DEV | SS | Sameer Sarangi
| DEV | NV | Nathan Vuong
| BSA | CL | Cung Le
| BSA | BY | Brooke Yale