The UAT Defect Log will be used by stakeholders and CTS to track defects/findings during UAT cycles for Vision NG windows. This document provides information as to the reporting process and how to fill out the document.

## Initial Defect Reporting

- Open the UAT Defect Log and locate the section of the document with the window name where the defect is occurring.

- Update the information in the corresponding cells as follows:

| Column | Description |
| --- | --- |
| Module | Found by using the menu path Main > Module name (e.g., Tables, Courtroom, etc.) |
| Window | Name of window |
| Date Reported | Date reported to CTS |
| Reporter | Initials of reporter |
| Tester | Initials of tester |
| Severity | Select one of the following: - High – equivalent to showstopper defect, cannot pass UAT without fixing defect - Medium – should be addressed but not a showstopper defect - Low – finding/defect that can pass UAT but should be addressed later or an enhancement |
| Status | New |
| Description (Findings/Steps to Recreate) | Provide a description of the issue and exact steps taken to replicate the issue |

- Once UAT cycle is completed, Reporter will email CTS and advise defects were added. CTS will review and update the document as follows:

| Column | Description |
| --- | --- |
| Status | Fix In-Progress: defect will be worked No Action: defect will not be addressed |
| UAT Iteration (CTS use only) | UAT Cycle where defect was reported |
| Date Return to UAT/Decision Date | Date Return to UAT: defect passed QA and released to UAT Decision Date: used with ‘No Action’ status |
| Comments/Decision | Additional information to support Status column |

- If a defect will be worked on, the issue will be retested and released back to stakeholders for testing. See Fix In-Progress for subsequent steps.

## Fix In-Progress

- Once CTS completes testing the fixed defect and it is ready for UAT, the UAT Defect Log will be updated as follows:

| Column | Description |
| --- | --- |
| Status | Returned to UAT: available for testing |
| Date Return to UAT/Decision Date | Date released to UAT |
| Comments/Decision | Additional information on fix implemented (if needed) |

- CTS will send out an email advising defect log has been updated/fixes have been released to UAT. See UAT – Pass or UAT – Fail for subsequent steps.

## UAT - Pass

- If testing is successful, Reporter will update the log as follows:

| Column | Description |
| --- | --- |
| Status | Resolved |
| UAT Retest Date | Date retested |
| UAT Retest Pass/Fail | Pass or Pass with Comments |

## UAT - Fail

- If testing is unsuccessful, Reporter will update the log as follows:

| Column | Description |
| --- | --- |
| Status | Returned to CTS |
| UAT Retest Date | Date retested |
| UAT Retest Pass/Fail | Fail |

- CTS will review and update the following columns:

| Column | Description |
| --- | --- |
| Status | Fix In-Progress: defect will be worked |
| UAT Iteration (CTS use only) | UAT Cycle where defect was reported |

- See Fix In-Progress for subsequent steps.