## Master Tracking
Sprint # | Track | Group Label | Main AR | Subtask | Related QA Subtasks | UAT Subtask | W# | Menu Group | Window Name | Object Name | Grouping | Status | Jira Status | QA Cycle | Dev | BSA | Date Started | To QA | 2 Week Start | Target Date | To UAT | UAT Start | Signed Off | Deployed | Build # | LOE to QA | Development | QA Test | Mitigation | UAT | Total Hours | Open Defects | Total Defects | Defect Log | On Dashboard | In Planning | No UAT (Internal) | Dev LOE (d) | QA LOE (d) | Total LOE (d) | Total Usage | Legacy Status | Metrics Status | Source | Match Method | Match Confidence | Overridden
Internal | Internal | Internal | VISAR-6166 | VISAR-7312 | VISAR-7469, VISAR-7349 |  | 1 | 1 - ADMIN | Auto Process Schedule | w_ct_m_mnt_auto_process_sched | Low High | In Development | Subtask Created | 1 | JC | BY | 2026-08-12 | 2026-08-26 | [8 empty] | 0 | 1.5 | 0 | 0 | 1.5 | 7 | 17 | Auto Process Schedule | Y |  | X | 8 | 5 | 13 | 41 | Internal | QA Cycle 2 | Pipeline + Metrics | Metrics hyperlink | High
Pre-Sprint | Internal | Pre-Sprint | VISAR-6166 | VISAR-7332 | VISAR-7429, VISAR-7407 |  | 2 | 1 - ADMIN | Date of Action Maintenance | w_ct_m_docket_date_of_action_maint | Low | Deployed | Subtask Completed | 2 | CN | DC | 2026-08-28 | 2026-09-11 |  |  | 2026-09-16 |  | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 2 | 2 | Date of Action |  |  | X | 4 | 1.5 | 5.5 | 8 | Deployed | Deployment Ready | Pipeline + Metrics | Metrics hyperlink | High | signedOff, deployed, build
| User | [5 empty] | 3 | 1 - ADMIN | Excel Batch Processing | w_ct_m_xl_batch_processing | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 243 |  |  | Pipeline |  | Unmatched
| User |  | VISAR-6166 | VISAR-7333 |  |  | 4 |  | Officer Consolidate | w_ct_m_officer_merge | Low High | Canceled | Canceled | 0 | CN |  | 2026-08-28 | [26 empty] | Metrics only | Metrics hyperlink | High
| Internal | [5 empty] | 5 | 1 - ADMIN | Person Delete | w_ct_m_person_delete | Low High | Not Started | [24 empty] | X | 8 | 5 | 13 | 0 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6499 | VISAR-6881, VISAR-6640 |  | 6 |  | Purge Duplicates | w_ct_m_purge_duplicate | Low | Deployed | Subtask Completed | 2 | SM | MU | 2025-12-31 | 2026-02-03 | 2026-03-25 | 2026-04-08 | 2026-05-01 |  | 2026-08-21 | 2026-05-05 | Build 5.02 | [12 empty] | 4 | 1.5 | 5.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
| Internal | [5 empty] | 7 | 1 - ADMIN | Vlan IP ranges | w_ct_m_vlan_ip_ranges | Low High | Not Started | [24 empty] | X | 8 | 5 | 13 | 37 |  |  | Pipeline |  | Unmatched
SG2 | User | SG2 | VISAR-6166 | VISAR-7419 |  |  | 8 | 3 - CALENDARING | Calendar List | w_ct_m_cal_list | Medium | In Development | Subtask In-Progress | 0 | NV | BY | 2026-10-05 | [8 empty] | 25 | 35.5 | 0 | 0 | 0 | 35.5 | 0 | 0 | Calendar List | Y |  |  | 12 | 6.5 | 18.5 | 73912 | In Development |  | Pipeline + Metrics | Metrics hyperlink | High | dev, bsa
SG2 | User | SG2 | VISAR-6166 | VISAR-7420 |  |  | 8.1 | 3 - CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | In Development | Subtask In-Progress | 0 | NV | BY | 2026-10-05 | [8 empty] | 15 | 38 | 0 | 0 | 0 | 38 | 0 | 0 | Post-Conviction Worksheet Report | Y |  |  | 12 | 6.5 | 18.5 | 1353 | In Development |  | Pipeline + Metrics | Metrics hyperlink | High
SG2 | User | SG2 | VISAR-6166 | VISAR-7421 | VISAR-7551, VISAR-7518, VISAR-7491 |  | 9 | 3 - CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | In UAT | In UAT | 3 | NV | CL | 2026-09-15 | 2026-10-05 | 2026-10-12 | 2026-10-26 | 2026-10-23 |  |  |  |  | 8 | 38.4 | 34 | 0 | 0 | 72.4 | 0 | 12 | Calendar Report | Y |  |  | 12 | 6.5 | 18.5 | 13643 | 2-Week |  | Pipeline + Metrics | Metrics hyperlink | High
SG2 | User | SG2 | VISAR-6166 | VISAR-7422 | VISAR-7560, VISAR-7559, VISAR-7550, VISAR-7519, VISAR-7490 |  | 9.1 | 3 - CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | In UAT | In UAT | 5 | NV | CL | 2026-09-15 | 2026-10-05 | 2026-10-12 | 2026-10-26 | 2026-10-23 |  |  |  |  | 5 | 21 | 28.5 | 0 | 0 | 49.5 | 1 | 9 | Calendar Batch Print | Y |  |  | 18 | 8 | 26 | 21740 | 2-Week |  | Pipeline + Metrics | Metrics hyperlink | High
SG2 | User | SG2 | VISAR-6166 | VISAR-7423 | VISAR-7493 |  | 9.2 | 3 - CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | Deployed | Subtask Completed | 1 | NV | CL | 2026-09-15 | 2026-10-05 | 2026-10-05 | 2026-10-19 | [5 empty] | 5 | [5 empty] | 0 | 0 | Web Browser of generated files | Y |  |  | 8 | 5 | 13 | 21221 | 2-Week |  | Pipeline + Metrics | Metrics hyperlink | High
SG2 | User | SG2 |  |  |  |  | 9.3 | 8 - COURTROOM | PDF Viewer from Minutes | w_ct_c_pdf_viewer | Low High | Not Started |  |  | NV | CL | [9 empty] | 5 | [5 empty] | 1 | 139 | Minutes | Y |  |  | 8 | 5 | 13 | 803806 | 2-Week |  | Pipeline |  | Unmatched
SG2 | User | SG2 | VISAR-6166 | VISAR-7401 | VISAR-7483, VISAR-7479, VISAR-7436 | VISAR-7545 | 10 | 3 - CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | In UAT | In UAT | 3 | CN | DC | 2026-09-09 | 2026-09-18 | 2026-09-29 | 2026-10-13 | 2026-10-02 | 2026-10-19 |  |  |  | 6 | 20 | 27 | 15 | 3 | 65 | 0 | 15 | Calendar Transfer | Y |  |  | 8 | 5 | 13 | 8014 | 1-Week | In Development | Pipeline + Metrics | Object name match | Medium
SG2 | User | SG2 | VISAR-6166 | VISAR-7424 |  |  | 11 | 3 - CALENDARING | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | Medium | Canceled | Canceled | 0 | [17 empty] | 0 | 0 | Calendar Transfer Notices | Y |  |  | 12 | 6.5 | 18.5 | 10 |  |  | Jira (canceled) | Manual - canceled window | High
SG2 | User | SG2 | VISAR-6166 | VISAR-7425 |  |  | 12 | 3 - CALENDARING | Court Closure Transfer | w_ct_m_cal_close_transfer | Low High | Canceled | Canceled | 0 | [17 empty] | 0 | 0 | Court closure transfer | Y | [8 empty] | Jira (canceled) | Manual - canceled window | High
SG2 | User | SG2 | VISAR-6166 | VISAR-7426 | VISAR-7509, VISAR-7499, VISAR-7472 | VISAR-7582 | 13 | 3 - CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | In UAT | In UAT | 3 | CN | DC | 2026-09-18 | 2026-09-29 | 2026-10-06 | 2026-10-20 | 2026-10-08 | 2026-10-19 |  |  |  | 6 | 18 | 16 | 6.5 | 3 | 43.5 | 1 | 17 | Court Trial Transfer | Y |  |  | 12 | 6.5 | 18.5 | 243 | 1-Week |  | Pipeline | Object name match | Medium
SG2 | User | SG2 | VISAR-6166 | VISAR-7427 | VISAR-7513 |  | 14 | 3 - CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | In QA - Dev | Subtask In-Progress | 1 | CN | CL | 2026-09-18 | 2026-10-12 | 2026-10-22 | 2026-11-05 | [5 empty] | 8 | 30 | 22 | 6 | 0 | 58 | 8 | 9 | Notice of Packaged Hearings | Y |  |  | 8 | 5 | 13 | 258 | In Development |  | Pipeline | Object name match | Medium | bsa
| User | [5 empty] | 15 | 4 - CASE | Case Backup and Restore | w_ct_m_case_backup_trg | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16 | 4 - CASE | Case Maintenance | w_ct_m_case_maint | Very High | Not Started | [25 empty] | 24 | 11 | 35 | 208279 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16.1 | 4 - CASE | Vision Public Case - Input | w_ct_r_public_case_input | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 1590 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16.2 | 4 - CASE | Person Information Select | w_ct_m_person_select | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 164937 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16.3 | 4 - CASE | Unavailable Court Dates | w_ct_r_unavailable_dates | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 58 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16.4 | 4 - CASE | Case Dates | w_ct_r_cal_case_dates | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 16389 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 16.5 | 4 - CASE | Other Cases | w_ct_r_cal_other_cases | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 6 |  |  | Pipeline |  | Unmatched
SG5 | User | SG5 | VISAR-6166 | VISAR-7557 |  |  | 17 | 4 - CASE | Case Summary | w_ct_m_case_summary | Medium High | In Sprint Planning | Subtask Created | 0 | SM | [10 empty] | 26 | [5 empty] | 0 | 0 | Case Summary |  | Y |  | 18 | 8 | 26 | 220508 |  |  | Pipeline | Object name match | Medium
SG5 | User | SG5 | VISAR-6166 | VISAR-7580 |  |  | 17.1 | 4 - CASE | Close Elig? Button | w_ct_r_case_closure_eligible | Low High | In Sprint Planning | Subtask Created | 0 | SM | [10 empty] | 5 | [5 empty] | 0 | 0 | Close Elig Button |  | Y |  | 8 | 5 | 13 | 2199 |  |  | Pipeline | Object name match | Medium
SG5 | User | SG5 | VISAR-6166 | VISAR-7563 |  |  | 17.2 | 4 - CASE | Bail Schedule Maintenance Response | w_ct_r_fscl_bail_sched_maint_response | Low High | In Sprint Planning | Subtask Created | 0 | SM | BY | [9 empty] | 0.5 | [5 empty] | 0 | 0 | Bail Schedule Maintenance Response |  | Y |  | 8 | 5 | 13 | 45034 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 18 | 4 - CASE | Case Transfer | w_ct_m_case_transfer_cst | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 19 | 4 - CASE | Citation Batches / Batch Entry | w_ct_m_cite_batch_entry | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 1333 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 20 | 4 - CASE | Citation Entry | w_ct_m_case_citation_entry | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 707 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 21 | 4 - CASE | LEA Interface | w_ct_m_case_lea_interface | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 6 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 22 | 4 - CASE | Mass Case/Calendar Copy | w_ct_m_mass_case_copy | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 23 | 4 - CASE | Missing Complaint | w_ct_m_case_missing_complaint | Medium High | Not Started | [19 empty] | 0 | 0 | Missing Complaints Purge |  |  |  | 18 | 8 | 26 | 7451 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 24 | 4 - CASE | NCIC Case Initiation | w_ct_m_case_maint_ncic | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1920 |  |  | Pipeline |  | Unmatched
SG1 | User | SG1 | VISAR-6166 | VISAR-7012 | VISAR-7384, VISAR-7314, VISAR-7178 | VISAR-7457 | 25 | 4 - CASE | Priors | w_ct_m_case_priors | High | Deployed | Subtask Completed | 3 | JL | MU | 2026-05-19 | 2026-07-07 | 2026-09-08 | 2026-09-22 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 6 | 6 | 0 | 59 | Priors | Y |  |  | 21 | 10 | 31 | 452623 | Deployed | UAT Ready | Pipeline + Metrics | Metrics hyperlink | High | twoWk, deployed, build
SG1 | User | SG1 | VISAR-6166 | VISAR-7012 |  | VISAR-7457 | 25.1 | 4 - CASE | Print - Copies Spec. | w_ct_m_case_priors_print_spec | Low | Deployed | Subtask Completed | 3 | JL | MU | 2026-05-19 | 2026-07-07 | 2026-09-08 | 2026-09-22 | 2026-09-15 | 2026-09-22 | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 59 | Priors | Y |  |  | 4 | 1.5 | 5.5 | 7717 | Deployed |  | Pipeline | Manual - bundled subtask | High | twoWk, deployed, build
| User | [5 empty] | 26 | 5 - COLLECTIONS | Campaign Maintenance | w_ct_m_coll_campaign_maint | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 14 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 27 | 5 - COLLECTIONS | Collections | w_ct_m_coll_collections | Very High | Not Started | [19 empty] | 0 | 0 | Cost of Collections |  |  |  | 24 | 11 | 35 | 247214 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 28 | 5 - COLLECTIONS | Collections Campaign Queue | w_ct_m_coll_campaign_queue | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 133 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 29 | 5 - COLLECTIONS | Collections Person Interface | w_ct_m_coll_person_interface | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 296 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 32 | 5 - COLLECTIONS | Financial Evaluation | w_ct_m_coll_fin_eval_list | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 7 |  |  | Pipeline |  | Unmatched
| User |  | VISAR-6166 | VISAR-6907 |  |  | 33 | 5 - COLLECTIONS | FTBCOD Interface | w_ct_m_case_ftbcod_select | High | On Hold | On-Hold | 0 | NV | CC | 2026-04-23 | [14 empty] | 0 | 0 | FTBCOD Interface | Y |  |  | 21 | 10 | 31 | 1217 |  | On Hold | Pipeline + Metrics | Metrics hyperlink | High
| User | [5 empty] | 34 | 5 - COLLECTIONS | FTBCOD Payment Processor | w_ct_m_ftbcod_payment | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 1108 |  |  | Pipeline + Metrics |  | Unmatched
| User | [5 empty] | 34.1 | 5 - COLLECTIONS | Import Action File (Select button) | w_ct_r_coll_ftbcod_import_actions | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 48 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 34.2 | 5 - COLLECTIONS | Import Claim Schedule File (FTBCOD) | w_ct_r_ftbcod_import_cs | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 124 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 35 | 5 - COLLECTIONS | FTBTI Interface | w_ct_m_coll_ftbti_interface | High | Not Started | [25 empty] | 21 | 10 | 31 | 177 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 36 | 5 - COLLECTIONS | FTBTI Payment Processor | w_ct_m_ftbti_payment | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 249 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 36.1 | 5 - COLLECTIONS | Import Claim Schedule File (FTBTI) | w_ct_r_cmmn_file_search | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 98 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 36.2 | 5 - COLLECTIONS | List Search | w_ct_r_cmmn_list_search | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 5 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 37 | 5 - COLLECTIONS | OCV Payment Processor | w_ct_m_ocv_payment | High | Not Started | [25 empty] | 21 | 10 | 31 | 373 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 38 | 5 - COLLECTIONS | OCV Return | w_ct_m_ocv_file_load | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 9 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 40 | 7 - COUNTER | Cash Bail Notice | w_ct_m_bail_bond_notice | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 4 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 41 | 7 - COUNTER | Bail Entry | w_ct_m_bail_maint | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 29457 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 41.1 | 7 - COUNTER | Agency Unit Address List (2-Bail Bond button) | w_ct_r_agency_unit_addrs_change | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 238 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 43 | 7 - COUNTER | Cashier Reconciliation | w_ct_m_cashier_recon | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 17084 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 44 | 7 - COUNTER | Counter Payment | w_ct_m_counter | Very High | Not Started | [25 empty] | 24 | 11 | 35 | 312924 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 44.1 | 7 - COUNTER | Receipts (many flavors) |  | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 |  |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 44.2 | 7 - COUNTER | Bail Forfeiture / Traffic School Payment Plans | w_ct_r_agree_pay_bf | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 3691 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 44.3 | 7 - COUNTER | Accept Payment | w_ct_r_payment | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 125125 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 44.4 | 7 - COUNTER | Notes | w_ct_r_cmmn_note | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 16020 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 45 | 7 - COUNTER | Multi-Case Payment | w_ct_m_fscl_multi_case_payment | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 5201 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 46 | 7 - COUNTER | Non-Case Payment | w_ct_m_noncase_pymt | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 5968 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 47 | 7 - COUNTER | Open Cashier Session | w_ct_m_cashier_open_session | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 16193 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 48 | 7 - COUNTER | TS Completion | w_ct_m_mark_ts_complete | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 44 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 49 | 7 - COUNTER | Victim Restitution Notice | w_ct_m_vr_notice | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 489 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50 | 8 - COURTROOM | Courtroom / Admin Minutes Entry | w_ct_courtroom | Very High | Not Started | [19 empty] | 1 | 139 | Minutes |  |  |  | 24 | 11 | 35 | 1147036 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.1 | 8 - COURTROOM | Docket Code Help | w_ct_doc_help_rsp | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 271196 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.2 | 8 - COURTROOM | Multi-Case Entry | w_ct_doc_multicase | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 148921 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.3 | 8 - COURTROOM | Print Imaging Barcode | w_ct_r_barcode_current_hrg | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 481486 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.4 | 8 - COURTROOM | Print Imaging Barcode Sheet (reprint) | w_ct_r_barcode_print | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 91198 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.5 | 8 - COURTROOM | Extended Text Entry Window | w_ct_r_ctrs_dckt_text | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 490158 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 50.6 | 8 - COURTROOM | Courtroom Print | w_ct_r_dckt_report_printing | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 0 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6475 | VISAR-6993, VISAR-6928, VISAR-6898, VISAR-6879, VISAR-6497 |  | 51 |  | Courtroom Setup | w_ct_m_ctrs_courtroom_setup | Low High | Deployed | Subtask Completed | 7 | SM | BY | 2025-12-23 | 2025-12-30 | 2026-01-14 | 2026-01-28 | 2025-12-29 | 2026-05-20 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 32 | Courtroom Setup |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
| User | [5 empty] | 52 |  | Minutes - Generic Notice |  |  | Not Started | [31 empty] | Metrics only |  | Unmatched
SG2 | User | SG2 | VISAR-6166 | VISAR-6315 | VISAR-7435, VISAR-7410, VISAR-7378, VISAR-7205, VISAR-7195 | VISAR-7498 | 53 | 8 - COURTROOM | Minutes | w_ct_m_docket_reporting | Medium High | In UAT | In UAT | 4 | SM | BY | 2025-12-15 | 2026-07-16 | 2026-09-18 | 2026-10-02 | 2026-07-16 | 2026-10-06 |  |  |  |  | 15 | 24 | 0 | 7 | 46 | 1 | 139 | Minutes |  |  |  | 18 | 8 | 26 | 1882930 | In UAT | QA Cycle 4 | Pipeline + Metrics | Manual - bundled subtask | High | twoWk, sprint
| User | [5 empty] | 53.1 | 8 - COURTROOM | CIS Sheets (16 Flavors) |  | Very High | Not Started | [25 empty] | 24 | 11 | 35 |  |  |  | Pipeline |  | Unmatched
SG2 | User | SG2 | VISAR-6166 | VISAR-6315 |  | VISAR-7498 | 53.3 | 8 - COURTROOM | VCJIS - Court Reports Preview | w_ct_r_dckt_preview_docket_rpt | Low High | In UAT | In UAT | 4 | SM | BY | 2025-12-15 | 2026-07-16 | 2026-09-18 | 2026-10-02 | 2026-07-16 | 2026-10-06 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 139 | Minutes |  |  |  | 8 | 5 | 13 | 149 | In UAT |  | Pipeline | Manual - bundled subtask | High | twoWk, sprint
| User | [5 empty] | 54 | 8 - COURTROOM | MOCS | w_ct_m_mocs | Very High | Not Started | [19 empty] | 0 | 0 | MOCS Docket Definition |  |  |  | 24 | 11 | 35 | 21233 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 54.1 | 8 - COURTROOM | Docket Selection ( MOCS) | w_ct_r_mocs_dkt_entry | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 91537 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 54.2 | 8 - COURTROOM | MOCS Multi Case Entry | w_ct_r_mocs_multi | Very High | Not Started | [25 empty] | 24 | 11 | 35 | 940 |  |  | Pipeline |  | Unmatched
SG1 | User | SG1 | VISAR-6166 | VISAR-7188 | VISAR-7390, VISAR-7366, VISAR-7289, VISAR-7288 |  | 55 | 9 - EXHIBITS | Exhibit List | w_ct_m_exhibit_list | Low High | Deployed | Subtask Completed | 3 | JL | DC | 2026-07-28 | 2026-07-30 | 2026-09-08 | 2026-09-22 | 2026-09-15 | 2026-09-28 | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 9 | 0 | 3 | 12 | 0 | 30 | Exhibit List | Y |  |  | 8 | 5 | 13 | 6712 | Deployed | UAT Ready | Pipeline + Metrics | Metrics hyperlink | High | twoWk, build
SG1 | User | SG1 | VISAR-6166 | VISAR-7188 |  |  | 55.1 | 9 - EXHIBITS | Exhibit Search | w_ct_r_exhibit_list_case_search | Low | Deployed | Subtask Completed | 3 | JL | DC | 2026-07-28 | 2026-07-30 | 2026-09-08 | 2026-09-22 | 2026-09-15 | 2026-09-28 | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | Exhibit List |  |  |  | 4 | 1.5 | 5.5 | 7131 | Deployed | UAT Ready | Pipeline + Metrics | Metrics hyperlink | High | twoWk, build
SG1 | Internal | SG1 Internal | VISAR-6166 | VISAR-7189 | VISAR-7408, VISAR-7330 |  | 56 | 9 - EXHIBITS | Exhibit Maintenance | w_ct_m_exhibit_maintenance | Low High | Deployed | Subtask Completed | 2 | SM | DC | 2026-07-15 | 2026-08-17 |  |  | 2026-09-17 |  |  | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 6 | 0 | 0 | 6 | 11 | 11 | Exhibit Maintenance | Y |  | X | 8 | 5 | 13 | 6 | Deployed | Deployment Ready | Pipeline + Metrics | Metrics hyperlink | High | deployed, build
SG1 | Internal | SG1 Internal | VISAR-6166 | VISAR-7189 |  |  | 56.1 | 9 - EXHIBITS | New Exhibit Hearing List | w_ct_m_exhibit_new_hearing | Low High | Deployed | Subtask Completed | 2 | SM | DC | 2026-07-15 | 2026-08-17 |  |  | 2026-09-17 |  |  | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 0 | 0 | 11 | 11 | Exhibit Maintenance | Y |  | X | 8 | 5 | 13 | 1 | Deployed | Deployment Ready | Pipeline + Metrics | Metrics hyperlink | High | deployed, build
SG1 | Internal | SG1 Internal | VISAR-6166 | VISAR-7185 | VISAR-7409, VISAR-7391 |  | 57 | 9 - EXHIBITS | Exhibit Management | w_ct_m_exhibit_management | Low | Deployed | Subtask Completed | 2 | NV | DC | 2026-07-14 | 2026-09-04 |  |  | 2026-09-14 |  |  | 2026-10-08 | Build 5.07 NG1.1 | [6 empty] | 20 | 20 | Exhibit Management | Y |  | X | 4 | 1.5 | 5.5 | 6 | Deployed | Deployment Ready | Pipeline + Metrics | Metrics hyperlink | High | deployed, build
SG1 | Internal | SG1 Internal | VISAR-6166 | VISAR-7206 | VISAR-7392 |  | 57.1 | 9 - EXHIBITS | Exhibit Management Search | w_ct_m_exhibit_management_srch |  | Deployed | Subtask Completed | 2 | NV | DC | 2026-07-20 | 2026-09-04 |  |  | 2026-09-15 |  |  | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 1 | 0 | 0 | 1 | 20 | 20 | Exhibit Management | Y |  | X |  |  |  | 7 | Deployed | Deployment Ready | Pipeline + Metrics | Metrics hyperlink | High | deployed, build
SG1 | User | SG1 | VISAR-6166 | VISAR-7206 |  |  | 57.2 | 9 - EXHIBITS | Exhibit History | w_ct_r_exhibit_history |  | Deployed | Subtask Completed | 2 | NV | DC | 2026-07-20 | 2026-09-04 | 2026-09-14 | 2026-09-28 | 2026-09-15 |  | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 0 | 0 | 20 | 20 | Exhibit Management | [6 empty] | 9 | Deployed | UAT Ready | Pipeline + Metrics | Metrics hyperlink | High | signedOff, deployed, build
SG1 | Internal | SG1 Internal | VISAR-6166 | VISAR-7206 | VISAR-7392 |  | 57.3 |  | Exhibit Disposition Notice | w_ct_m_exhibit_management_srch |  | Deployed | Subtask Completed | 2 | NV | DC | 2026-07-20 | 2026-09-04 |  |  | 2026-09-15 |  |  | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 0 | 0 | 0 | 0 | 20 | 20 | Exhibit Management | Y | [7 empty] | Deployment Ready | Metrics only | Metrics hyperlink | High | deployed, build
| User | [5 empty] | 58 | 10 - FISCAL | Bail Maintenance | w_ct_m_bail_maint | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 29457 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 59 | 10 - FISCAL | Case Distribution Override | w_ct_m_fscl_dist_override | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 3 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6797 | VISAR-7096, VISAR-7073, VISAR-7022, VISAR-7007, VISAR-6987, VISAR-6874 |  | 60 |  | Case Payment History | w_ct_m_fscl_payment_hist |  | Deployed | Subtask Completed | 6 | NV | MU | 2026-03-16 | 2026-04-13 | 2026-05-06 | 2026-05-20 | 2026-06-05 | 2026-06-05 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 1 | 28 | Case Payment History |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
| User | [5 empty] | 61 | 10 - FISCAL | Check Approval | w_ct_m_fscl_chk_apprv | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1111 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 61.1 | 10 - FISCAL | Specify Check Number | w_ct_r_fscl_chk_nbr | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 61.2 | 10 - FISCAL | Print Checks | w_ct_r_fscl_prnt_chks | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 62 | 10 - FISCAL | Check Maintenance | w_ct_m_fscl_chk_maint | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 546 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 63 | 10 - FISCAL | Fiscal Case Analysis | w_ct_m_fiscal_case_analysis | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 1296 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 64 | 10 - FISCAL | Misapplications/Voids | w_ct_m_fscl_pmt_misapp_void | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 6926 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 64.1 | 10 - FISCAL | w_ct_r_fiscal_batch_cases | w_ct_r_fiscal_batch_cases | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 130 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 65 | 10 - FISCAL | Reapply Payment | w_ct_m_fscl_reapp_remit | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 10 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 66 | 10 - FISCAL | Reversals | w_ct_m_fscl_pmt_reversals | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 83 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 66.1 | 10 - FISCAL | w_ct_r_fiscal_multi_cases_reversal | w_ct_r_fiscal_multi_cases_reversal | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 1 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 67 | 10 - FISCAL | Victim Restitution Approval | w_ct_m_fscl_vr_apprv | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 491 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 68 | 10 - FISCAL | Summary Judgment | w_ct_m_summary_judgement | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1012 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 69 | 11 - FISCAL MAINTENANCE | Bail Distribution Schedule | w_ct_m_fscl_bail_dist_sched | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 114 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 70 | 11 - FISCAL MAINTENANCE | Base Distribution Xref | w_ct_m_fscl_base_dist_xref | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 1 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 71 | 11 - FISCAL MAINTENANCE | Bondsman / Surety | w_ct_m_bondsman_surety | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 89 |  |  | Pipeline |  | Unmatched
SG6 | User | SG6 | VISAR-6166 | VISAR-7564 |  |  | 72 | 11 - FISCAL MAINTENANCE | Chart of Accounts | w_ct_m_fscl_chart_of_accts | Low | In Sprint Planning | Subtask Created | 0 | CN | [10 empty] | 5 | [5 empty] | 0 | 0 | Chart of Accounts |  | Y |  | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7544 | VISAR-7554 |  | 73 | 11 - FISCAL MAINTENANCE | Cost of Collections | w_ct_m_fscl_cost_of_collections | Low High | In QA - BSA | In QA | 1 | KH | DC | 2026-10-19 | 2026-10-21 | [7 empty] | 5 | [5 empty] | 0 | 0 | Cost of Collections |  |  |  | 8 | 5 | 13 | 13 |  |  | Pipeline | Object name match | Medium
SG7 | User | SG7 | VISAR-6166 | VISAR-7565 |  |  | 74 | 11 - FISCAL MAINTENANCE | Fee Distribution Schedule | w_ct_m_fscl_fee_dist_sched | Low High | In Sprint Planning | Subtask Created | 0 | NV | [10 empty] | 10 | [5 empty] | 0 | 0 | Fee Distribution Schedule |  | Y |  | 8 | 5 | 13 | 14 |  |  | Pipeline | Object name match | Medium
SG7 | User | SG7 | VISAR-6166 | VISAR-7566 |  |  | 75 | 11 - FISCAL MAINTENANCE | Fund Maintenance | w_ct_m_fscl_fund_maint | Low High | In Sprint Planning | Subtask Created | 0 | NV | [10 empty] | 8 | [5 empty] | 0 | 0 | Fund Maintenance |  | Y |  | 8 | 5 | 13 | 11 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 76 | 11 - FISCAL MAINTENANCE | PA Distribution Schedule | w_ct_m_fscl_pa_dist_sched | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 57 |  |  | Pipeline |  | Unmatched
SG6 | User | SG6 | VISAR-6166 | VISAR-7567 |  |  | 77 | 11 - FISCAL MAINTENANCE | PA Distribution Xref | w_ct_m_fscl_dist_xref | Low | In Sprint Planning | Subtask Created | 0 | NV | [10 empty] | 7 | [5 empty] | 0 | 0 | PA Distribution Xref |  | Y |  | 4 | 1.5 | 5.5 | 1 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 78 | 11 - FISCAL MAINTENANCE | Special Distribution Schedule | w_ct_m_fscl_spl_dist_sched | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 26 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 79 | 11 - FISCAL MAINTENANCE | VR Distribution Schedule | w_ct_m_fscl_vr_dist_sched | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 1 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 80 | 12 - INTERFACES | ATP Dashboard | w_ct_m_atp_dashboard | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1524 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 81 | 12 - INTERFACES | Check Auditor/Controller | w_ct_m_fscl_audit_controller | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 54 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 82 | 12 - INTERFACES | DMV Abstract on Demand | w_ct_m_dmv_abstract_on_demand | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 83 | 12 - INTERFACES | DMV Admin Transactions | w_ct_m_dmv_admin_tran | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 12 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 84 | 12 - INTERFACES | DMV Error Cases Report | w_ct_m_dmv_error_queue_mon | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1270 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 85 | 12 - INTERFACES | DMV Error Maintenance | w_ct_m_dmv_abstract_maint | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 15000 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 86 | 12 - INTERFACES | DMV Prior Missing Report | w_ct_m_dmv_priors_missing_cases | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 2 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 87 | 12 - INTERFACES | DOJ Interface | w_ct_m_intf_doj_review | High | Not Started | [25 empty] | 21 | 10 | 31 | 1633 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 87.1 | 12 - INTERFACES | DOJ Abstract | w_ct_r_doj_abstract_viewer | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 16 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 88 | 12 - INTERFACES | OneOC - Clerk Review Module | w_ct_m_oneoc_interface | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1979 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 89 | 13 - JBSIS | JBSIS Audit Report | w_ct_m_jbsis_audit_report | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 46 |  |  | Pipeline |  | Unmatched
SG1 | User | SG1 | VISAR-6166 | VISAR-7215 | VISAR-7385, VISAR-7319 | VISAR-7468 | 90 | 13 - JBSIS | JBSIS Maintenance | w_jbsis_maintenance | Medium | Deployed | Subtask Completed | 2 | NV | DC | 2026-07-21 | 2026-08-13 | 2026-09-02 | 2026-09-16 | 2026-09-15 | 2026-09-18 | 2026-09-29 | 2026-10-08 | Build 5.07 NG1.1 |  | 0 | 1.5 | 4 | 0 | 18.5 | 1 | 17 | JBSIS Maintenance | Y |  |  | 12 | 6.5 | 18.5 | 3177 | Deployed | UAT Ready | Pipeline + Metrics | Metrics hyperlink | High | hUAT, build
| User | [5 empty] | 91 | 13 - JBSIS | JBSIS Report Defn. | w_ct_m_jbsis_report_detail | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 41 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 92 | 13 - JBSIS | JBSIS Reporting | w_ct_jbsis_manrpt | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 572 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 92.1 | 13 - JBSIS | JBSIS Case Listing | w_ct_jbsis_case_person | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 2524 |  |  | Pipeline |  | Unmatched
SG8 | User | SG8 | VISAR-6166 | VISAR-7568 |  |  | 93 | 15 - PERSON | Attorney Maintenance | w_ct_m_attorney | Medium | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Attorney Maintenance |  | Y |  | 12 | 6.5 | 18.5 | 1410 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7569 |  |  | 94 | 15 - PERSON | Interpreters Maintenance | w_ct_m_interpreters | Low High | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Interpreters Maintenance |  | Y |  | 8 | 5 | 13 | 127 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7570 |  |  | 94.1 | 15 - PERSON | Interpreters in System | w_ct_r_interpreters_lookup | Low | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Interpreters in System |  | Y |  | 4 | 1.5 | 5.5 | 157 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7571 |  |  | 94.2 | 15 - PERSON | Interpreter Remarks(Ctrl+Alt+T under Remarks) | w_ct_r_interpreter_remarks | Low | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Interpreter Remarks(Ctrl+Alt+T under Remarks) |  | Y |  | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7572 |  |  | 95 | 15 - PERSON | Multi-Person Maintenance | w_ct_m_multi_person_maint | Low High | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Multi-Person Maintenance |  | Y |  | 8 | 5 | 13 | 6620 |  |  | Pipeline | Object name match | Medium
SG8 | User | SG8 | VISAR-6166 | VISAR-7573 |  |  | 95.1 | 15 - PERSON | Multi-Person Maintenance Datafix Report | w_ct_r_mpm_report | Low | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Multi-Person Maintenance Datafix Report |  | Y |  | 4 | 1.5 | 5.5 | 6329 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 96 | 15 - PERSON | Person Link/Unlink | w_ct_m_person_link_unlink | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 238 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 97 | 15 - PERSON | Person Maintenance | w_ct_m_person_maint | Medium | Not Started | [19 empty] | 0 | 0 | Multi-Person Maintenance Datafix Report |  |  |  | 12 | 6.5 | 18.5 | 146301 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 97.1 | 15 - PERSON | Person Search | w_ct_r_person_search | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 126349 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 97.2 | 15 - PERSON | Quick Add |  | Low High | Not Started | [25 empty] | 8 | 5 | 13 |  |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 98 | 15 - PERSON | Person Unlink | w_ct_m_person_unlink | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 3 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 99 | 15 - PERSON | Professional Consolidation | w_ct_m_professional_consolidation | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 6 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 100 | 15 - PERSON | Professional Maintenance | w_ct_m_professional_maint | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 74 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 100.1 | 15 - PERSON | New Professional | w_ct_r_professional_new | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 20 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 101 | 15 - PERSON | Sealed Access | w_ct_r_security_admin | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 817 |  |  | Pipeline |  | Unmatched
SG3 | User | SG3 | VISAR-6166 | VISAR-7443 |  |  | 102 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium | In Development | In Unit Test | 0 | SM |  | 2026-10-19 | [8 empty] | 8 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | Batch Purge | Y |  |  | 12 | 6.5 | 18.5 | 126 |  |  | Pipeline | Object name match | Medium
SG3 | User | SG3 | VISAR-6166 | VISAR-7444 | VISAR-7547 |  | 103 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium | In QA - BSA | In QA | 1 | CN | DC | 2026-10-09 | 2026-10-20 | [7 empty] | 10 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | Calendar File Location | Y |  |  | 12 | 6.5 | 18.5 | 460 | In Development |  | Pipeline | Object name match | Medium
SG3 | User | SG3 | VISAR-6166 | VISAR-7445 | VISAR-7561, VISAR-7549 |  | 104 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium | In QA - Dev | In Unit Test | 2 | SM | BY | 2026-10-05 | 2026-10-20 | 2026-10-22 | 2026-11-05 | [5 empty] | 8 | 37 | 9 | 9 | 0 | 55 | 15 | 16 | Case File Purge | Y |  |  | 12 | 6.5 | 18.5 | 140 | In Development |  | Pipeline | Object name match | Medium | dev, bsa
SG4 | User | SG4 | VISAR-6166 | VISAR-7446 |  |  | 105 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High | In Sprint Planning | Subtask Created | 0 | CN | [10 empty] | 8 | [5 empty] | 0 | 0 | File Location | Y | Y |  | 8 | 5 | 13 | 6575 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7447 | VISAR-7546 |  | 105.1 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low | In QA - BSA | In QA | 1 | CN | DC | 2026-10-13 | 2026-10-20 | [7 empty] | 4 | 4.5 | 0 | 0 | 0 | 4.5 | 0 | 0 | Location History | Y |  |  | 4 | 1.5 | 5.5 | 641 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7448 |  |  | 106 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High | In Sprint Planning | Subtask Created | 0 | SM | [10 empty] | 5 | [5 empty] | 0 | 0 | File Request | Y | Y |  | 8 | 5 | 13 | 3406 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7449 |  |  | 107 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low | In Sprint Planning | Subtask Created | 0 | SM | [10 empty] | 5 | [5 empty] | 0 | 0 | File Request Inquiry | Y | Y |  | 4 | 1.5 | 5.5 | 5 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7450 |  |  | 108 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High | In Development | Subtask In-Progress | 0 | CN |  | 2026-10-19 | [8 empty] | 5 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | File Request Maintenance |  |  |  | 8 | 5 | 13 | 3 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7451 |  |  | 109 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium | In Sprint Planning | Subtask Created | 0 | NV | BY | [9 empty] | 8 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | Image Maintenance | Y | Y |  | 12 | 6.5 | 18.5 | 38737 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7452 |  |  | 109.1 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low | In Sprint Planning | Subtask Created | 0 | NV | BY | [9 empty] | 5 | [5 empty] | 0 | 0 | Docket Code Lookup | Y | Y |  | 4 | 1.5 | 5.5 | 3 |  |  | Pipeline | Object name match | Medium
SG4 | User | SG4 | VISAR-6166 | VISAR-7453 |  |  | 110 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium | In Sprint Planning | Subtask Created | 0 | NV | BY | [9 empty] | 0.5 | [5 empty] | 0 | 0 | Image Viewer | Y | Y |  | 12 | 6.5 | 18.5 | 57610 |  |  | Pipeline | Object name match | Medium
SG3 | User | SG3 | VISAR-6166 | VISAR-7454 |  |  | 111 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium | In Sprint Planning | Subtask Created | 0 | SM | [10 empty] | 8 | [5 empty] | 0 | 0 | Missing Complaints Purge | Y | Y |  | 12 | 6.5 | 18.5 | 0 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 112 | 17 - REPORTS | Monthly Funding Report | w_ct_m_fscl_month_fund_report | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 750 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.1 | 17 - REPORTS | Open Cases Report | w_ct_m_open_cases | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 1523 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.2 | 17 - REPORTS | Bail Bond Activity Report | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.3 | 17 - REPORTS | Bail Bond Summary Judgment | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.4 | 17 - REPORTS | Bail Forfeiture Report | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.5 | 17 - REPORTS | Summary Judgment Bail Bonds Payment Due | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.6 | 17 - REPORTS | Case Calendar Summary | w_ct_m_cal_sum | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 2870 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.7 | 17 - REPORTS | Case Payment Activity Query | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 113.8 | 17 - REPORTS | Cash Bail Forfeiture Notice | w_ct_r_report_builder | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 37048 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 114 | 17 - REPORTS | State Prison Abstracts | w_ct_m_prsn_abstract | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 3987 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 115 | 18 - SCHEDULE MAINTENANCE | Special Schedule | w_ct_m_fscl_special_schedule | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 116 | 18 - SCHEDULE MAINTENANCE | Speed Schedule | w_ct_m_fscl_speed_sched | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 4 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 116.1 | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule | w_ct_r_fscl_speed_sched | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 117 | 18 - SCHEDULE MAINTENANCE | Speed Schedule 2 | w_ct_m_fscl_speed_sched_2 | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 5 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 117.1 | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule (Speed Sched2) | w_ct_r_fscl_speed_sched_2 | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 118 | 19 - SECURITY | Advanced Menu Manager | w_ct_m_menu_full | Medium | Not Started | [24 empty] | X | 12 | 6.5 | 18.5 | 8 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 119 | 19 - SECURITY | Basic Menu Manager | w_ct_m_menu_basic | Medium | Not Started | [24 empty] | X | 12 | 6.5 | 18.5 | 41 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 119.1 | 19 - SECURITY | Vision Menu Profile Report | w_ct_r_menu_profile_report | Low | Not Started | [24 empty] | X | 4 | 1.5 | 5.5 | 6 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 120 | 19 - SECURITY | Menu Admin | w_ct_r_menu_admin | Medium | Not Started | [24 empty] | X | 12 | 6.5 | 18.5 | 5 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 121 | 19 - SECURITY | Security Admin | w_ct_r_security_admin | Medium High | Not Started | [24 empty] | X | 18 | 8 | 26 | 817 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6895 | VISAR-7051, VISAR-6920 |  | 122 |  | Unlock Case | w_ct_m_case_lock_maintenance | Low | Deployed | Subtask Completed | 2 | NV | BY | 2026-04-21 | 2026-04-27 | 2026-05-22 | 2026-06-05 | 2026-04-27 | 2026-06-03 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 6 | Unlock Case - Case Lock Maintenance |  |  |  | 4 | 1.5 | 5.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
Internal | Internal | Internal | VISAR-6166 | VISAR-7368 |  |  | 123 | 20 - TABLES | Agency Codes | w_ct_m_agency_codes | Low | On Hold | On-Hold | 0 | NV | BY | 2026-09-03 | [14 empty] | 0 | 0 | Agency Codes | Y |  | X | 4 | 1.5 | 5.5 | 33 | Internal | On Hold | Pipeline + Metrics | Metrics hyperlink | High
Internal | Internal | Internal | VISAR-6166 | VISAR-7296 | VISAR-7548, VISAR-7379, VISAR-7365, VISAR-7318 |  | 124 | 20 - TABLES | Agency X-Ref Maintenance | w_ct_m_maint_agy_xref | Low High | In QA - BSA | In QA | 2 | CN | BY | 2026-08-04 | 2026-08-13 | [8 empty] | 0 | 1 | 2 | 0 | 3 | 1 | 9 | Agency X-Ref Maintenance | Y |  | X | 8 | 5 | 13 | 25 | Internal | QA Cycle 3 | Pipeline + Metrics | Metrics hyperlink | High
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6168 | VISAR-6875, VISAR-6830, VISAR-6700 |  | 125 |  | Bail Schedule | w_ct_m_fscl_bail_sched_maint | Medium High | Deployed | Subtask Completed | 3 | JL | MU | 2025-09-16 | 2026-02-23 | 2026-03-25 | 2026-04-08 | 2026-05-01 | 2026-04-29 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 58 | Bail Schedule |  |  |  | 18 | 8 | 26 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6168 | VISAR-6875, VISAR-6830, VISAR-6700 |  | 125.1 |  | Bail Schedule - Review | w_ct_m_fscl_bail_sched_maint | Medium High | Deployed | Subtask Completed | 3 | JL | MU | 2025-09-16 | 2026-02-23 | 2026-03-25 | 2026-04-08 | 2026-05-01 | 2026-04-29 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 58 | Bail Schedule |  |  |  | 18 | 8 | 26 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
| User | [5 empty] | 126 | 20 - TABLES | Calendar Plan Maintenance | w_ct_m_calendar_plan | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 48 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 127 | 20 - TABLES | Code Mover | w_ct_m_code_mover | Low High | Not Started | [24 empty] | X | 8 | 5 | 13 | 222 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6190 | VISAR-6632, VISAR-6606, VISAR-6543, VISAR-6458, VISAR-6256 |  | 128 |  | Code Entry | w_ct_m_codes | Low High | Deployed | Subtask Completed | 9 | NV | BY | 2025-09-24 | 2025-10-15 | 2025-12-18 | 2026-01-01 | 2026-01-12 |  | 2026-08-21 | 2026-02-05 | Build 5.01 | [6 empty] | 2 | 99 | Code Entry |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6450 | VISAR-7059, VISAR-7019 |  | 129 |  | CodesXref Maintenance | w_ct_m_maint_xref | Medium | Deployed | Subtask Completed | 2 | JL | BY | 2025-12-15 | 2026-05-19 | 2026-05-26 | 2026-06-09 | 2026-05-27 |  | 2026-08-21 | 2026-06-30 | Build 5.03 | [6 empty] | 0 | 11 | Codes XRef Maintenance |  |  |  | 12 | 6.5 | 18.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6274 | VISAR-6949, VISAR-6929, VISAR-6833, VISAR-6697, VISAR-6449 |  | 130 |  | Court Control | w_ct_m_mnt_control | Low High | Deployed | Subtask Completed | 5 | SM | MU | 2025-10-23 | 2025-12-15 | 2026-02-04 | 2026-02-18 | 2026-03-25 |  | 2026-08-21 | 2026-05-05 | Pre-release | [6 empty] | 0 | 46 | Court Control |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
| Internal |  | VISAR-6166 | VISAR-7388 |  |  | 130.1 | 20 - TABLES | MOCS Docket Definition | w_ct_m_mocs_dkt_defn | Medium | On Hold | On-Hold | 0 | JC |  | 2026-09-03 | [14 empty] | 0 | 0 | MOCS Docket Definition |  |  | X | 12 | 6.5 | 18.5 | 7 |  | In Development | Pipeline + Metrics | Metrics hyperlink | High
Internal | Internal | Internal | VISAR-6166 | VISAR-7311 | VISAR-7354 |  | 131 | 20 - TABLES | Court Holidays | w_ct_m_court_holidays | Low High | In QA - Dev | Subtask In-Progress | 2 | CN | BY | 2026-08-12 | 2026-08-27 | [8 empty] | 26 | 5.5 | 1 | 0 | 32.5 | 12 | 12 | Court Holidays | Y |  | X | 8 | 5 | 13 | 26 | Internal | QA Cycle 1 | Pipeline + Metrics | Metrics hyperlink | High
| User | [5 empty] | 132 | 20 - TABLES | Docket Code Macro Configuration | w_ct_m_docket_macro | Low High | Not Started | [25 empty] | 8 | 5 | 13 | 33 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 133 | 20 - TABLES | Docket Code Macro Maintenance | w_ct_m_docket_macro_maint | Medium High | Not Started | [25 empty] | 18 | 8 | 26 | 6 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 133.1 | 20 - TABLES | Docket Macro Preview | w_ct_r_dckt_macro_preview | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 134 | 20 - TABLES | Docket Code Macro Mover | w_ct_m_docket_macro_move | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 22 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 135 | 20 - TABLES | Docket Code Maintenance | w_ct_m_docket_code_maint | Medium High | Not Started | [24 empty] | X | 18 | 8 | 26 | 4097 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 135.1 | 20 - TABLES | w_ct_r_docket_codes | w_ct_r_docket_codes | Low | Not Started | [24 empty] | X | 4 | 1.5 | 5.5 | 3050 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 135.2 | 20 - TABLES | w_ct_r_lookup_nbr | w_ct_r_lookup_nbr | Low | Not Started | [24 empty] | X | 4 | 1.5 | 5.5 | 0 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 136 | 20 - TABLES | Docket Code Reference | w_ct_m_docket_codes_reference | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 22715 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6167 | VISAR-6627, VISAR-6605, VISAR-6538, VISAR-6456, VISAR-6422, VISAR-6206 |  | 137 |  | Error Code | w_ct_m_error_codes | Low | Deployed | Subtask Completed | 10 | SM | MU | 2025-09-16 | 2025-09-25 | 2025-12-18 | 2026-01-01 | 2026-02-04 |  | 2026-08-21 | 2026-02-05 | Pre-release | [6 empty] | 0 | 58 | Error Codes |  |  |  | 4 | 1.5 | 5.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6217 | VISAR-6628, VISAR-6607, VISAR-6537, VISAR-6459, VISAR-6424, VISAR-6304, VISAR-6276 |  | 138 |  | Event Codes | w_ct_m_event_codes | Low | Deployed | Subtask Completed | 9 | SM | MU | 2025-10-06 | 2025-10-23 | 2025-11-07 | 2025-11-21 | 2025-12-23 |  | 2026-08-21 | 2026-02-05 | Pre-release | [6 empty] | 0 | 43 | Event Codes |  |  |  | 4 | 1.5 | 5.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
| User | [5 empty] | 139 | 20 - TABLES | Fee Schedule | w_ct_m_fscl_fee_sched | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 45 |  |  | Pipeline |  | Unmatched
| Internal | [5 empty] | 140 | 20 - TABLES | Generic Notice Maintenance | w_ct_m_letter_maint | Low High | Not Started | [24 empty] | X | 8 | 5 | 13 | 6 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6189 | VISAR-6550, VISAR-6457, VISAR-6216 |  | 141 |  | Job Error Log | w_ct_m_job_error_log | Low | Deployed | Subtask Completed | 5 | SM | BY | 2025-09-24 | 2025-10-06 | 2025-12-18 | 2026-01-01 | 2025-12-18 |  | 2026-08-21 | 2026-02-05 | Pre-release | [6 empty] | 0 | 59 | Job Error Log |  |  |  | 4 | 1.5 | 5.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
| Internal | [5 empty] | 142 | 20 - TABLES | Letter Maintenance | w_ct_m_letter_maint_lm | Low High | Not Started | [24 empty] | X | 8 | 5 | 13 | 2 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 143 | 20 - TABLES | PA Schedule Maintenance | w_ct_m_maint_pa_sched | Low | Not Started | [25 empty] | 4 | 1.5 | 5.5 | 2 |  |  | Pipeline |  | Unmatched
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6254 | VISAR-6952, VISAR-6921, VISAR-6896, VISAR-6878, VISAR-6753, VISAR-6478 |  | 144 |  | Parm Lookups | w_ct_m_parm_lookups | Low High | Deployed | Subtask Completed | 6 | NV | BY | 2025-10-20 | 2025-12-24 | 2026-02-04 | 2026-02-18 | 2025-12-22 |  | 2026-08-21 | 2026-05-05 | Pre-release | [6 empty] | 2 | 45 | Parm Lookups |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6848 | VISAR-7161, VISAR-7029, VISAR-6976, VISAR-6897 |  | 145 |  | Sentence Workflow Maintanence | w_ct_case_sent_wkflow_mapping | Medium-High | Deployed | Subtask Completed | 4 | NV | CL | 2026-04-03 | 2026-04-21 | 2026-05-06 | 2026-05-20 | 2026-04-21 |  | 2026-08-21 | 2026-08-26 | 1.0 | [12 empty] | 18 | 8 | 26 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6316 | VISAR-7052, VISAR-7021, VISAR-7008, VISAR-6766 |  | 146 |  | SP Registry | w_ct_m_sp_registry | Low High | Deployed | Subtask Completed | 5 | NV | BY | 2025-11-18 | 2025-12-24 | 2026-01-09 | 2026-01-23 | 2025-12-24 |  | 2026-08-21 | 2026-06-30 | Pre-release2 | [6 empty] | 0 | 39 | SP Registry |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High | signedOff
Internal | Internal | Internal | VISAR-6166 | VISAR-7382 |  |  | 147 | 20 - TABLES | Unit Codes | w_ct_m_unit_codes | Medium | Backlog | Backlog | 0 | SM | CL | 2026-09-03 | [14 empty] | 0 | 0 | Unit Codes | Y |  | X | 12 | 6.5 | 18.5 | 169 | Internal | Backlog | Pipeline + Metrics | Metrics hyperlink | High
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6544 | VISAR-7187, VISAR-7168, VISAR-6832 |  | 148 |  | Violation Agency X-Ref | w_ct_m_viol_agency_xref | Low High | Deployed | Subtask Completed | 3 | NV | MU | 2026-01-12 | 2026-03-25 | 2026-06-18 | 2026-07-02 | 2026-07-16 | 2026-07-22 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 15 | Violation Agency XRef |  |  |  | 8 | 5 | 13 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
Pre-Sprint | User | Pre-Sprint | VISAR-6166 | VISAR-6474 | VISAR-7202, VISAR-7196, VISAR-7186, VISAR-7156, VISAR-6954, VISAR-6951 |  | 149 |  | Violations | w_ct_m_violations | Medium | Deployed | Subtask Completed | 5 | NV | MU | 2025-12-24 | 2026-01-12 | 2026-01-12 | 2026-01-26 | 2026-06-30 | 2026-07-22 | 2026-08-21 | 2026-08-26 | 1.0 | [6 empty] | 0 | 32 | Violations |  |  |  | 12 | 6.5 | 18.5 |  |  | Deployed to Production | Metrics only | Metrics hyperlink | High
SG6 | User | SG6 | VISAR-6166 | VISAR-7574 |  |  | 150 | 21 - WARRANTS | Pending Warrant Review | w_ct_m_warrant_review | Medium | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Pending Warrant Review |  | Y |  | 12 | 6.5 | 18.5 | 791 |  |  | Pipeline | Object name match | Medium
SG6 | User | SG6 | VISAR-6166 | VISAR-7575 |  |  | 151 | 21 - WARRANTS | Warrant Image Viewer | w_ct_m_warrant_images | Low High | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Warrant Image Viewer |  | Y |  | 8 | 5 | 13 | 1440 |  |  | Pipeline | Object name match | Medium
SG6 | User | SG6 | VISAR-6166 | VISAR-7576 |  |  | 152 | 21 - WARRANTS | Warrant Maintenance | w_ct_m_warrant_signal_mon | Medium | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Warrant Maintenance |  | Y |  | 12 | 6.5 | 18.5 | 961 |  |  | Pipeline | Object name match | Medium
SG7 | Internal | SG7 Internal | VISAR-6166 | VISAR-7577 |  |  | 153 | 21 - WARRANTS | Warrant Maintenance (CTS) (Warrant Signal Audit) | w_ct_m_warrant_signal_audit | Medium | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Warrant Maintenance (CTS) (Warrant Signal Audit) |  | Y | X | 12 | 6.5 | 18.5 | 45 |  |  | Pipeline | Object name match | Medium
SG7 | User | SG7 | VISAR-6166 | VISAR-7578 |  |  | 154 | 21 - WARRANTS | Warrant Reports | w_ct_r_main_report | Medium | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Warrant Reports |  | Y |  | 12 | 6.5 | 18.5 | 335 |  |  | Pipeline | Object name match | Medium
SG7 | Internal | SG7 Internal | VISAR-6166 | VISAR-7579 |  |  | 155 | 21 - WARRANTS | Warrant XML Viewer (CTS) | w_ct_m_warrant_awss_xml | Low High | In Sprint Planning | Subtask Created | 0 | [17 empty] | 0 | 0 | Warrant XML Viewer (CTS) |  | Y | X | 8 | 5 | 13 | 2 |  |  | Pipeline | Object name match | Medium
| User | [5 empty] | 156 | GENERAL | Log on Window (initial loading of config items) |  | Medium High | Not Started | [25 empty] | 18 | 8 | 26 |  |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 157 | GENERAL | Menu Actions |  | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 |  |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 158 | GENERAL | Case Search (Adv Search) | w_ct_r_case_search | Medium High | Not Started | [19 empty] | 23 | 23 | Case Search |  |  |  | 18 | 8 | 26 | 148370 |  |  | Pipeline |  | Unmatched
| User | [5 empty] | 159 | GENERAL | Simple Case Search | w_ct_r_simple_search | Medium | Not Started | [25 empty] | 12 | 6.5 | 18.5 | 2000956 |  |  | Pipeline |  | Unmatched
Patch | Patch | Patch | VISAR-7396 | VISAR-7428 |  |  |  |  | Bail Schedule Watermark |  |  | Deployed | Subtask Completed | 0 |  |  | 2026-09-15 | [17 empty] | Y | [8 empty] | VISAR-7396 (Patch) | Direct | High
Patch | Patch | Patch | VISAR-7396 | VISAR-7397 |  |  |  |  | Code Entries |  |  | Deployed | Subtask Completed | 0 |  |  | 2026-09-09 | [17 empty] | Y | [8 empty] | VISAR-7396 (Patch) | Direct | High

## Crosswalk
W# | Window Name | Object Name | Dev Subtask | Jira Title | Match Method | Confidence | Related QA Subtasks
1 | Auto Process Schedule | w_ct_m_mnt_auto_process_sched | VISAR-7312 | Internal - Auto Process Schedule - w_ct_m_mnt_auto_process_sched | Metrics hyperlink | High | VISAR-7469, VISAR-7349
2 | Date of Action Maintenance | w_ct_m_docket_date_of_action_maint | VISAR-7332 | Internal - Date of Action Maintenance - w_ct_m_docket_date_of_action_maint | Metrics hyperlink | High | VISAR-7429, VISAR-7407
4 | Officer Consolidate | w_ct_m_officer_merge | VISAR-7333 | Officer Consolidate - w_ct_m_officer_merge | Metrics hyperlink | High
6 | Purge Duplicates | w_ct_m_purge_duplicate | VISAR-6499 | Purge Duplicate Cases - w_ct_m_purge_duplicate | Metrics hyperlink | High | VISAR-6881, VISAR-6640
8 | Calendar List | w_ct_m_cal_list | VISAR-7419 | SG2 - Calendar List - w_ct_m_cal_list | Metrics hyperlink | High
8.1 | Post-Conviction Worksheet Report | w_ct_r_pcw | VISAR-7420 | SG2 - Post-Conviction Worksheet Report - w_ct_r_pcw | Metrics hyperlink | High
9 | Calendar Report | w_ct_m_cal_report_list | VISAR-7421 | SG2 - Calendar Report - w_ct_m_cal_report_list | Metrics hyperlink | High | VISAR-7551, VISAR-7518, VISAR-7491
9.1 | Calendar Batch Print | w_ct_r_batch_print | VISAR-7422 | SG2 - Calendar Batch Print - w_ct_r_batch_print | Metrics hyperlink | High | VISAR-7560, VISAR-7559, VISAR-7550, VISAR-7519, VISAR-7490
9.2 | Web Browser of generated files | w_ct_r_pdf_viewer | VISAR-7423 | SG2 - Web Browser of Generated Files - w_ct_r_pdf_viewer | Metrics hyperlink | High | VISAR-7493
10 | Calendar Transfer | w_ct_m_cal_transfer | VISAR-7401 | SG2 - Calendar Transfer - w_ct_m_cal_transfer | Object name match | Medium | VISAR-7483, VISAR-7479, VISAR-7436
11 | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | VISAR-7424 | SG2 - EXCLUDED - Calendar Transfer Notices - w_ct_m_cal_transfer_notice | Manual - canceled window | High
12 | Court Closure Transfer | w_ct_m_cal_close_transfer | VISAR-7425 | SG2 - EXCLUDED - Court Closure Transfer - w_ct_m_cal_close_transfer | Manual - canceled window | High
13 | Court Trial Transfer | w_ct_m_cal_transfer_location | VISAR-7426 | SG2 - Court Trial Transfer - w_ct_m_cal_transfer_location | Object name match | Medium | VISAR-7509, VISAR-7499, VISAR-7472
14 | Notice of Packaged Hearings | w_ct_m_case_package_list | VISAR-7427 | SG2 - Notice of Packaged Hearings - w_ct_m_case_package_list | Object name match | Medium | VISAR-7513
17 | Case Summary | w_ct_m_case_summary | VISAR-7557 | Case Summary - w_ct_m_case_summary | Object name match | Medium
17.1 | Close Elig? Button | w_ct_r_case_closure_eligible | VISAR-7580 | SG5 - Close Elig? Button - w_ct_r_case_closure_eligible | Object name match | Medium
17.2 | Bail Schedule Maintenance Response | w_ct_r_fscl_bail_sched_maint_response | VISAR-7563 | SG5 - Bail Schedule Maintenance Response - w_ct_r_fscl_bail_sched_maint_response | Object name match | Medium
25 | Priors | w_ct_m_case_priors | VISAR-7012 | Priors - w_ct_m_case_priors | Metrics hyperlink | High | VISAR-7384, VISAR-7314, VISAR-7178
25.1 | Print - Copies Spec. | w_ct_m_case_priors_print_spec | VISAR-7012 | Priors - w_ct_m_case_priors | Manual - bundled subtask | High
33 | FTBCOD Interface | w_ct_m_case_ftbcod_select | VISAR-6907 | FTBCOD Interface - w_ct_m_case_ftbcod_select | Metrics hyperlink | High
51 | Courtroom Setup | w_ct_m_ctrs_courtroom_setup | VISAR-6475 | Courtroom Setup - w_ct_m_ctrs_courtroom_setup | Metrics hyperlink | High | VISAR-6993, VISAR-6928, VISAR-6898, VISAR-6879, VISAR-6497
53 | Minutes | w_ct_m_docket_reporting | VISAR-6315 | Minutes - w_ct_m_docket_reporting | Manual - bundled subtask | High | VISAR-7435, VISAR-7410, VISAR-7378, VISAR-7205, VISAR-7195
53.3 | VCJIS - Court Reports Preview | w_ct_r_dckt_preview_docket_rpt | VISAR-6315 | Minutes - w_ct_m_docket_reporting | Manual - bundled subtask | High
55 | Exhibit List | w_ct_m_exhibit_list | VISAR-7188 | Exhibit List - w_ct_m_exhibit_list | Metrics hyperlink | High | VISAR-7390, VISAR-7366, VISAR-7289, VISAR-7288
55.1 | Exhibit Search | w_ct_r_exhibit_list_case_search | VISAR-7188 | Exhibit List - w_ct_m_exhibit_list | Metrics hyperlink | High
56 | Exhibit Maintenance | w_ct_m_exhibit_maintenance | VISAR-7189 | Exhibit Maintenance - w_ct_m_exhibit_maintenance | Metrics hyperlink | High | VISAR-7408, VISAR-7330
56.1 | New Exhibit Hearing List | w_ct_m_exhibit_new_hearing | VISAR-7189 | Exhibit Maintenance - w_ct_m_exhibit_maintenance | Metrics hyperlink | High
57 | Exhibit Management | w_ct_m_exhibit_management | VISAR-7185 | SG1 - Exhibit Management - w_ct_m_exhibit_management | Metrics hyperlink | High | VISAR-7409, VISAR-7391
57.1 | Exhibit Management Search | w_ct_m_exhibit_management_srch | VISAR-7206 | Exhibit Management Search - w_ct_m_exhibit_management_srch | Metrics hyperlink | High | VISAR-7392
57.2 | Exhibit History | w_ct_r_exhibit_history | VISAR-7206 | Exhibit Management Search - w_ct_m_exhibit_management_srch | Metrics hyperlink | High
57.3 | Exhibit Disposition Notice | w_ct_m_exhibit_management_srch | VISAR-7206 | Exhibit Management Search - w_ct_m_exhibit_management_srch | Metrics hyperlink | High | VISAR-7392
60 | Case Payment History | w_ct_m_fscl_payment_hist | VISAR-6797 | Case Payment History - w_ct_m_fscl_payment_hist | Metrics hyperlink | High | VISAR-7096, VISAR-7073, VISAR-7022, VISAR-7007, VISAR-6987, VISAR-6874
72 | Chart of Accounts | w_ct_m_fscl_chart_of_accts | VISAR-7564 | SG6 - Chart of Accounts - w_ct_m_fscl_chart_of_accts | Object name match | Medium
73 | Cost of Collections | w_ct_m_fscl_cost_of_collections | VISAR-7544 | Cost of Collections - w_ct_m_fscl_cost_of_collections | Object name match | Medium | VISAR-7554
74 | Fee Distribution Schedule | w_ct_m_fscl_fee_dist_sched | VISAR-7565 | SG7 - Fee Distribution Schedule - w_ct_m_fscl_fee_dist_sched | Object name match | Medium
75 | Fund Maintenance | w_ct_m_fscl_fund_maint | VISAR-7566 | SG7 - Fund Maintenance - w_ct_m_fscl_fund_maint | Object name match | Medium
77 | PA Distribution Xref | w_ct_m_fscl_dist_xref | VISAR-7567 | SG6 - PA Distribution Xref - w_ct_m_fscl_dist_xref | Object name match | Medium
90 | JBSIS Maintenance | w_jbsis_maintenance | VISAR-7215 | SG1 - JBSIS Maintenance - w_jbsis_maintenance | Metrics hyperlink | High | VISAR-7385, VISAR-7319
93 | Attorney Maintenance | w_ct_m_attorney | VISAR-7568 | SG8 - Attorney Maintenance - w_ct_m_attorney | Object name match | Medium
94 | Interpreters Maintenance | w_ct_m_interpreters | VISAR-7569 | SG8 - Interpreters Maintenance - w_ct_m_interpreters | Object name match | Medium
94.1 | Interpreters in System | w_ct_r_interpreters_lookup | VISAR-7570 | SG8 - Interpreters in System - w_ct_r_interpreters_lookup | Object name match | Medium
94.2 | Interpreter Remarks(Ctrl+Alt+T under Remarks) | w_ct_r_interpreter_remarks | VISAR-7571 | SG8 - Interpreter Remarks(Ctrl+Alt+T under Remarks) - w_ct_r_interpreter_remarks | Object name match | Medium
95 | Multi-Person Maintenance | w_ct_m_multi_person_maint | VISAR-7572 | SG8 - Multi-Person Maintenance - w_ct_m_multi_person_maint | Object name match | Medium
95.1 | Multi-Person Maintenance Datafix Report | w_ct_r_mpm_report | VISAR-7573 | SG8 - Multi-Person Maintenance Datafix Report - w_ct_r_mpm_report | Object name match | Medium
102 | Batch Purge | w_ct_m_purged_cases | VISAR-7443 | SG3 - Batch Purge - w_ct_m_purged_cases | Object name match | Medium
103 | Calendar File Location | w_ct_s_rcds_cal_loc | VISAR-7444 | SG3 - Calendar File Location - w_ct_s_rcds_cal_loc | Object name match | Medium | VISAR-7547
104 | Case File Purge | w_ct_m_case_file_purge | VISAR-7445 | SG3 - Case File Purge - w_ct_m_case_file_purge | Object name match | Medium | VISAR-7561, VISAR-7549
105 | File Location | w_ct_s_rcds_location | VISAR-7446 | SG4 - File Location - w_ct_s_rcds_location | Object name match | Medium
105.1 | Location History | w_ct_s_rcds_location_history | VISAR-7447 | SG4 - Location History - w_ct_s_rcds_location_history | Object name match | Medium | VISAR-7546
106 | File Request | w_ct_s_rcds_request | VISAR-7448 | SG4 - File Request - w_ct_s_rcds_request | Object name match | Medium
107 | File Request Inquiry | w_ct_s_rcds_request_inquiry | VISAR-7449 | SG4 - File Request Inquiry - w_ct_s_rcds_request_inquiry | Object name match | Medium
108 | File Request Maintenance | w_ct_s_rcds_request_maint | VISAR-7450 | SG4 - File Request Maintenance - w_ct_s_rcds_request_maint | Object name match | Medium
109 | Image Maintenance | w_ct_m_case_docket_image | VISAR-7451 | SG4 - Image Maintenance - w_ct_m_case_docket_image | Object name match | Medium
109.1 | Docket Code Lookup | w_ct_r_case_docket | VISAR-7452 | SG4 - Docket Code Lookup - w_ct_r_case_docket | Object name match | Medium
110 | Image Viewer | w_ct_m_image_viewer | VISAR-7453 | SG4 - Image Viewer - w_ct_m_image_viewer | Object name match | Medium
111 | Missing Complaints Purge | w_ct_m_missing_complaints_purge | VISAR-7454 | SG3 - Missing Complaints Purge - w_ct_m_missing_complaints_purge | Object name match | Medium
122 | Unlock Case | w_ct_m_case_lock_maintenance | VISAR-6895 | Unlock Case - w_ct_m_case_lock_maintenance | Metrics hyperlink | High | VISAR-7051, VISAR-6920
123 | Agency Codes | w_ct_m_agency_codes | VISAR-7368 | Internal - Agency Codes - w_ct_m_agency_codes | Metrics hyperlink | High
124 | Agency X-Ref Maintenance | w_ct_m_maint_agy_xref | VISAR-7296 | Internal - Agency X-Ref Maintenance - w_ct_m_maint_agy_xref | Metrics hyperlink | High | VISAR-7548, VISAR-7379, VISAR-7365, VISAR-7318
125 | Bail Schedule | w_ct_m_fscl_bail_sched_maint | VISAR-6168 | Bail Schedule Maintenance window - w_ct_m_fscl_bail_sched_maint | Metrics hyperlink | High | VISAR-6875, VISAR-6830, VISAR-6700
125.1 | Bail Schedule - Review | w_ct_m_fscl_bail_sched_maint | VISAR-6168 | Bail Schedule Maintenance window - w_ct_m_fscl_bail_sched_maint | Metrics hyperlink | High | VISAR-6875, VISAR-6830, VISAR-6700
128 | Code Entry | w_ct_m_codes | VISAR-6190 | Code Entry Table window - w_ct_m_codes | Metrics hyperlink | High | VISAR-6632, VISAR-6606, VISAR-6543, VISAR-6458, VISAR-6256
129 | CodesXref Maintenance | w_ct_m_maint_xref | VISAR-6450 | Codes X-Ref Maintenance window - w_ct_m_maint_xref | Metrics hyperlink | High | VISAR-7059, VISAR-7019
130 | Court Control | w_ct_m_mnt_control | VISAR-6274 | Court Control window - w_ct_m_mnt_control | Metrics hyperlink | High | VISAR-6949, VISAR-6929, VISAR-6833, VISAR-6697, VISAR-6449
130.1 | MOCS Docket Definition | w_ct_m_mocs_dkt_defn | VISAR-7388 | MOCS Docket Definition - w_ct_m_mocs_dkt_defn | Metrics hyperlink | High
131 | Court Holidays | w_ct_m_court_holidays | VISAR-7311 | Internal - Court Holidays - w_ct_m_court_holidays | Metrics hyperlink | High | VISAR-7354
137 | Error Code | w_ct_m_error_codes | VISAR-6167 | Error codes window - w_ct_m_error_codes | Metrics hyperlink | High | VISAR-6627, VISAR-6605, VISAR-6538, VISAR-6456, VISAR-6422, VISAR-6206
138 | Event Codes | w_ct_m_event_codes | VISAR-6217 | Event Codes - w_ct_m_event_codes | Metrics hyperlink | High | VISAR-6628, VISAR-6607, VISAR-6537, VISAR-6459, VISAR-6424, VISAR-6304, VISAR-6276
141 | Job Error Log | w_ct_m_job_error_log | VISAR-6189 | Job Error Log window - w_ct_m_job_error_log | Metrics hyperlink | High | VISAR-6550, VISAR-6457, VISAR-6216
144 | Parm Lookups | w_ct_m_parm_lookups | VISAR-6254 | Parm Lookups - w_ct_m_parm_lookups | Metrics hyperlink | High | VISAR-6952, VISAR-6921, VISAR-6896, VISAR-6878, VISAR-6753, VISAR-6478
145 | Sentence Workflow Maintanence | w_ct_case_sent_wkflow_mapping | VISAR-6848 | Sentence Workflow Maintenance - w_ct_case_sent_wkflow_mapping | Metrics hyperlink | High | VISAR-7161, VISAR-7029, VISAR-6976, VISAR-6897
146 | SP Registry | w_ct_m_sp_registry | VISAR-6316 | SP Registry - w_ct_m_sp_registry | Metrics hyperlink | High | VISAR-7052, VISAR-7021, VISAR-7008, VISAR-6766
147 | Unit Codes | w_ct_m_unit_codes | VISAR-7382 | Internal - Unit Codes - w_ct_m_unit_codes | Metrics hyperlink | High
148 | Violation Agency X-Ref | w_ct_m_viol_agency_xref | VISAR-6544 | Violation Agency X-Ref - w_ct_m_viol_agency_xref | Metrics hyperlink | High | VISAR-7187, VISAR-7168, VISAR-6832
149 | Violations | w_ct_m_violations | VISAR-6474 | Violations - w_ct_m_violations | Metrics hyperlink | High | VISAR-7202, VISAR-7196, VISAR-7186, VISAR-7156, VISAR-6954, VISAR-6951
150 | Pending Warrant Review | w_ct_m_warrant_review | VISAR-7574 | SG6 - Pending Warrant Review - w_ct_m_warrant_review | Object name match | Medium
151 | Warrant Image Viewer | w_ct_m_warrant_images | VISAR-7575 | SG6 - Warrant Image Viewer - w_ct_m_warrant_images | Object name match | Medium
152 | Warrant Maintenance | w_ct_m_warrant_signal_mon | VISAR-7576 | SG6 - Warrant Maintenance - w_ct_m_warrant_signal_mon | Object name match | Medium
153 | Warrant Maintenance (CTS) (Warrant Signal Audit) | w_ct_m_warrant_signal_audit | VISAR-7577 | SG7 - Warrant Maintenance (CTS) (Warrant Signal Audit) - w_ct_m_warrant_signal_audit | Object name match | Medium
154 | Warrant Reports | w_ct_r_main_report | VISAR-7578 | SG7 - Warrant Reports - w_ct_r_main_report | Object name match | Medium
155 | Warrant XML Viewer (CTS) | w_ct_m_warrant_awss_xml | VISAR-7579 | SG7 - Warrant XML Viewer (CTS) - w_ct_m_warrant_awss_xml | Object name match | Medium

## Reconciliation
W# | Window Name | Subtask | Issue | Derived | Your Record | Action
1 | Auto Process Schedule | VISAR-7312 | Reached QA but no 2 Week Start trigger | (blank) | 2026-08-26 | Enter 2 Week Start manually
2 | Date of Action Maintenance | VISAR-7332 | In/through UAT but no UAT Start date | 2026-09-16 |  | Enter UAT Start manually
6 | Purge Duplicates | VISAR-6499 | In/through UAT but no UAT Start date | 2026-05-01 |  | Enter UAT Start manually
9 | Calendar Report | VISAR-7421 | Derived status differs from Pipeline col G | In UAT | 2-Week | Confirm correct status
9 | Calendar Report | VISAR-7421 | In/through UAT but no UAT Start date | 2026-10-23 |  | Enter UAT Start manually
9.1 | Calendar Batch Print | VISAR-7422 | Derived status differs from Pipeline col G | In UAT | 2-Week | Confirm correct status
9.1 | Calendar Batch Print | VISAR-7422 | In/through UAT but no UAT Start date | 2026-10-23 |  | Enter UAT Start manually
9.2 | Web Browser of generated files | VISAR-7423 | Derived status differs from Pipeline col G | Deployed | 2-Week | Confirm correct status
9.2 | Web Browser of generated files | VISAR-7423 | Deployed but no Deployed date | (no build) |  | Enter Deployed date
10 | Calendar Transfer | VISAR-7401 | Derived status differs from Pipeline col G | In UAT | 1-Week | Confirm correct status
13 | Court Trial Transfer | VISAR-7426 | Derived status differs from Pipeline col G | In UAT | 1-Week | Confirm correct status
56 | Exhibit Maintenance | VISAR-7189 | In/through UAT but no UAT Start date | 2026-09-17 |  | Enter UAT Start manually
56.1 | New Exhibit Hearing List | VISAR-7189 | In/through UAT but no UAT Start date | 2026-09-17 |  | Enter UAT Start manually
57 | Exhibit Management | VISAR-7185 | In/through UAT but no UAT Start date | 2026-09-14 |  | Enter UAT Start manually
57.1 | Exhibit Management Search | VISAR-7206 | In/through UAT but no UAT Start date | 2026-09-15 |  | Enter UAT Start manually
57.2 | Exhibit History | VISAR-7206 | In/through UAT but no UAT Start date | 2026-09-15 |  | Enter UAT Start manually
57.3 | Exhibit Disposition Notice | VISAR-7206 | In/through UAT but no UAT Start date | 2026-09-15 |  | Enter UAT Start manually
73 | Cost of Collections | VISAR-7544 | Reached QA but no 2 Week Start trigger | (blank) | 2026-10-21 | Enter 2 Week Start manually
103 | Calendar File Location | VISAR-7444 | Reached QA but no 2 Week Start trigger | (blank) | 2026-10-20 | Enter 2 Week Start manually
105.1 | Location History | VISAR-7447 | Reached QA but no 2 Week Start trigger | (blank) | 2026-10-20 | Enter 2 Week Start manually
123 | Agency Codes | VISAR-7368 | Derived status differs from Pipeline col G | On Hold | Internal | Confirm correct status
124 | Agency X-Ref Maintenance | VISAR-7296 | Reached QA but no 2 Week Start trigger | (blank) | 2026-08-13 | Enter 2 Week Start manually
128 | Code Entry | VISAR-6190 | In/through UAT but no UAT Start date | 2026-01-12 |  | Enter UAT Start manually
129 | CodesXref Maintenance | VISAR-6450 | In/through UAT but no UAT Start date | 2026-05-27 |  | Enter UAT Start manually
130 | Court Control | VISAR-6274 | In/through UAT but no UAT Start date | 2026-03-25 |  | Enter UAT Start manually
131 | Court Holidays | VISAR-7311 | Reached QA but no 2 Week Start trigger | (blank) | 2026-08-27 | Enter 2 Week Start manually
137 | Error Code | VISAR-6167 | In/through UAT but no UAT Start date | 2026-02-04 |  | Enter UAT Start manually
138 | Event Codes | VISAR-6217 | In/through UAT but no UAT Start date | 2025-12-23 |  | Enter UAT Start manually
141 | Job Error Log | VISAR-6189 | In/through UAT but no UAT Start date | 2025-12-18 |  | Enter UAT Start manually
144 | Parm Lookups | VISAR-6254 | In/through UAT but no UAT Start date | 2025-12-22 |  | Enter UAT Start manually
145 | Sentence Workflow Maintanence | VISAR-6848 | In/through UAT but no UAT Start date | 2026-04-21 |  | Enter UAT Start manually
146 | SP Registry | VISAR-6316 | In/through UAT but no UAT Start date | 2025-12-24 |  | Enter UAT Start manually
147 | Unit Codes | VISAR-7382 | Derived status differs from Pipeline col G | Backlog | Internal | Confirm correct status

## Excluded Subtasks
Subtask | Title | Jira Status | Reason
VISAR-7358 | Test Subtask | Subtask Completed | Test artifact - not a window
VISAR-7127 | POWER BUILDER - VisionNG Minutes PDF - Merge with Powerbuilder CIS, OtherCases, or Standalone | Subtask Completed | Project admin task - not a window
VISAR-6749 | Vision NG - Inventory of OpenWithParm Windows | Subtask Completed | Project admin task - not a window
VISAR-6663 | Vision NG - Menu Security Error | Subtask Completed | Project admin task - not a window
VISAR-6205 | VisionNG Window Migration - Master | Subtask In-Progress | Project admin task - not a window
VISAR-7414 | Dev - Calendar List - (2 windows) | Canceled | Superseded by per-window subtasks

## Field Notes
Field | Derivation
Status | Dashboard status derived from the DEV subtask. Subtask Completed = Deployed; In QA = In QA - BSA; work statuses after QA = In QA - Dev; before QA = In Development.
(status mapping) | In Unit Test, In Progress w/Users and In Progress w/Vision are all treated as development.
Sprint # | What the window DEPLOYS WITH: SG1, SG2, ... for sprint-bound work; Internal for a standalone internal window; Patch; TBD when planned but the group is undecided; blank when not yet planned. This is the deployment grouping key - a build for SG1 is every row where Sprint # = SG1, both tracks.
Track | What PROCESS the window follows: User, Internal or Patch. Set from Pipeline col H (X = Internal) and confirmed at Planning. Only Track = User runs the two-week UAT countdown and the UAT workflow.
Group Label | Computed display string only - never edit. SG1 + Internal shows as "SG1 Internal"; a standalone internal window shows as "Internal".
Subtask | The DEV subtask. QA-cycle duplicates are listed in Related QA Subtasks.
QA Cycle | Metrics col U for pre-process windows (Metrics rows 2-40); count of transitions into In QA for all others.
Date Started | First transition into Subtask In-Progress.
To QA | First transition into In QA.
2 Week Start | First transition OUT of In QA to any status. Blank = clock never triggered. Not set for Internal (No UAT) windows.
Target Date | 2 Week Start + 14 calendar days. Always blank when Track is not User - those windows deploy with their sprint instead of against a date.
To UAT | First transition into In UAT.
UAT Start | Metrics col Z, plus the dashboard Sent to UAT section (Actual UAT Start date). Blank = UAT not started.
Deployed | Metrics col AC (Deploy Date).
Signed Off | No source yet - manual entry until the PDC comment workflow starts.
UAT Subtask | The UAT fix subtask (UAT - SG# - Window - object), created by uatinit.js when the UAT Defect Log has defects at Fix In-Progress. The open one if any, otherwise the most recent. One per dev subtask.
Development / QA Test / Mitigation / UAT | Hours from the Hours Log table in the Jira descriptions, since 2026-09-23 (the Metrics sheet is no longer used). The column an entry is typed in decides the bucket. A window adds up its dev subtask, its UAT subtask(s) and their QA copies; rows a QA copy inherited from the dev subtask are not counted twice. Re-read every refresh, so an edited entry changes the total. Shown once on decimal rows sharing a subtask.
Total Hours | Development + QA Test + Mitigation + UAT.
Open / Total Defects | DEFECTS sheet of the matched log. Open = New, Return to Dev / Returned to Dev, Retest In Progress.
Dev/QA/Total LOE, Total Usage | Pipeline columns Dev LOE, QA LOE, Total LOE, Total Usage (found by header) - original estimates in days and 1-year usage count. Reference only.
Legacy Status | Pipeline col G - your previous manual status, kept for cross-check.
Overridden | Fields pinned by hand that beat the Jira-derived value. The refresh skill must never overwrite a field named here.
Source | Pipeline = present in Pipeline sheet; Metrics only = completed window removed from Pipeline.