## Pipeline with LOE
Priority # | ID | SG | MENU | SUB-MENU | OBJECT NAME | GROUPING | STATUS | No UAT (CTS Only) | Grouped DEV LOE | OPS | FIS | COL | ETA to UAT | COMMENTS | Dev LOE | QA LOE | Total LOE | Total Usage | bailschedule | collections | collectionssu | courtroom | courtroomsu | ct_developer | ct_user | eus | fiscal1 | fiscal2 | fiscalsu | impact | inquiry | interpreter | jbsissu | judges | noncourtroom | noncourtroomsu
1 | 25 |  | 4 - CASE | Priors | w_ct_m_case_priors | High | Deployed |  |  | R - CP | I | C |  |  | 21 | 10 | 31 | 452623 | 0 | 21282 | 12632 | 46525 | 1145 | 72 | 0 | 0 | 0 | 0 | 0 | 3167 | 0 | 1284 | 1 | 0 | 344843 | 21672
2 | 25.1 |  | 4 - CASE | Print - Copies Spec. | w_ct_m_case_priors_print_spec | Low | Deployed |  |  | R - CP | I | I |  |  | 4 | 1.5 | 5.5 | 7717 | 0 | 10 | 8 | 6692 | 75 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 139 | 0 | 0 | 783 | 0
3 | 90 |  | 13 - JBSIS | JBSIS Maintenance | w_jbsis_maintenance | Medium | Deployed |  |  | R - IM | I | I |  |  | 12 | 6.5 | 18.5 | 3177 | 0 | 0 | 0 | 0 | 4 | 74 | 0 | 0 | 0 | 0 | 0 | 2449 | 0 | 0 | 135 | 0 | 0 | 515
4 | 2 |  | 1 - ADMIN | Date of Action Maintenance | w_ct_m_docket_date_of_action_maint | Low | Deployed | X | [6 empty] | 4 | 1.5 | 5.5 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 55 |  | 9 - EXHIBITS | Exhibit List | w_ct_m_exhibit_list | Low High | Deployed |  |  | R - CT | I | I |  |  | 8 | 5 | 13 | 6712 | 0 | 7 | 1 | 6222 | 140 | 24 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 2 | 0 | 0 | 286 | 12
6 | 55.1 |  | 9 - EXHIBITS | Exhibit Search | w_ct_r_exhibit_list_case_search | Low | Deployed |  |  | R - CT | I | I |  |  | 4 | 1.5 | 5.5 | 7131 | 0 | 7 | 1 | 6631 | 148 | 27 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 2 | 0 | 0 | 285 | 12
7 | 56 |  | 9 - EXHIBITS | Exhibit Maintenance | w_ct_m_exhibit_maintenance | Low High | Deployed | X | [6 empty] | 8 | 5 | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 56.1 |  | 9 - EXHIBITS | New Exhibit Hearing List | w_ct_m_exhibit_new_hearing | Low High | Deployed | X | [6 empty] | 8 | 5 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 57 |  | 9 - EXHIBITS | Exhibit Management | w_ct_m_exhibit_management | Low | Deployed | X | [6 empty] | 4 | 1.5 | 5.5 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 57.1 |  | 9 - EXHIBITS | Exhibit Management Search | w_ct_m_exhibit_management_srch |  | Deployed | X | [9 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 57.2 |  | 9 - EXHIBITS | Exhibit History | w_ct_r_exhibit_history |  | Deployed |  |  | R - CT | I | I | [5 empty] | 9 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 53 |  | 8 - COURTROOM | Minutes | w_ct_m_docket_reporting | Medium High | In UAT |  |  | R - CT | C | R |  |  | 18 | 8 | 26 | 1882930 | 29 | 209940 | 126322 | 380608 | 30035 | 2244 | 144 | 0 | 55790 | 16044 | 24541 | 32769 | 1904 | 15414 | 1336 | 38 | 918799 | 66973
13 | 53.3 |  | 8 - COURTROOM | VCJIS - Court Reports Preview | w_ct_r_dckt_preview_docket_rpt | Low High | In UAT |  |  | R - CT | I | C |  |  | 8 | 5 | 13 | 149 | 0 | 10 | 0 | 56 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 76 | 1
14 | 10 |  | 3 - CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | 1-Week |  |  | R - CT | I | I |  |  | 8 | 5 | 13 | 8014 | 0 | 37 | 8 | 6506 | 79 | 10 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 4 | 0 | 0 | 1324 | 14
15 | 13 |  | 3 - CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | 1-Week |  |  | R - CT | I | I |  |  | 12 | 6.5 | 18.5 | 243 | 0 | 1 | 1 | 168 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 10 | 0 | 0 | 55 | 0
16 | 9 |  | 3 - CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | 2-Week |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 13643 | 0 | 20 | 17 | 5872 | 60 | 19 | 0 | 0 | 0 | 0 | 0 | 141 | 73 | 689 | 0 | 4 | 6514 | 234
17 | 9.1 |  | 3 - CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | 2-Week |  |  | R - CP | I | I |  |  | 18 | 8 | 26 | 21740 | 0 | 14 | 0 | 6166 | 14 | 16 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 1295 | 0 | 0 | 14216 | 8
18 | 9.2 |  | 3 - CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | 2-Week |  |  | R - CP | I | I |  | rearragned 9.3 dependency w_ct_c_pdf_viewer | 8 | 5 | 13 | 21221 | 0 | 7 | 0 | 5892 | 11 | 13 | 0 | 0 | 354 | 1 | 15 | 7 | 0 | 1212 | 0 | 0 | 13701 | 8
19 | 9.3 |  | 8 - COURTROOM | PDF Viewer from Minutes | w_ct_c_pdf_viewer | Low High | 2-Week |  |  | R - CT | C | R |  |  | 8 | 5 | 13 | 803806 | 42 | 42861 | 21252 | 107110 | 12140 | 679 | 16 | 0 | 38253 | 4824 | 8675 | 18001 | 333 | 2988 | 397 | 3 | 514880 | 31352
20 | 14 |  | 3 - CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | In Development |  |  | R - CT | I | I |  |  | 8 | 5 | 13 | 258 | 0 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 250 | 0
21 | 8 |  | 3 - CALENDARING | Calendar List | w_ct_m_cal_list | Medium | In Development |  |  | R - CT | I | I |  |  | 12 | 6.5 | 18.5 | 73912 | 0 | 908 | 551 | 66145 | 5070 | 43 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | 0 | 1 | 0 | 125 | 42
22 | 8.1 |  | 3 - CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | In Development |  |  | R - CT | I | I |  |  | 12 | 6.5 | 18.5 | 1353 | 0 | 0 | 0 | 1341 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
23 | 103 | SG3 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium | In Development |  | 48 | R - CP | I | I | 2026-11-02 |  | 12 | 6.5 | 18.5 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 458 | 0
24 | 104 | SG3 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium | In Development |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 140 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 84 | 46
25 | 102 | SG3 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium |  |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 74 | 48
26 | 111 | SG3 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 105 | SG4 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High |  |  | 48 | R - CP | I | I | 2026-11-23 |  | 8 | 5 | 13 | 6575 | 0 | 159 | 205 | 806 | 75 | 1 | 0 | 0 | 4 | 4 | 4 | 73 | 96 | 1 | 0 | 0 | 4945 | 202
28 | 105.1 | SG4 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low |  |  |  | R - CP | I | I |  |  | 4 | 1.5 | 5.5 | 641 | 0 | 5 | 3 | 60 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 462 | 79
29 | 106 | SG4 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High |  |  |  | R - CP | I | I |  |  | 8 | 5 | 13 | 3406 | 2 | 48 | 227 | 554 | 36 | 0 | 0 | 0 | 100 | 44 | 21 | 66 | 0 | 11 | 4 | 0 | 2221 | 72
30 | 107 | SG4 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low |  |  |  | R - CP | I | I |  | 9/15 MU: pending RF response on window usage | 4 | 1.5 | 5.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
31 | 108 | SG4 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High |  |  |  | R - CP | I | I |  | 9/15 MU: pending RF response on window usage | 8 | 5 | 13 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
32 | 109 | SG4 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium |  |  |  | R - CP | C | C |  |  | 12 | 6.5 | 18.5 | 38737 | 0 | 323 | 535 | 738 | 2816 | 68 | 0 | 0 | 0 | 15 | 220 | 617 | 0 | 13 | 0 | 0 | 30597 | 2795
33 | 109.1 | SG4 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low |  |  |  | R - CP | C | C |  |  | 4 | 1.5 | 5.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
34 | 110 | SG4 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium |  |  |  | R - CP | C | C |  |  | 12 | 6.5 | 18.5 | 57610 | 0 | 1928 | 680 | 2128 | 2086 | 101 | 0 | 0 | 21 | 32 | 240 | 861 | 0 | 436 | 13 | 7 | 46527 | 2550
35 | 17 | SG5 | 4 - CASE | Case Summary | w_ct_m_case_summary | Medium High |  |  | 34 | R - CP | C | C | 2026-12-14 |  | 18 | 8 | 26 | 220508 | 4 | 10825 | 6249 | 40910 | 6459 | 1692 | 38 | 43 | 45025 | 8603 | 22190 | 7049 | 476 | 1818 | 1152 | 42 | 64018 | 3915
36 | 17.1 | SG5 | 4 - CASE | Close Elig? Button | w_ct_r_case_closure_eligible | Low High |  |  |  | R - CP | I | I |  |  | 8 | 5 | 13 | 2199 | 0 | 0 | 0 | 17 | 40 | 215 | 0 | 0 | 0 | 0 | 0 | 1548 | 0 | 0 | 0 | 0 | 178 | 201
37 | 17.2 | SG5 | 4 - CASE | Bail Schedule Maintenance Response | w_ct_r_fscl_bail_sched_maint_response | Low High |  |  |  | R - CP | I | I |  |  | 8 | 5 | 13 | 45034 | 0 | 25645 | 4070 | 169 | 21 | 140 | 4 | 6 | 135 | 300 | 454 | 928 | 11 | 6 | 24 | 3 | 11852 | 1266
38 | 150 | SG6 | 21 - WARRANTS | Pending Warrant Review | w_ct_m_warrant_review | Medium |  |  | 40 | R - CP | I | I | 2027-01-04 |  | 12 | 6.5 | 18.5 | 791 | 0 | 1 | 0 | 28 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 740 | 7
39 | 151 | SG6 | 21 - WARRANTS | Warrant Image Viewer | w_ct_m_warrant_images | Low High |  |  |  | R - CP | I | I |  |  | 8 | 5 | 13 | 1440 | 0 | 4 | 0 | 106 | 6 | 36 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 663 | 580
40 | 152 | SG6 | 21 - WARRANTS | Warrant Maintenance | w_ct_m_warrant_signal_mon | Medium |  |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 961 | 0 | 11 | 0 | 55 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 18 | 0 | 0 | 746 | 65
41 | 72 | SG6 | 11 - FISCAL MAINTENANCE | Chart of Accounts | w_ct_m_fscl_chart_of_accts | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 77 | SG6 | 11 - FISCAL MAINTENANCE | PA Distribution Xref | w_ct_m_fscl_dist_xref | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 154 | SG7 | 21 - WARRANTS | Warrant Reports | w_ct_r_main_report | Medium |  |  | 48 | R - CP | I | I | 2027-01-25 |  | 12 | 6.5 | 18.5 | 335 | 0 | 0 | 0 | 5 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 296 | 14
44 | 153 | SG7 | 21 - WARRANTS | Warrant Maintenance (CTS) (Warrant Signal Audit) | w_ct_m_warrant_signal_audit | Medium |  | X | [6 empty] | 12 | 6.5 | 18.5 | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 155 | SG7 | 21 - WARRANTS | Warrant XML Viewer (CTS) | w_ct_m_warrant_awss_xml | Low High |  | X | [6 empty] | 8 | 5 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 74 | SG7 | 11 - FISCAL MAINTENANCE | Fee Distribution Schedule | w_ct_m_fscl_fee_dist_sched | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 75 | SG7 | 11 - FISCAL MAINTENANCE | Fund Maintenance | w_ct_m_fscl_fund_maint | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 93 | SG8 | 15 - PERSON | Attorney Maintenance | w_ct_m_attorney | Medium |  |  | 40 | R - IM | I | I | 2027-02-15 |  | 12 | 6.5 | 18.5 | 1410 | 0 | 14 | 4 | 638 | 23 | 34 | 0 | 0 | 0 | 0 | 0 | 502 | 0 | 8 | 1 | 0 | 181 | 5
49 | 94 | SG8 | 15 - PERSON | Interpreters Maintenance | w_ct_m_interpreters | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 127 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 0
50 | 94.1 | SG8 | 15 - PERSON | Interpreters in System | w_ct_r_interpreters_lookup | Low |  |  |  | R - IM | I | I |  |  | 4 | 1.5 | 5.5 | 157 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0
51 | 94.2 | SG8 | 15 - PERSON | Interpreter Remarks(Ctrl+Alt+T under Remarks) | w_ct_r_interpreter_remarks | Low |  |  |  | R - IM | I | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 95 | SG8 | 15 - PERSON | Multi-Person Maintenance | w_ct_m_multi_person_maint | Low High |  |  |  | R - CP | I | C |  |  | 8 | 5 | 13 | 6620 | 0 | 2453 | 59 | 81 | 26 | 13 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 695 | 1 | 0 | 3190 | 39
53 | 95.1 | SG8 | 15 - PERSON | Multi-Person Maintenance Datafix Report | w_ct_r_mpm_report | Low |  |  |  | R - CP | I | C |  |  | 4 | 1.5 | 5.5 | 6329 | 0 | 2416 | 49 | 122 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 830 | 2 | 0 | 2811 | 27
54 | 73 | SG8 | 11 - FISCAL MAINTENANCE | Cost of Collections | w_ct_m_fscl_cost_of_collections | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 96 |  | 15 - PERSON | Person Link/Unlink | w_ct_m_person_link_unlink | Medium |  |  | 52 | R - CP | I | C | 2027-03-08 |  | 12 | 6.5 | 18.5 | 238 | 0 | 0 | 205 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0
56 | 98 |  | 15 - PERSON | Person Unlink | w_ct_m_person_unlink | Low High |  |  |  | R - CP | I | I |  |  | 8 | 5 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 99 |  | 15 - PERSON | Professional Consolidation | w_ct_m_professional_consolidation | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
58 | 100 |  | 15 - PERSON | Professional Maintenance | w_ct_m_professional_maint | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 74 | 0 | 0 | 0 | 0 | 50 | 13 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 1
59 | 100.1 |  | 15 - PERSON | New Professional | w_ct_r_professional_new | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 20 | 0 | 0 | 0 | 0 | 19 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 70 |  | 11 - FISCAL MAINTENANCE | Base Distribution Xref | w_ct_m_fscl_base_dist_xref | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 41 |  | 7 - COUNTER | Bail Entry | w_ct_m_bail_maint | Medium High |  |  | 44 | R - CP | R | R | 2027-03-29 |  | 18 | 8 | 26 | 29457 | 0 | 472 | 1472 | 222 | 0 | 11 | 0 | 0 | 11238 | 4015 | 2344 | 9 | 0 | 11 | 0 | 0 | 9538 | 125
62 | 41.1 |  | 7 - COUNTER | Agency Unit Address List (2-Bail Bond button) | w_ct_r_agency_unit_addrs_change | Low High |  |  |  | R - CP | R | R |  |  | 8 | 5 | 13 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 13 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 58 |  | 10 - FISCAL | Bail Maintenance | w_ct_m_bail_maint | Medium High |  |  |  | I | R | I |  |  | 18 | 8 | 26 | 29457 | 0 | 472 | 1472 | 222 | 0 | 11 | 0 | 0 | 11238 | 4015 | 2344 | 9 | 0 | 11 | 0 | 0 | 9538 | 125
64 | 44 |  | 7 - COUNTER | Counter Payment | w_ct_m_counter | Very High |  |  | 56 | R - CP | C | R | 2027-04-19 |  | 24 | 11 | 35 | 312924 | 0 | 112285 | 25372 | 6260 | 98 | 127 | 32 | 0 | 16448 | 1875 | 8664 | 1270 | 0 | 52 | 2 | 0 | 123855 | 16584
65 | 44.1 |  | 7 - COUNTER | Receipts (many flavors) |  | Medium |  |  |  | R - CP | C | R |  |  | 12 | 6.5 | 18.5
66 | 44.2 |  | 7 - COUNTER | Bail Forfeiture / Traffic School Payment Plans | w_ct_r_agree_pay_bf | Low |  |  |  | R - CP | C | R |  |  | 4 | 1.5 | 5.5 | 3691 | 0 | 728 | 203 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 2361 | 134
67 | 44.3 |  | 7 - COUNTER | Accept Payment | w_ct_r_payment | Medium |  |  |  | R - CP | C | R |  |  | 12 | 6.5 | 18.5 | 125125 | 0 | 41104 | 10740 | 3477 | 0 | 1 | 0 | 0 | 3656 | 492 | 1014 | 1094 | 0 | 46 | 0 | 0 | 60911 | 2590
68 | 44.4 |  | 7 - COUNTER | Notes | w_ct_r_cmmn_note | Low |  |  |  | R - CP | C | R |  |  | 4 | 1.5 | 5.5 | 16020 | 0 | 6010 | 1217 | 4 | 0 | 0 | 0 | 0 | 8094 | 206 | 59 | 276 | 0 | 0 | 0 | 0 | 150 | 4
69 | 47 |  | 7 - COUNTER | Open Cashier Session | w_ct_m_cashier_open_session | Low |  |  | 44 | R - CP | C | R | 2027-05-10 |  | 4 | 1.5 | 5.5 | 16193 | 0 | 4935 | 1705 | 337 | 0 | 1 | 0 | 0 | 1786 | 217 | 438 | 192 | 0 | 2 | 0 | 0 | 5966 | 614
70 | 43 |  | 7 - COUNTER | Cashier Reconciliation | w_ct_m_cashier_recon | Low High |  |  |  | R - CP | C | R |  |  | 8 | 5 | 13 | 17084 | 0 | 5005 | 1740 | 351 | 0 | 2 | 0 | 0 | 2236 | 255 | 478 | 222 | 0 | 2 | 0 | 0 | 6005 | 788
71 | 45 |  | 7 - COUNTER | Multi-Case Payment | w_ct_m_fscl_multi_case_payment | Low High |  |  |  | C | C | R |  |  | 8 | 5 | 13 | 5201 | 0 | 4126 | 593 | 3 | 0 | 24 | 0 | 0 | 16 | 45 | 0 | 4 | 0 | 5 | 0 | 0 | 384 | 1
72 | 46 |  | 7 - COUNTER | Non-Case Payment | w_ct_m_noncase_pymt | Low |  |  |  | R - CP | C | I |  |  | 4 | 1.5 | 5.5 | 5968 | 0 | 719 | 414 | 154 | 0 | 0 | 0 | 0 | 313 | 94 | 46 | 19 | 0 | 0 | 0 | 0 | 4065 | 144
73 | 48 |  | 7 - COUNTER | TS Completion | w_ct_m_mark_ts_complete | Low High |  |  |  | R - CP | I | C |  |  | 8 | 5 | 13 | 44 | 0 | 10 | 10 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1
74 | 49 |  | 7 - COUNTER | Victim Restitution Notice | w_ct_m_vr_notice | Low High |  |  |  | R - CP | C | C |  |  | 8 | 5 | 13 | 489 | 0 | 0 | 0 | 43 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 442 | 2
75 | 67 |  | 10 - FISCAL | Victim Restitution Approval | w_ct_m_fscl_vr_apprv | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 491 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 476 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 21 |  | 4 - CASE | LEA Interface | w_ct_m_case_lea_interface | Low |  |  |  | R - CP | I | I | 2027-05-31 | 9/15 MU: pending RF response on window usage | 4 | 1.5 | 5.5 | 6 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1
77 | 80 |  | 12 - INTERFACES | ATP Dashboard | w_ct_m_atp_dashboard | Medium |  |  | 42 | R - CP | I | C |  |  | 12 | 6.5 | 18.5 | 1524 | 0 | 0 | 1062 | 0 | 3 | 57 | 0 | 0 | 0 | 0 | 1 | 105 | 0 | 0 | 0 | 0 | 292 | 4
78 | 88 |  | 12 - INTERFACES | OneOC - Clerk Review Module | w_ct_m_oneoc_interface | Medium |  |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 1979 | 0 | 0 | 0 | 3 | 121 | 15 | 0 | 0 | 0 | 0 | 0 | 62 | 0 | 109 | 0 | 0 | 1656 | 13
79 | 40 |  | 7 - COUNTER | Cash Bail Notice | w_ct_m_bail_bond_notice | Medium High |  |  |  | C | R | I |  |  | 18 | 8 | 26 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 19 |  | 4 - CASE | Citation Batches / Batch Entry | w_ct_m_cite_batch_entry | Medium High |  |  | 54 | R - CP | I | I | 2027-06-21 |  | 18 | 8 | 26 | 1333 | 0 | 0 | 0 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1314 | 6
81 | 20 |  | 4 - CASE | Citation Entry | w_ct_m_case_citation_entry | Medium High |  |  |  | R - CP | I | I |  |  | 18 | 8 | 26 | 707 | 0 | 0 | 0 | 31 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669 | 5
82 | 23 |  | 4 - CASE | Missing Complaint | w_ct_m_case_missing_complaint | Medium High |  |  |  | I | R | I |  |  | 18 | 8 | 26 | 7451 | 0 | 0 | 2 | 0 | 0 | 8 | 0 | 0 | 4584 | 2319 | 532 | 0 | 0 | 0 | 0 | 0 | 6 | 0
83 | 16 |  | 4 - CASE | Case Maintenance | w_ct_m_case_maint | Very High |  |  | 60 | R - CP | C | C | 2027-07-12 |  | 24 | 11 | 35 | 208279 | 3 | 15401 | 9379 | 23976 | 1015 | 339 | 28 | 0 | 11839 | 3475 | 4415 | 2247 | 0 | 137 | 128 | 0 | 131341 | 4556
84 | 16.1 |  | 4 - CASE | Vision Public Case - Input | w_ct_r_public_case_input | Low |  |  |  | R - CP | I | I |  |  | 4 | 1.5 | 5.5 | 1590 | 0 | 29 | 0 | 21 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 32 | 0 | 8 | 0 | 0 | 1477 | 22
85 | 16.2 |  | 4 - CASE | Person Information Select | w_ct_m_person_select | Low High |  |  |  | R - CP | C | C |  |  | 8 | 5 | 13 | 164937 | 0 | 56351 | 11828 | 7433 | 257 | 75 | 0 | 0 | 3963 | 172 | 470 | 4596 | 0 | 273 | 14 | 0 | 77374 | 2131
86 | 16.3 |  | 4 - CASE | Unavailable Court Dates | w_ct_r_unavailable_dates | Low |  |  |  | R - CP | I | C |  |  | 4 | 1.5 | 5.5 | 58 | 0 | 14 | 2 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 31 | 0
87 | 16.4 |  | 4 - CASE | Case Dates | w_ct_r_cal_case_dates | Low |  |  |  | R - CP | I | C |  |  | 4 | 1.5 | 5.5 | 16389 | 0 | 12389 | 486 | 2969 | 68 | 5 | 0 | 0 | 46 | 41 | 9 | 58 | 0 | 0 | 0 | 0 | 203 | 115
88 | 16.5 |  | 4 - CASE | Other Cases | w_ct_r_cal_other_cases | Low |  |  |  | R - CP | I | I |  |  | 4 | 1.5 | 5.5 | 6 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
89 | 24 |  | 4 - CASE | NCIC Case Initiation | w_ct_m_case_maint_ncic | Medium |  |  |  | R - CP | I | I |  |  | 12 | 6.5 | 18.5 | 1920 | 0 | 31 | 0 | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 11 | 0 | 0 | 1800 | 25
90 | 59 |  | 10 - FISCAL | Case Distribution Override | w_ct_m_fscl_dist_override | Medium |  |  | 56 | I | R | I | 2027-08-02 |  | 12 | 6.5 | 18.5 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 61 |  | 10 - FISCAL | Check Approval | w_ct_m_fscl_chk_apprv | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1038 | 26 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 61.1 |  | 10 - FISCAL | Specify Check Number | w_ct_r_fscl_chk_nbr | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 61.2 |  | 10 - FISCAL | Print Checks | w_ct_r_fscl_prnt_chks | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 62 |  | 10 - FISCAL | Check Maintenance | w_ct_m_fscl_chk_maint | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 546 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 534 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 71 |  | 11 - FISCAL MAINTENANCE | Bondsman / Surety | w_ct_m_bondsman_surety | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 89 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 64 |  | 10 - FISCAL | Misapplications/Voids | w_ct_m_fscl_pmt_misapp_void | Medium |  |  | 52 | I | R | R | 2027-08-23 |  | 12 | 6.5 | 18.5 | 6926 | 0 | 0 | 315 | 0 | 0 | 5 | 0 | 0 | 4277 | 372 | 1605 | 17 | 0 | 0 | 0 | 0 | 0 | 335
97 | 64.1 |  | 10 - FISCAL | w_ct_r_fiscal_batch_cases | w_ct_r_fiscal_batch_cases | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 130 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 85 | 14 | 23 | 1 | 0 | 0 | 0 | 0 | 0 | 0
98 | 65 |  | 10 - FISCAL | Reapply Payment | w_ct_m_fscl_reapp_remit | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 66 |  | 10 - FISCAL | Reversals | w_ct_m_fscl_pmt_reversals | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 66.1 |  | 10 - FISCAL | w_ct_r_fiscal_multi_cases_reversal | w_ct_r_fiscal_multi_cases_reversal | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 76 |  | 11 - FISCAL MAINTENANCE | PA Distribution Schedule | w_ct_m_fscl_pa_dist_sched | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 82 |  | 12 - INTERFACES | DMV Abstract on Demand | w_ct_m_dmv_abstract_on_demand | Low |  |  | 50 | R - IM | I | I | 2027-09-13 |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 83 |  | 12 - INTERFACES | DMV Admin Transactions | w_ct_m_dmv_admin_tran | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
104 | 84 |  | 12 - INTERFACES | DMV Error Cases Report | w_ct_m_dmv_error_queue_mon | Medium |  |  |  | R - IM | I | I |  |  | 12 | 6.5 | 18.5 | 1270 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0
105 | 85 |  | 12 - INTERFACES | DMV Error Maintenance | w_ct_m_dmv_abstract_maint | Medium High |  |  |  | R - IM | I | I |  |  | 18 | 8 | 26 | 15000 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 14992 | 0 | 0 | 0 | 0 | 0 | 0
106 | 86 |  | 12 - INTERFACES | DMV Prior Missing Report | w_ct_m_dmv_priors_missing_cases | Low |  |  |  | R - IM | I | I |  |  | 4 | 1.5 | 5.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
107 | 143 |  | 20 - TABLES | PA Schedule Maintenance | w_ct_m_maint_pa_sched | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 87 |  | 12 - INTERFACES | DOJ Interface | w_ct_m_intf_doj_review | High |  |  | 55 | R - IM | I | I | 2027-10-04 |  | 21 | 10 | 31 | 1633 | 0 | 0 | 0 | 38 | 1 | 156 | 0 | 0 | 0 | 0 | 0 | 803 | 0 | 0 | 0 | 0 | 624 | 11
109 | 87.1 |  | 12 - INTERFACES | DOJ Abstract | w_ct_r_doj_abstract_viewer | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 16 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4 | 0
110 | 3 |  | 1 - ADMIN | Excel Batch Processing | w_ct_m_xl_batch_processing | Medium High |  |  |  | R - IM | I | I |  |  | 18 | 8 | 26 | 243 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 46
111 | 78 |  | 11 - FISCAL MAINTENANCE | Special Distribution Schedule | w_ct_m_fscl_spl_dist_sched | Low High |  |  |  | I | R | I |  |  | 8 | 5 | 13 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 89 |  | 13 - JBSIS | JBSIS Audit Report | w_ct_m_jbsis_audit_report | Medium |  |  | 50 | R - IM | I | I | 2027-10-25 |  | 12 | 6.5 | 18.5 | 46 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 32 | 0 | 0 | 0
113 | 91 |  | 13 - JBSIS | JBSIS Report Defn. | w_ct_m_jbsis_report_detail | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 41 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 4 | 0 | 0 | 0
114 | 92 |  | 13 - JBSIS | JBSIS Reporting | w_ct_jbsis_manrpt | Medium High |  |  |  | R - IM | I | I |  |  | 18 | 8 | 26 | 572 | 0 | 0 | 0 | 0 | 6 | 37 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 124 | 0 | 2 | 30
115 | 92.1 |  | 13 - JBSIS | JBSIS Case Listing | w_ct_jbsis_case_person | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 2524 | 0 | 0 | 0 | 0 | 1 | 44 | 0 | 0 | 0 | 0 | 0 | 2117 | 0 | 0 | 98 | 0 | 0 | 264
116 | 79 |  | 11 - FISCAL MAINTENANCE | VR Distribution Schedule | w_ct_m_fscl_vr_dist_sched | Low |  |  |  | I | R | I |  |  | 4 | 1.5 | 5.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 126 |  | 20 - TABLES | Calendar Plan Maintenance | w_ct_m_calendar_plan | Medium High |  |  | 60 | R - IM | I | I | 2027-11-15 |  | 18 | 8 | 26 | 48 | 0 | 0 | 0 | 2 | 1 | 31 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 2
118 | 132 |  | 20 - TABLES | Docket Code Macro Configuration | w_ct_m_docket_macro | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0
119 | 133 |  | 20 - TABLES | Docket Code Macro Maintenance | w_ct_m_docket_macro_maint | Medium High |  |  |  | R - IM | I | I |  |  | 18 | 8 | 26 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 133.1 |  | 20 - TABLES | Docket Macro Preview | w_ct_r_dckt_macro_preview | Low |  |  |  | R - IM | I | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 139 |  | 20 - TABLES | Fee Schedule | w_ct_m_fscl_fee_sched | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 45 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 134 |  | 20 - TABLES | Docket Code Macro Mover | w_ct_m_docket_macro_move | Medium |  |  | 50 | R - IM | I | I | 2027-12-06 |  | 12 | 6.5 | 18.5 | 22 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0
123 | 135 |  | 20 - TABLES | Docket Code Maintenance | w_ct_m_docket_code_maint | Medium High |  | X | [6 empty] | 18 | 8 | 26 | 4097 | 0 | 14 | 115 | 187 | 114 | 1277 | 2 | 4 | 7 | 11 | 48 | 1374 | 8 | 26 | 32 | 2 | 767 | 109
124 | 135.1 |  | 20 - TABLES | w_ct_r_docket_codes | w_ct_r_docket_codes | Low |  | X | [6 empty] | 4 | 1.5 | 5.5 | 3050 | 0 | 0 | 75 | 61 | 98 | 1426 | 1 | 2 | 0 | 9 | 36 | 1248 | 0 | 0 | 29 | 0 | 15 | 50
125 | 135.2 |  | 20 - TABLES | w_ct_r_lookup_nbr | w_ct_r_lookup_nbr | Low |  | X | [6 empty] | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 136 |  | 20 - TABLES | Docket Code Reference | w_ct_m_docket_codes_reference | Low |  |  |  | R - IM | I | I |  |  | 4 | 1.5 | 5.5 | 22715 | 0 | 490 | 800 | 17960 | 802 | 33 | 0 | 0 | 157 | 118 | 87 | 676 | 0 | 38 | 1 | 1 | 1498 | 54
127 | 32 |  | 5 - COLLECTIONS | Financial Evaluation | w_ct_m_coll_fin_eval_list | Low High |  |  |  | I | I | R |  |  | 8 | 5 | 13 | 7 | 0 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 113.1 |  | 17 - REPORTS | Open Cases Report | w_ct_m_open_cases | Medium |  |  | 60 | R - CP | I | R | 2027-12-27 |  | 12 | 6.5 | 18.5 | 1523 | 0 | 5 | 489 | 25 | 206 | 33 | 0 | 0 | 0 | 4 | 0 | 157 | 0 | 0 | 0 | 0 | 361 | 243
129 | 114 |  | 17 - REPORTS | State Prison Abstracts | w_ct_m_prsn_abstract | Medium High |  |  |  | R - CP | I | I |  |  | 18 | 8 | 26 | 3987 | 0 | 758 | 0 | 187 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 3003 | 2
130 | 113.6 |  | 17 - REPORTS | Case Calendar Summary | w_ct_m_cal_sum | Medium |  |  |  | R - CT | I | I |  |  | 12 | 6.5 | 18.5 | 2870 | 0 | 1 | 1 | 2513 | 251 | 1 | 0 | 0 | 0 | 1 | 6 | 76 | 0 | 4 | 0 | 0 | 9 | 7
131 | 69 |  | 11 - FISCAL MAINTENANCE | Bail Distribution Schedule | w_ct_m_fscl_bail_dist_sched | Medium High |  |  | 54 | I | R | I | 2028-01-17 |  | 18 | 8 | 26 | 114 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 112 |  | 17 - REPORTS | Monthly Funding Report | w_ct_m_fscl_month_fund_report | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 750 | 0 | 0 | 237 | 0 | 0 | 1 | 0 | 0 | 1 | 505 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 113.2 |  | 17 - REPORTS | Bail Bond Activity Report | w_ct_r_report_builder | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
134 | 113.3 |  | 17 - REPORTS | Bail Bond Summary Judgment | w_ct_r_report_builder | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
135 | 113.4 |  | 17 - REPORTS | Bail Forfeiture Report | w_ct_r_report_builder | Medium |  |  | 60 | I | R | I | 2028-02-07 |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
136 | 113.5 |  | 17 - REPORTS | Summary Judgment Bail Bonds Payment Due | w_ct_r_report_builder | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
137 | 113.7 |  | 17 - REPORTS | Case Payment Activity Query | w_ct_r_report_builder | Medium |  |  |  | C | R | I |  |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
138 | 113.8 |  | 17 - REPORTS | Cash Bail Forfeiture Notice | w_ct_r_report_builder | Medium |  |  |  | C | R | I |  |  | 12 | 6.5 | 18.5 | 37048 | 0 | 256 | 2157 | 1862 | 372 | 323 | 0 | 0 | 5354 | 7560 | 977 | 406 | 0 | 6627 | 2 | 0 | 10489 | 663
139 | 68 |  | 10 - FISCAL | Summary Judgment | w_ct_m_summary_judgement | Medium |  |  |  | I | R | I |  |  | 12 | 6.5 | 18.5 | 1012 | 0 | 1 | 1 | 0 | 3 | 96 | 0 | 0 | 648 | 20 | 240 | 1 | 0 | 0 | 0 | 0 | 2 | 0
140 | 63 |  | 10 - FISCAL | Fiscal Case Analysis | w_ct_m_fiscal_case_analysis | Medium High |  |  | 50 | I | R | C | 2028-02-28 |  | 18 | 8 | 26 | 1296 | 0 | 0 | 12 | 0 | 0 | 28 | 0 | 0 | 106 | 47 | 1103 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 26 |  | 5 - COLLECTIONS | Campaign Maintenance | w_ct_m_coll_campaign_maint | Low High |  |  |  | I | I | R |  |  | 8 | 5 | 13 | 14 | 0 | 0 | 6 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 15 |  | 4 - CASE | Case Backup and Restore | w_ct_m_case_backup_trg | Low High |  |  |  | R - IM | I | I |  |  | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 18 |  | 4 - CASE | Case Transfer | w_ct_m_case_transfer_cst | Low High |  |  |  | R - IM | C | C |  |  | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 22 |  | 4 - CASE | Mass Case/Calendar Copy | w_ct_m_mass_case_copy | Low High |  |  |  | R - CT | I | I |  |  | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 28 |  | 5 - COLLECTIONS | Collections Campaign Queue | w_ct_m_coll_campaign_queue | Medium |  |  | 60 | I | I | R | 2028-03-20 | L:\ drive | 12 | 6.5 | 18.5 | 133 | 0 | 0 | 126 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 29 |  | 5 - COLLECTIONS | Collections Person Interface | w_ct_m_coll_person_interface | Medium |  |  |  | I | I | R |  | L:\ drive | 12 | 6.5 | 18.5 | 296 | 0 | 0 | 294 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 81 |  | 12 - INTERFACES | Check Auditor/Controller | w_ct_m_fscl_audit_controller | Low High |  |  |  | I | R | I |  | L:\ drive | 8 | 5 | 13 | 54 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 51 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 115 |  | 18 - SCHEDULE MAINTENANCE | Special Schedule | w_ct_m_fscl_special_schedule | Low |  |  |  | R - IM | C | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 116 |  | 18 - SCHEDULE MAINTENANCE | Speed Schedule | w_ct_m_fscl_speed_sched | Low High |  |  |  | R - IM | C | I |  |  | 8 | 5 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1
150 | 116.1 |  | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule | w_ct_r_fscl_speed_sched | Low |  |  |  | R - IM | C | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 117 |  | 18 - SCHEDULE MAINTENANCE | Speed Schedule 2 | w_ct_m_fscl_speed_sched_2 | Low High |  |  |  | R - IM | C | I |  |  | 8 | 5 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
152 | 117.1 |  | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule (Speed Sched2) | w_ct_r_fscl_speed_sched_2 | Low |  |  |  | R - IM | C | I |  |  | 4 | 1.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 27 |  | 5 - COLLECTIONS | Collections | w_ct_m_coll_collections | Very High |  |  | 53 | I | I | R | 2028-04-10 |  | 24 | 11 | 35 | 247214 | 0 | 214314 | 27153 | 2 | 2 | 23 | 2 | 0 | 0 | 16 | 7 | 5653 | 0 | 0 | 0 | 0 | 0 | 42
154 | 38 |  | 5 - COLLECTIONS | OCV Return | w_ct_m_ocv_file_load | Low High |  |  |  | I | I | R |  | L:\ drive | 8 | 5 | 13 | 9 | 0 | 0 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 37 |  | 5 - COLLECTIONS | OCV Payment Processor | w_ct_m_ocv_payment | High |  |  |  | I | I | R |  |  | 21 | 10 | 31 | 373 | 0 | 0 | 369 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 33 |  | 5 - COLLECTIONS | FTBCOD Interface | w_ct_m_case_ftbcod_select | High |  |  | 47 | I | I | R | 2028-04-10 | L:\ drive | 21 | 10 | 31 | 1217 | 0 | 0 | 1197 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 34 |  | 5 - COLLECTIONS | FTBCOD Payment Processor | w_ct_m_ftbcod_payment | Medium High |  |  |  | I | I | R |  | L:\ drive | 18 | 8 | 26 | 1108 | 0 | 0 | 1100 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 34.1 |  | 5 - COLLECTIONS | Import Action File (Select button) | w_ct_r_coll_ftbcod_import_actions | Low |  |  |  | I | I | R |  | L:\ drive | 4 | 1.5 | 5.5 | 48 | 0 | 0 | 46 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 34.2 |  | 5 - COLLECTIONS | Import Claim Schedule File (FTBCOD) | w_ct_r_ftbcod_import_cs | Low |  |  |  | I | I | R |  | L:\ drive | 4 | 1.5 | 5.5 | 124 | 0 | 0 | 121 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 35 |  | 5 - COLLECTIONS | FTBTI Interface | w_ct_m_coll_ftbti_interface | High |  |  | 47 | I | I | R | 2028-05-01 | L:\ drive | 21 | 10 | 31 | 177 | 0 | 0 | 160 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 36 |  | 5 - COLLECTIONS | FTBTI Payment Processor | w_ct_m_ftbti_payment | Medium High |  |  |  | I | I | R |  | L:\ drive | 18 | 8 | 26 | 249 | 0 | 0 | 246 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 36.1 |  | 5 - COLLECTIONS | Import Claim Schedule File (FTBTI) | w_ct_r_cmmn_file_search | Low |  |  |  | I | I | R |  | L:\ drive | 4 | 1.5 | 5.5 | 98 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 36.2 |  | 5 - COLLECTIONS | List Search | w_ct_r_cmmn_list_search | Low |  |  |  | I | I | R |  | L:\ drive | 4 | 1.5 | 5.5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 97 |  | 15 - PERSON | Person Maintenance | w_ct_m_person_maint | Medium |  |  | 38 | R - CP | C | C | 2028-05-22 |  | 12 | 6.5 | 18.5 | 146301 | 0 | 40891 | 7974 | 6966 | 642 | 573 | 4 | 0 | 19433 | 6662 | 5771 | 4240 | 0 | 438 | 82 | 0 | 50661 | 1964
165 | 97.1 |  | 15 - PERSON | Person Search | w_ct_r_person_search | Medium High |  |  |  | R - CP | C | C |  | 9/17 MU: will be worked on with Simple/Adv. Case Search | 18 | 8 | 26 | 126349 | 0 | 10428 | 2919 | 6325 | 746 | 723 | 11 | 0 | 25770 | 8906 | 6959 | 911 | 0 | 2373 | 92 | 0 | 58361 | 1825
166 | 97.2 |  | 15 - PERSON | Quick Add |  | Low High |  |  |  | R - CP | C | C |  | 9/17 MU: will be worked on with Simple/Adv. Case Search | 8 | 5 | 13
167 | 158 |  | GENERAL | Case Search (Adv Search) | w_ct_r_case_search | Medium High |  |  | 30 | R - IM | C | R | 2028-06-12 |  | 18 | 8 | 26 | 148370 | 2 | 13435 | 4673 | 14398 | 527 | 1025 | 31 | 10 | 17196 | 4082 | 15861 | 5439 | 192 | 51 | 132 | 18 | 68622 | 2676
168 | 159 |  | GENERAL | Simple Case Search | w_ct_r_simple_search | Medium |  |  |  | R - IM | C | R |  |  | 12 | 6.5 | 18.5 | 2000956 | 31 | 344330 | 181542 | 496605 | 62660 | 5753 | 370 | 43 | 170726 | 38249 | 37853 | 56393 | 2125 | 21647 | 3150 | 80 | 521151 | 58248
169 | 50 |  | 8 - COURTROOM | Courtroom / Admin Minutes Entry | w_ct_courtroom | Very High |  |  | 120 | R - CT | C | R | 2028-07-03 |  | 24 | 11 | 35 | 1147036 | 2 | 61199 | 46752 | 627849 | 9624 | 227 | 10 | 0 | 35215 | 11426 | 9436 | 8817 | 0 | 2414 | 20 | 0 | 327344 | 6701
170 | 50.1 |  | 8 - COURTROOM | Docket Code Help | w_ct_doc_help_rsp | Low High |  |  |  | R - CT | C | R |  |  | 8 | 5 | 13 | 271196 | 0 | 4707 | 2309 | 238021 | 2697 | 78 | 43 | 2 | 1491 | 254 | 776 | 1805 | 2 | 43 | 8 | 0 | 18456 | 504
171 | 50.2 |  | 8 - COURTROOM | Multi-Case Entry | w_ct_doc_multicase | Medium |  |  |  | R - CT | I | R |  |  | 12 | 6.5 | 18.5 | 148921 | 0 | 488 | 408 | 144934 | 407 | 3 | 0 | 0 | 24 | 2 | 19 | 204 | 0 | 2 | 1 | 0 | 2415 | 14
172 | 50.3 |  | 8 - COURTROOM | Print Imaging Barcode | w_ct_r_barcode_current_hrg | Low High |  |  |  | R - CT | C | R |  |  | 8 | 5 | 13 | 481486 | 0 | 21047 | 6323 | 262402 | 1152 | 1 | 0 | 0 | 12580 | 3974 | 4785 | 1541 | 0 | 393 | 0 | 0 | 163707 | 3581
173 | 50.4 |  | 8 - COURTROOM | Print Imaging Barcode Sheet (reprint) | w_ct_r_barcode_print | Low High |  |  |  | R - CT | C | R |  |  | 8 | 5 | 13 | 91198 | 0 | 3611 | 682 | 33624 | 825 | 2 | 0 | 0 | 973 | 342 | 397 | 496 | 0 | 1636 | 1 | 0 | 48281 | 328
174 | 50.5 |  | 8 - COURTROOM | Extended Text Entry Window | w_ct_r_ctrs_dckt_text | Low |  |  |  | R - CT | C | R |  |  | 4 | 1.5 | 5.5 | 490158 | 0 | 3322 | 2264 | 414276 | 4956 | 1 | 0 | 0 | 6836 | 616 | 661 | 1548 | 0 | 90 | 0 | 0 | 55345 | 243
175 | 50.6 |  | 8 - COURTROOM | Courtroom Print | w_ct_r_dckt_report_printing | Low High |  |  |  | R - CT | C | R |  |  | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 53.1 |  | 8 - COURTROOM | CIS Sheets (16 Flavors) |  | Very High |  |  |  | R - CT | C | C |  |  | 24 | 11 | 35
177 | 54 |  | 8 - COURTROOM | MOCS | w_ct_m_mocs | Very High |  |  | 72 | R - CT | I | I | 2028-07-24 |  | 24 | 11 | 35 | 21233 | 0 | 209 | 79 | 20668 | 148 | 15 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 1 | 0 | 29 | 39
178 | 54.2 |  | 8 - COURTROOM | MOCS Multi Case Entry | w_ct_r_mocs_multi | Very High |  |  |  | R - CT | I | I |  |  | 24 | 11 | 35 | 940 | 0 | 0 | 0 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 54.1 |  | 8 - COURTROOM | Docket Selection ( MOCS) | w_ct_r_mocs_dkt_entry | Medium |  |  |  | R - CT | I | I |  |  | 12 | 6.5 | 18.5 | 91537 | 0 | 0 | 0 | 91093 | 278 | 6 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 131 | 0
180 | 130.1 |  | 20 - TABLES | MOCS Docket Definition | w_ct_m_mocs_dkt_defn | Medium |  | X | [6 empty] | 12 | 6.5 | 18.5 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 101 |  | 15 - PERSON | Sealed Access | w_ct_r_security_admin | Medium High |  |  | 52 | R - IM | I | I | 2028-08-14 |  | 18 | 8 | 26 | 817 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0
182 | 121 |  | 19 - SECURITY | Security Admin | w_ct_r_security_admin | Medium High |  | X | [6 empty] | 18 | 8 | 26 | 817 | 0 | 0 | 0 | 0 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0
183 | 5 |  | 1 - ADMIN | Person Delete | w_ct_m_person_delete | Low High |  | X | [6 empty] | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 7 |  | 1 - ADMIN | Vlan IP ranges | w_ct_m_vlan_ip_ranges | Low High |  | X | [6 empty] | 8 | 5 | 13 | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 118 |  | 19 - SECURITY | Advanced Menu Manager | w_ct_m_menu_full | Medium |  | X | 48 |  |  |  | 2028-09-04 |  | 12 | 6.5 | 18.5 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 119 |  | 19 - SECURITY | Basic Menu Manager | w_ct_m_menu_basic | Medium |  | X | [6 empty] | 12 | 6.5 | 18.5 | 41 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 119.1 |  | 19 - SECURITY | Vision Menu Profile Report | w_ct_r_menu_profile_report | Low |  | X | [6 empty] | 4 | 1.5 | 5.5 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 120 |  | 19 - SECURITY | Menu Admin | w_ct_r_menu_admin | Medium |  | X | [6 empty] | 12 | 6.5 | 18.5 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 127 |  | 20 - TABLES | Code Mover | w_ct_m_code_mover | Low High |  | X | [6 empty] | 8 | 5 | 13 | 222 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 140 |  | 20 - TABLES | Generic Notice Maintenance | w_ct_m_letter_maint | Low High |  | X | 46 |  |  |  | 2028-09-25 |  | 8 | 5 | 13 | 6 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
191 | 142 |  | 20 - TABLES | Letter Maintenance | w_ct_m_letter_maint_lm | Low High |  | X | [6 empty] | 8 | 5 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 156 |  | GENERAL | Log on Window (initial loading of config items) |  | Medium High |  |  |  | R - IM | C | R |  |  | 18 | 8 | 26
193 | 157 |  | GENERAL | Menu Actions |  | Medium |  |  |  | R - IM | C | R |  |  | 12 | 6.5 | 18.5
194 | 1 |  | 1 - ADMIN | Auto Process Schedule | w_ct_m_mnt_auto_process_sched | Low High | Internal | X | 40 |  |  |  | 2028-10-16 |  | 8 | 5 | 13 | 41 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 124 |  | 20 - TABLES | Agency X-Ref Maintenance | w_ct_m_maint_agy_xref | Low High | Internal | X | [6 empty] | 8 | 5 | 13 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 131 |  | 20 - TABLES | Court Holidays | w_ct_m_court_holidays | Low High | Internal | X | [6 empty] | 8 | 5 | 13 | 26 | 0 | 0 | 0 | 6 | 1 | 17 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
197 | 147 |  | 20 - TABLES | Unit Codes | w_ct_m_unit_codes | Medium | Internal | X | [6 empty] | 12 | 6.5 | 18.5 | 169 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
198 | 123 |  | 20 - TABLES | Agency Codes | w_ct_m_agency_codes | Low | Internal | X | [6 empty] | 4 | 1.5 | 5.5 | 33 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 2039 | 1052.5 | 3091.5

## Complexity LOE
Category | Dev | QA
Low | 4 | 1.5
Low High | 8 | 5
Medium | 12 | 6.5
Medium High | 18 | 8
High | 21 | 10
Very High | 24 | 11
Standard level of effort (days) per complexity level.
Edit the Dev / QA values above - the LOE columns on 'Pipeline with LOE' recalculate automatically.

## Pipeline - OPS
Priority Group | ID | MENU | SUB-MENU | OBJECT NAME | GROUPING | STATUS | No UAT (CTS Only) | OPS | FIS | COL | COMMENTS
1 | 25 | 4 - CASE | Priors | w_ct_m_case_priors | High | 2-Week |  | R - CP | I | C
| 25.1 | 4 - CASE | Print - Copies Spec. | w_ct_m_case_priors_print_spec | Low | 2-Week |  | R - CP | I | I
| 90 | 13 - JBSIS | JBSIS Maintenance | w_jbsis_maintenance | Medium | 2-Week |  | R - IM | I | I
| 1 | 1 - ADMIN | Auto Process Schedule | w_ct_m_mnt_auto_process_sched | Low High | Internal | X
| 2 | 1 - ADMIN | Date of Action Maintenance | w_ct_m_docket_date_of_action_maint | Low | Internal | X
| 124 | 20 - TABLES | Agency X-Ref Maintenance | w_ct_m_maint_agy_xref | Low High | Internal | X
| 131 | 20 - TABLES | Court Holidays | w_ct_m_court_holidays | Low High | Internal | X
| 147 | 20 - TABLES | Unit Codes | w_ct_m_unit_codes | Medium | Internal | X
| 123 | 20 - TABLES | Agency Codes | w_ct_m_agency_codes | Low | Internal | X
2 | 55 | 9 - EXHIBITS | Exhibit List | w_ct_m_exhibit_list | Low High | QA Completed |  | R - CT | I | I
| 55.1 | 9 - EXHIBITS | Exhibit Search | w_ct_r_exhibit_list_case_search | Low | QA Completed |  | R - CT | I | I
| 56 | 9 - EXHIBITS | Exhibit Maintenance | w_ct_m_exhibit_maintenance | Low High | QA - In Mitigation | X
| 56.1 | 9 - EXHIBITS | New Exhibit Hearing List | w_ct_m_exhibit_new_hearing | Low High | QA - In Mitigation | X
| 57 | 9 - EXHIBITS | Exhibit Management | w_ct_m_exhibit_management | Low | QA - In Mitigation | X
| 57.1 | 9 - EXHIBITS | Exhibit Management Search | w_ct_m_exhibit_management_srch |  | QA - In Mitigation | X
| 57.2 | 9 - EXHIBITS | Exhibit History | w_ct_r_exhibit_history |  | QA - In Mitigation |  | R - CT | I | I
3 | 53 | 8 - COURTROOM | Minutes | w_ct_m_docket_reporting | Medium High | QA - In Mitigation |  | R - CT | C | R
| 158 | GENERAL | Case Search (Adv Search) | w_ct_r_case_search | Medium High |  |  | R - IM | C | R
| 159 | GENERAL | Simple Case Search | w_ct_r_simple_search | Medium |  |  | R - IM | C | R
4 | 9 | 3 - CALENDARING | Calendar Report | w_ct_m_cal_report_list | Medium | Pending Dev Assignment |  | R - CP | I | I
| 9.1 | 3 - CALENDARING | Calendar Batch Print | w_ct_r_batch_print | Medium high | Pending Dev Assignment |  | R - CP | I | I
| 9.2 | 3 - CALENDARING | Web Browser of generated files | w_ct_r_pdf_viewer | Low High | Pending Dev Assignment |  | R - CP | I | I
| 8 | 3 - CALENDARING | Calendar List | w_ct_m_cal_list | Medium | Pending Dev Assignment |  | R - CT | I | I
| 8.1 | 3 - CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | Pending Dev Assignment |  | R - CT | I | I
5 | 10 | 3 - CALENDARING | Calendar Transfer | w_ct_m_cal_transfer | Low High | In Development |  | R - CT | I | I
| 11 | 3 - CALENDARING | Calendar Transfer Notices | w_ct_m_cal_transfer_notice | Medium | Pending Dev Assignment |  | R - CT | I | I
| 13 | 3 - CALENDARING | Court Trial Transfer | w_ct_m_cal_transfer_location | Medium | Pending Dev Assignment |  | R - CT | I | I
| 14 | 3 - CALENDARING | Notice of Packaged Hearings | w_ct_m_case_package_list | Low High | Pending Dev Assignment |  | R - CT | I | I
6 | 109 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium |  |  | R - CP | C | C
| 109.1 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low |  |  | R - CP | C | C
| 110 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium |  |  | R - CP | C | C
7 | 97 | 15 - PERSON | Person Maintenance | w_ct_m_person_maint | Medium |  |  | R - CP | C | C
| 97.1 | 15 - PERSON | Person Search | w_ct_r_person_search | Medium High |  |  | R - CP | C | C
| 97.2 | 15 - PERSON | Quick Add |  | Low High |  |  | R - CP | C | C
| 93 | 15 - PERSON | Attorney Maintenance | w_ct_m_attorney | Medium |  |  | R - IM | I | I
| 94 | 15 - PERSON | Interpreters Maintenance | w_ct_m_interpreters | Low High |  |  | R - IM | I | I
| 94.1 | 15 - PERSON | Interpreters in System | w_ct_r_interpreters_lookup | Low |  |  | R - IM | I | I
| 94.2 | 15 - PERSON | Interpreter Remarks(Ctrl+Alt+T under Remarks) | w_ct_r_interpreter_remarks | Low |  |  | R - IM | I | I
8 | 95 | 15 - PERSON | Multi-Person Maintenance | w_ct_m_multi_person_maint | Low High |  |  | R - CP | I | C
| 95.1 | 15 - PERSON | Multi-Person Maintenance Datafix Report | w_ct_r_mpm_report | Low |  |  | R - CP | I | C
| 96 | 15 - PERSON | Person Link/Unlink | w_ct_m_person_link_unlink | Medium |  |  | R - CP | I | C
| 98 | 15 - PERSON | Person Unlink | w_ct_m_person_unlink | Low High |  |  | R - CP | I | I
| 100 | 15 - PERSON | Professional Maintenance | w_ct_m_professional_maint | Low High |  |  | R - IM | I | I
| 100.1 | 15 - PERSON | New Professional | w_ct_r_professional_new | Low High |  |  | R - IM | I | I
| 99 | 15 - PERSON | Professional Consolidation | w_ct_m_professional_consolidation | Low High |  |  | R - IM | I | I
9 | 17 | 4 - CASE | Case Summary | w_ct_m_case_summary | Medium High |  |  | R - CP | C | C
| 17.1 | 4 - CASE | Close Elig? Button | w_ct_r_case_closure_eligible | Low High |  |  | R - CP | I | I
| 17.2 | 4 - CASE | Bail Schedule Maintenance Response | w_ct_r_fscl_bail_sched_maint_response | Low High |  |  | R - CP | I | I
| 21 | 4 - CASE | LEA Interface | w_ct_m_case_lea_interface | Low |  |  | R - CP | I | I
| 80 | 12 - INTERFACES | ATP Dashboard | w_ct_m_atp_dashboard | Medium |  |  | R - CP | I | C
| 88 | 12 - INTERFACES | OneOC - Clerk Review Module | w_ct_m_oneoc_interface | Medium |  |  | R - CP | I | I
10 | 44 | 7 - COUNTER | Counter Payment | w_ct_m_counter | Very High |  |  | R - CP | C | R
| 44.1 | 7 - COUNTER | Receipts (many flavors) |  | Medium |  |  | R - CP | C | R
| 44.2 | 7 - COUNTER | Bail Forfeiture / Traffic School Payment Plans | w_ct_r_agree_pay_bf | Low |  |  | R - CP | C | R
| 44.3 | 7 - COUNTER | Accept Payment | w_ct_r_payment | Medium |  |  | R - CP | C | R
| 44.4 | 7 - COUNTER | Notes | w_ct_r_cmmn_note | Low |  |  | R - CP | C | R
11 | 47 | 7 - COUNTER | Open Cashier Session | w_ct_m_cashier_open_session | Low |  |  | R - CP | C | R
| 43 | 7 - COUNTER | Cashier Reconciliation | w_ct_m_cashier_recon | Low High |  |  | R - CP | C | R
| 45 | 7 - COUNTER | Multi-Case Payment | w_ct_m_fscl_multi_case_payment | Low High |  |  | C | C | R
| 46 | 7 - COUNTER | Non-Case Payment | w_ct_m_noncase_pymt | Low |  |  | R - CP | C | I
| 48 | 7 - COUNTER | TS Completion | w_ct_m_mark_ts_complete | Low High |  |  | R - CP | I | C
| 49 | 7 - COUNTER | Victim Restitution Notice | w_ct_m_vr_notice | Low High |  |  | R - CP | C | C
| 67 | 10 - FISCAL | Victim Restitution Approval | w_ct_m_fscl_vr_apprv | Low |  |  | I | R | I
| 40 | 7 - COUNTER | Cash Bail Notice | w_ct_m_bail_bond_notice | Medium High |  |  | C | R | I
12 | 19 | 4 - CASE | Citation Batches / Batch Entry | w_ct_m_cite_batch_entry | Medium High |  |  | R - CP | I | I
| 20 | 4 - CASE | Citation Entry | w_ct_m_case_citation_entry | Medium High |  |  | R - CP | I | I
| 23 | 4 - CASE | Missing Complaint | w_ct_m_case_missing_complaint | Medium High |  |  | I | R | I
13 | 16 | 4 - CASE | Case Maintenance | w_ct_m_case_maint | Very High |  |  | R - CP | C | C
| 16.1 | 4 - CASE | Vision Public Case - Input | w_ct_r_public_case_input | Low |  |  | R - CP | I | I
| 16.2 | 4 - CASE | Person Information Select | w_ct_m_person_select | Low High |  |  | R - CP | C | C
| 16.3 | 4 - CASE | Unavailable Court Dates | w_ct_r_unavailable_dates | Low |  |  | R - CP | I | C
| 16.4 | 4 - CASE | Case Dates | w_ct_r_cal_case_dates | Low |  |  | R - CP | I | C
| 16.5 | 4 - CASE | Other Cases | w_ct_r_cal_other_cases | Low |  |  | R - CP | I | I
| 24 | 4 - CASE | NCIC Case Initiation | w_ct_m_case_maint_ncic | Medium |  |  | R - CP | I | I
14 | 150 | 21 - WARRANTS | Pending Warrant Review | w_ct_m_warrant_review | Medium |  |  | R - CP | I | I
| 151 | 21 - WARRANTS | Warrant Image Viewer | w_ct_m_warrant_images | Low High |  |  | R - CP | I | I
| 152 | 21 - WARRANTS | Warrant Maintenance | w_ct_m_warrant_signal_mon | Medium |  |  | R - CP | I | I
| 154 | 21 - WARRANTS | Warrant Reports | w_ct_r_main_report | Medium |  |  | R - CP | I | I
| 153 | 21 - WARRANTS | Warrant Maintenance (CTS) (Warrant Signal Audit) | w_ct_m_warrant_signal_audit | Medium |  | X
| 155 | 21 - WARRANTS | Warrant XML Viewer (CTS) | w_ct_m_warrant_awss_xml | Low High |  | X
15 | 41 | 7 - COUNTER | Bail Entry | w_ct_m_bail_maint | Medium High |  |  | R - CP | R | R
| 41.1 | 7 - COUNTER | Agency Unit Address List (2-Bail Bond button) | w_ct_r_agency_unit_addrs_change | Low High |  |  | R - CP | R | R
| 58 | 10 - FISCAL | Bail Maintenance | w_ct_m_bail_maint | Medium High |  |  | I | R | I
| 61 | 10 - FISCAL | Check Approval | w_ct_m_fscl_chk_apprv | Medium |  |  | I | R | I
| 61.1 | 10 - FISCAL | Specify Check Number | w_ct_r_fscl_chk_nbr | Low |  |  | I | R | I
| 61.2 | 10 - FISCAL | Print Checks | w_ct_r_fscl_prnt_chks | Low |  |  | I | R | I
| 62 | 10 - FISCAL | Check Maintenance | w_ct_m_fscl_chk_maint | Medium |  |  | I | R | I
| 59 | 10 - FISCAL | Case Distribution Override | w_ct_m_fscl_dist_override | Medium |  |  | I | R | I
| 64 | 10 - FISCAL | Misapplications/Voids | w_ct_m_fscl_pmt_misapp_void | Medium |  |  | I | R | R
| 64.1 | 10 - FISCAL | w_ct_r_fiscal_batch_cases | w_ct_r_fiscal_batch_cases | Low High |  |  | I | R | I
| 65 | 10 - FISCAL | Reapply Payment | w_ct_m_fscl_reapp_remit | Low High |  |  | I | R | I
| 66 | 10 - FISCAL | Reversals | w_ct_m_fscl_pmt_reversals | Medium |  |  | I | R | I
| 66.1 | 10 - FISCAL | w_ct_r_fiscal_multi_cases_reversal | w_ct_r_fiscal_multi_cases_reversal | Low |  |  | I | R | I
16 | 63 | 10 - FISCAL | Fiscal Case Analysis | w_ct_m_fiscal_case_analysis | Medium High |  |  | I | R | C
| 68 | 10 - FISCAL | Summary Judgment | w_ct_m_summary_judgement | Medium |  |  | I | R | I
| 139 | 20 - TABLES | Fee Schedule | w_ct_m_fscl_fee_sched | Medium |  |  | I | R | I
| 143 | 20 - TABLES | PA Schedule Maintenance | w_ct_m_maint_pa_sched | Low |  |  | I | R | I
17 | 27 | 5 - COLLECTIONS | Collections | w_ct_m_coll_collections | Very High |  |  | I | I | R
| 32 | 5 - COLLECTIONS | Financial Evaluation | w_ct_m_coll_fin_eval_list | Low High |  |  | I | I | R
18 | 102 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium |  |  | R - CP | I | I
| 103 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium |  |  | R - CP | I | I
| 104 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium |  |  | R - CP | I | I
| 111 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium |  |  | I | R | I
19 | 105 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High |  |  | R - CP | I | I
| 105.1 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low |  |  | R - CP | I | I
| 106 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High |  |  | R - CP | I | I
| 107 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low |  |  | R - CP | I | I
| 108 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High |  |  | R - CP | I | I
20 | 69 | 11 - FISCAL MAINTENANCE | Bail Distribution Schedule | w_ct_m_fscl_bail_dist_sched | Medium High |  |  | I | R | I
| 70 | 11 - FISCAL MAINTENANCE | Base Distribution Xref | w_ct_m_fscl_base_dist_xref | Low High |  |  | I | R | I
| 71 | 11 - FISCAL MAINTENANCE | Bondsman / Surety | w_ct_m_bondsman_surety | Medium |  |  | I | R | I
| 72 | 11 - FISCAL MAINTENANCE | Chart of Accounts | w_ct_m_fscl_chart_of_accts | Low |  |  | I | R | I
| 73 | 11 - FISCAL MAINTENANCE | Cost of Collections | w_ct_m_fscl_cost_of_collections | Low High |  |  | I | R | I
| 74 | 11 - FISCAL MAINTENANCE | Fee Distribution Schedule | w_ct_m_fscl_fee_dist_sched | Low High |  |  | I | R | I
21 | 75 | 11 - FISCAL MAINTENANCE | Fund Maintenance | w_ct_m_fscl_fund_maint | Low High |  |  | I | R | I
| 76 | 11 - FISCAL MAINTENANCE | PA Distribution Schedule | w_ct_m_fscl_pa_dist_sched | Low High |  |  | I | R | I
| 77 | 11 - FISCAL MAINTENANCE | PA Distribution Xref | w_ct_m_fscl_dist_xref | Low |  |  | I | R | I
| 78 | 11 - FISCAL MAINTENANCE | Special Distribution Schedule | w_ct_m_fscl_spl_dist_sched | Low High |  |  | I | R | I
| 79 | 11 - FISCAL MAINTENANCE | VR Distribution Schedule | w_ct_m_fscl_vr_dist_sched | Low |  |  | I | R | I
22 | 82 | 12 - INTERFACES | DMV Abstract on Demand | w_ct_m_dmv_abstract_on_demand | Low |  |  | R - IM | I | I
| 83 | 12 - INTERFACES | DMV Admin Transactions | w_ct_m_dmv_admin_tran | Low High |  |  | R - IM | I | I
| 84 | 12 - INTERFACES | DMV Error Cases Report | w_ct_m_dmv_error_queue_mon | Medium |  |  | R - IM | I | I
| 85 | 12 - INTERFACES | DMV Error Maintenance | w_ct_m_dmv_abstract_maint | Medium High |  |  | R - IM | I | I
| 86 | 12 - INTERFACES | DMV Prior Missing Report | w_ct_m_dmv_priors_missing_cases | Low |  |  | R - IM | I | I
23 | 87 | 12 - INTERFACES | DOJ Interface | w_ct_m_intf_doj_review | High |  |  | R - IM | I | I
| 87.1 | 12 - INTERFACES | DOJ Abstract | w_ct_r_doj_abstract_viewer | Low High |  |  | R - IM | I | I
| 89 | 13 - JBSIS | JBSIS Audit Report | w_ct_m_jbsis_audit_report | Medium |  |  | R - IM | I | I
| 91 | 13 - JBSIS | JBSIS Report Defn. | w_ct_m_jbsis_report_detail | Low High |  |  | R - IM | I | I
| 92 | 13 - JBSIS | JBSIS Reporting | w_ct_jbsis_manrpt | Medium High |  |  | R - IM | I | I
| 92.1 | 13 - JBSIS | JBSIS Case Listing | w_ct_jbsis_case_person | Low High |  |  | R - IM | I | I
| 3 | 1 - ADMIN | Excel Batch Processing | w_ct_m_xl_batch_processing | Medium High |  |  | R - IM | I | I
24 | 115 | 18 - SCHEDULE MAINTENANCE | Special Schedule | w_ct_m_fscl_special_schedule | Low |  |  | R - IM | C | I
| 116 | 18 - SCHEDULE MAINTENANCE | Speed Schedule | w_ct_m_fscl_speed_sched | Low High |  |  | R - IM | C | I
| 116.1 | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule | w_ct_r_fscl_speed_sched | Low |  |  | R - IM | C | I
| 117 | 18 - SCHEDULE MAINTENANCE | Speed Schedule 2 | w_ct_m_fscl_speed_sched_2 | Low High |  |  | R - IM | C | I
| 117.1 | 18 - SCHEDULE MAINTENANCE | Copy Existing Speed Schedule (Speed Sched2) | w_ct_r_fscl_speed_sched_2 | Low |  |  | R - IM | C | I
| 126 | 20 - TABLES | Calendar Plan Maintenance | w_ct_m_calendar_plan | Medium High |  |  | R - IM | I | I
25 | 135 | 20 - TABLES | Docket Code Maintenance | w_ct_m_docket_code_maint | Medium High |  | X
| 135.1 | 20 - TABLES | w_ct_r_docket_codes | w_ct_r_docket_codes | Low |  | X
| 135.2 | 20 - TABLES | w_ct_r_lookup_nbr | w_ct_r_lookup_nbr | Low |  | X
| 132 | 20 - TABLES | Docket Code Macro Configuration | w_ct_m_docket_macro | Low High |  |  | R - IM | I | I
| 133 | 20 - TABLES | Docket Code Macro Maintenance | w_ct_m_docket_macro_maint | Medium High |  |  | R - IM | I | I
| 133.1 | 20 - TABLES | Docket Macro Preview | w_ct_r_dckt_macro_preview | Low |  |  | R - IM | I | I
| 134 | 20 - TABLES | Docket Code Macro Mover | w_ct_m_docket_macro_move | Medium |  |  | R - IM | I | I
| 136 | 20 - TABLES | Docket Code Reference | w_ct_m_docket_codes_reference | Low |  |  | R - IM | I | I
26 | 15 | 4 - CASE | Case Backup and Restore | w_ct_m_case_backup_trg | Low High |  |  | R - IM | I | I
| 18 | 4 - CASE | Case Transfer | w_ct_m_case_transfer_cst | Low High |  |  | R - IM | C | C
| 22 | 4 - CASE | Mass Case/Calendar Copy | w_ct_m_mass_case_copy | Low High |  |  | R - CT | I | I
27 | 113.1 | 17 - REPORTS | Open Cases Report | w_ct_m_open_cases | Medium |  |  | R - CP | I | R
| 114 | 17 - REPORTS | State Prison Abstracts | w_ct_m_prsn_abstract | Medium High |  |  | R - CP | I | I
| 113.6 | 17 - REPORTS | Case Calendar Summary | w_ct_m_cal_sum | Medium |  |  | R - CT | I | I
| 113.2 | 17 - REPORTS | Bail Bond Activity Report | w_ct_r_report_builder | Medium |  |  | I | R | I
| 113.3 | 17 - REPORTS | Bail Bond Summary Judgment | w_ct_r_report_builder | Medium |  |  | I | R | I
| 113.4 | 17 - REPORTS | Bail Forfeiture Report | w_ct_r_report_builder | Medium |  |  | I | R | I
| 113.5 | 17 - REPORTS | Summary Judgment Bail Bonds Payment Due | w_ct_r_report_builder | Medium |  |  | I | R | I
| 113.7 | 17 - REPORTS | Case Payment Activity Query | w_ct_r_report_builder | Medium |  |  | C | R | I
| 113.8 | 17 - REPORTS | Cash Bail Forfeiture Notice | w_ct_r_report_builder | Medium |  |  | C | R | I
| 112 | 17 - REPORTS | Monthly Funding Report | w_ct_m_fscl_month_fund_report | Medium |  |  | I | R | I
28 | 26 | 5 - COLLECTIONS | Campaign Maintenance | w_ct_m_coll_campaign_maint | Low High |  |  | I | I | R
| 28 | 5 - COLLECTIONS | Collections Campaign Queue | w_ct_m_coll_campaign_queue | Medium |  |  | I | I | R | L:\ drive
| 29 | 5 - COLLECTIONS | Collections Person Interface | w_ct_m_coll_person_interface | Medium |  |  | I | I | R | L:\ drive
29 | 33 | 5 - COLLECTIONS | FTBCOD Interface | w_ct_m_case_ftbcod_select | High |  |  | I | I | R | L:\ drive
| 34 | 5 - COLLECTIONS | FTBCOD Payment Processor | w_ct_m_ftbcod_payment | Medium High |  |  | I | I | R | L:\ drive
| 34.1 | 5 - COLLECTIONS | Import Action File (Select button) | w_ct_r_coll_ftbcod_import_actions | Low |  |  | I | I | R | L:\ drive
| 34.2 | 5 - COLLECTIONS | Import Claim Schedule File (FTBCOD) | w_ct_r_ftbcod_import_cs | Low |  |  | I | I | R | L:\ drive
| 35 | 5 - COLLECTIONS | FTBTI Interface | w_ct_m_coll_ftbti_interface | High |  |  | I | I | R | L:\ drive
| 36 | 5 - COLLECTIONS | FTBTI Payment Processor | w_ct_m_ftbti_payment | Medium High |  |  | I | I | R | L:\ drive
| 36.1 | 5 - COLLECTIONS | Import Claim Schedule File (FTBTI) | w_ct_r_cmmn_file_search | Low |  |  | I | I | R | L:\ drive
| 36.2 | 5 - COLLECTIONS | List Search | w_ct_r_cmmn_list_search | Low |  |  | I | I | R | L:\ drive
30 | 38 | 5 - COLLECTIONS | OCV Return | w_ct_m_ocv_file_load | Low High |  |  | I | I | R | L:\ drive
| 37 | 5 - COLLECTIONS | OCV Payment Processor | w_ct_m_ocv_payment | High |  |  | I | I | R
| 81 | 12 - INTERFACES | Check Auditor/Controller | w_ct_m_fscl_audit_controller | Low High |  |  | I | R | I | L:\ drive
31 | 50 | 8 - COURTROOM | Courtroom / Admin Minutes Entry | w_ct_courtroom | Very High |  |  | R - CT | C | R
| 50.1 | 8 - COURTROOM | Docket Code Help | w_ct_doc_help_rsp | Low High |  |  | R - CT | C | R
| 50.2 | 8 - COURTROOM | Multi-Case Entry | w_ct_doc_multicase | Medium |  |  | R - CT | I | R
| 50.3 | 8 - COURTROOM | Print Imaging Barcode | w_ct_r_barcode_current_hrg | Low High |  |  | R - CT | C | R
| 50.4 | 8 - COURTROOM | Print Imaging Barcode Sheet (reprint) | w_ct_r_barcode_print | Low High |  |  | R - CT | C | R
| 50.5 | 8 - COURTROOM | Extended Text Entry Window | w_ct_r_ctrs_dckt_text | Low |  |  | R - CT | C | R
| 50.6 | 8 - COURTROOM | Courtroom Print | w_ct_r_dckt_report_printing | Low High |  |  | R - CT | C | R
| 53.1 | 8 - COURTROOM | CIS Sheets (16 Flavors) |  | Very High |  |  | R - CT | C | C
| 53.2 | 8 - COURTROOM | PDF Viewer from Minutes | w_ct_c_pdf_viewer | Low High |  |  | R - CT | C | R
| 53.3 | 8 - COURTROOM | VCJIS - Court Reports Preview | w_ct_r_dckt_preview_docket_rpt | Low High |  |  | R - CT | I | C
32 | 54 | 8 - COURTROOM | MOCS | w_ct_m_mocs | Very High |  |  | R - CT | I | I
| 54.1 | 8 - COURTROOM | Docket Selection ( MOCS) | w_ct_r_mocs_dkt_entry | Medium |  |  | R - CT | I | I
| 54.2 | 8 - COURTROOM | MOCS Multi Case Entry | w_ct_r_mocs_multi | Very High |  |  | R - CT | I | I
| 130.1 | 20 - TABLES | MOCS Docket Definition | w_ct_m_mocs_dkt_defn | Medium |  | X
33 | 121 | 19 - SECURITY | Security Admin | w_ct_r_security_admin | Medium High |  | X
| 101 | 15 - PERSON | Sealed Access | w_ct_r_security_admin | Medium High |  |  | R - IM | I | I
| 5 | 1 - ADMIN | Person Delete | w_ct_m_person_delete | Low High |  | X
| 7 | 1 - ADMIN | Vlan IP ranges | w_ct_m_vlan_ip_ranges | Low High |  | X
34 | 118 | 19 - SECURITY | Advanced Menu Manager | w_ct_m_menu_full | Medium |  | X
| 119 | 19 - SECURITY | Basic Menu Manager | w_ct_m_menu_basic | Medium |  | X
| 119.1 | 19 - SECURITY | Vision Menu Profile Report | w_ct_r_menu_profile_report | Low |  | X
| 120 | 19 - SECURITY | Menu Admin | w_ct_r_menu_admin | Medium |  | X
35 | 127 | 20 - TABLES | Code Mover | w_ct_m_code_mover | Low High |  | X
| 140 | 20 - TABLES | Generic Notice Maintenance | w_ct_m_letter_maint | Low High |  | X
| 142 | 20 - TABLES | Letter Maintenance | w_ct_m_letter_maint_lm | Low High |  | X
| 156 | GENERAL | Log on Window (initial loading of config items) |  | Medium High |  |  | R - IM | C | R
| 157 | GENERAL | Menu Actions |  | Medium |  |  | R - IM | C | R