## Sprint Planning
Sprint # | Subtask | W# | Menu Group | Window / Subscreen Name | Object Name | Grouping | Dev | BSA | DEV LEAD LOE | Orig LOE | Status |  | Subtask Status
SG2 | VISAR-7419 | 8 | 3 - CALENDARING | Calendar List | w_ct_m_cal_list | Medium | NV | BY | 25 | 18.5 | QA |  | Active
SG2 | VISAR-7420 | 8.1 | 3 - CALENDARING | Post-Conviction Worksheet Report | w_ct_r_pcw | Medium | NV | BY | 15 | 18.5 | QA |  | Active
SG5 | VISAR-7557 | 17 | 4 - CASE | Case Summary | w_ct_m_case_summary | Medium High | SM |  | 26 | 26 | BACKLOG |  | Ready
SG5 | VISAR-7580 | 17.1 | 4 - CASE | Close Elig? Button | w_ct_r_case_closure_eligible | Low High | SM |  | 5 | 13 | BACKLOG |  | Ready
SG5 | VISAR-7563 | 17.2 | 4 - CASE | Bail Schedule Maintenance Response | w_ct_r_fscl_bail_sched_maint_response | Low High | SM | BY | 0.5 | 13 | BACKLOG |  | Ready
SG6 | VISAR-7564 | 72 | 11 - FISCAL MAINTENANCE | Chart of Accounts | w_ct_m_fscl_chart_of_accts | Low | CN |  | 5 | 5.5 | BACKLOG |  | Ready
SG8 | VISAR-7544 | 73 | 11 - FISCAL MAINTENANCE | Cost of Collections | w_ct_m_fscl_cost_of_collections | Low High | KH | DC | 5 | 13 | QA |  | Active
SG7 | VISAR-7565 | 74 | 11 - FISCAL MAINTENANCE | Fee Distribution Schedule | w_ct_m_fscl_fee_dist_sched | Low High | NV |  | 10 | 13 | BACKLOG | Do 1st same dev | Ready
SG7 | VISAR-7566 | 75 | 11 - FISCAL MAINTENANCE | Fund Maintenance | w_ct_m_fscl_fund_maint | Low High | NV |  | 8 | 13 | BACKLOG | Do 2nd same dev | Ready
SG6 | VISAR-7567 | 77 | 11 - FISCAL MAINTENANCE | PA Distribution Xref | w_ct_m_fscl_dist_xref | Low | NV |  | 7 | 5.5 | BACKLOG | Do 3rd same dev | Ready
SG8 | VISAR-7568 | 93 | 15 - PERSON | Attorney Maintenance | w_ct_m_attorney | Medium |  |  |  | 18.5 | BACKLOG |  | Planning
SG8 | VISAR-7569 | 94 | 15 - PERSON | Interpreters Maintenance | w_ct_m_interpreters | Low High |  |  |  | 13 | BACKLOG |  | Planning
SG8 | VISAR-7570 | 94.1 | 15 - PERSON | Interpreters in System | w_ct_r_interpreters_lookup | Low |  |  |  | 5.5 | BACKLOG |  | Planning
SG8 | VISAR-7571 | 94.2 | 15 - PERSON | Interpreter Remarks(Ctrl+Alt+T under Remarks) | w_ct_r_interpreter_remarks | Low |  |  |  | 5.5 | BACKLOG |  | Planning
SG8 | VISAR-7572 | 95 | 15 - PERSON | Multi-Person Maintenance | w_ct_m_multi_person_maint | Low High |  |  |  | 13 | BACKLOG |  | Planning
SG8 | VISAR-7573 | 95.1 | 15 - PERSON | Multi-Person Maintenance Datafix Report | w_ct_r_mpm_report | Low |  |  |  | 5.5 | BACKLOG |  | Planning
SG3 | VISAR-7443 | 102 | 16 - RECORDS | Batch Purge | w_ct_m_purged_cases | Medium | SM |  | 8 | 18.5 | INPROG |  | Active
SG3 | VISAR-7444 | 103 | 16 - RECORDS | Calendar File Location | w_ct_s_rcds_cal_loc | Medium | CN | DC | 10 | 18.5 | INPROG |  | Active
SG3 | VISAR-7445 | 104 | 16 - RECORDS | Case File Purge | w_ct_m_case_file_purge | Medium | SM | BY | 8 | 18.5 |  |  | Active
SG4 | VISAR-7446 | 105 | 16 - RECORDS | File Location | w_ct_s_rcds_location | Low High | CN |  | 8 | 13 |  |  | Ready
SG4 | VISAR-7447 | 105.1 | 16 - RECORDS | Location History | w_ct_s_rcds_location_history | Low | CN | DC | 4 | 5.5 |  |  | Active
SG4 | VISAR-7448 | 106 | 16 - RECORDS | File Request | w_ct_s_rcds_request | Low High | SM |  | 5 | 13 |  |  | Ready
SG4 | VISAR-7449 | 107 | 16 - RECORDS | File Request Inquiry | w_ct_s_rcds_request_inquiry | Low | SM |  | 5 | 5.5 |  |  | Ready
SG4 | VISAR-7450 | 108 | 16 - RECORDS | File Request Maintenance | w_ct_s_rcds_request_maint | Low High | CN |  | 5 | 13 |  |  | Active
SG4 | VISAR-7451 | 109 | 16 - RECORDS | Image Maintenance | w_ct_m_case_docket_image | Medium | NV | BY | 8 | 18.5 |  |  | Ready
SG4 | VISAR-7452 | 109.1 | 16 - RECORDS | Docket Code Lookup | w_ct_r_case_docket | Low | NV | BY | 5 | 5.5 |  |  | Ready
SG4 | VISAR-7453 | 110 | 16 - RECORDS | Image Viewer | w_ct_m_image_viewer | Medium | NV | BY | 0.5 | 18.5 |  |  | Ready
SG3 | VISAR-7454 | 111 | 16 - RECORDS | Missing Complaints Purge | w_ct_m_missing_complaints_purge | Medium | SM |  | 8 | 18.5 |  |  | Ready
SG6 | VISAR-7574 | 150 | 21 - WARRANTS | Pending Warrant Review | w_ct_m_warrant_review | Medium | [6 empty] | Planning
SG6 | VISAR-7575 | 151 | 21 - WARRANTS | Warrant Image Viewer | w_ct_m_warrant_images | Low High | [6 empty] | Planning
SG6 | VISAR-7576 | 152 | 21 - WARRANTS | Warrant Maintenance | w_ct_m_warrant_signal_mon | Medium | [6 empty] | Planning
SG7 | VISAR-7577 | 153 | 21 - WARRANTS | Warrant Maintenance (CTS) (Warrant Signal Audit) | w_ct_m_warrant_signal_audit | Medium | [6 empty] | Planning
SG7 | VISAR-7578 | 154 | 21 - WARRANTS | Warrant Reports | w_ct_r_main_report | Medium | [6 empty] | Planning
SG7 | VISAR-7579 | 155 | 21 - WARRANTS | Warrant XML Viewer (CTS) | w_ct_m_warrant_awss_xml | Low High | [6 empty] | Planning
| VISAR-7556 | NEW | TABLES | VNG Reports UI | w_ct_m_vng_reports | Low Medium | KH |  | 5 |  |  |  | Active