## ITEMS
ID | Window | TYPE | Window Defect ID | Date Tested | Issue | Scenario | Latest Update | Status | Syncfusion Ticket - if applicable
1 | Error Codes | TECH DEBT | 14 | 2025-10-21 | Adding multiple blank rows | 1. Add 3 blank rows 2. Right click and delete 3. Deletes all blank rows | 11/18/25: Removed ability to add multiple rows at once. | Added
2 | Job Error Log | TECH DEBT | 22 | 2025-10-22 | Window Resizing | Decreasing the window size, then increasing the window size causes the alert type column to display twice. | 10/29/25: leave as-is for now (move to different category to be addressed later) | Added
3 | Event Codes | STAKEHOLDER REVIEW | 17 | 2025-11-03 | Cannot add multiple empty rows | Only one row can be added at a time; user has to save changes in 1 row then add for additional row; current window allows for multiple rows to be entered | 11/03/25: separate discussion with stakeholders - devs to update functionality (single click opens row in edit mode) | Added
4 | All | STAKEHOLDER REVIEW | N/A | N/A | Screenshot updates in procedures | Due to new UI changes, not sure if IMPACT needs to update all procedures before NG Deployment? | 12/02/25: per Bail Schedule QA review meeting with Kristen, looking to explore option of updating screenshots as procedures are requested to be updated; also looking into a "help tool" advising users on basic functions (e.g., add row, edit row) | Resolved
5 | Bail Schedule | EHNHANCEMENT | N/A | N/A | Clear button for violation search results | Request by user to add clear button after search result is returned; current workaround is to highlight and delete selection | 12/02/25: noted as enhancment per Bail Schedule QA review meeting with Kristen | Added
6 | Bail Schedule | EHNHANCEMENT | N/A | N/A | Advanced Search option for violations | Request by user to search for violations using partial match (e.g., "231" would return any statute that has a section number matching entered value); currently this functionality does not exist | 12/02/25: noted as enhancement per Bail Schedule QA review meeting with Kristen | Added
7 | Code Entry | TECH DEBT | N/A | N/A | Code Entry does not immediately show codes moved via Code Mover | Using Code Mover from QA to PROD, user has to manually clear cache or wait 30 minutes for cache to clear | 03/05/26: interim solution is to clear cache | Added
8 | Parm Lookups | TECH DEBT | 32 | 2026-04-23 | Dropdown fields do not work when user uses minimized or 'Tile Horizontal' view | 1. Open PL Blazor Window 2. Open another Vision window 3. Select Window, Tile Horizontal 4. Enter edit mode 5. Modify Date or DW Object dropdown selection 6. Exit edit mode - LOOKUP_SEQ section expands and the Description section is no longer visible unless you resize the window. Window freezes | 04/23/26: Devs addressed the defect causing the dropdown to appear in the incorrect spot. Devs will look into the resizing issue more if it occurs for external windows. | Added
9 | Parm Lookups | TECH DEBT | 43 | 2026-04-23 | Window does not load data | 1. Open PL Blazor Window 2. Double Click an associated docket code 3. Close the PL Blazor Window with the Docket Code Maintenance window still selected 4. Open PL Blazor Window through Main > Tables > Parm Lookups - window loads with no data. See Screenshot ID 46. | 04/23/26: Devs will look into this issue if it occurs for other windows or once the issue can be consistently recreated. | Added
10 | SP Registry | TECH DEBT | 3 | 2026-04-27 | Vertical scroll bar disappears when the window is 50% of the vision width or smaller | 1. Open SP Registry and another Vision window 2. Select Window > Tile Vertical - scroll bar disappears, but the scroll functionality remains | 5/13/26: The defect reported was that the right side column filter cut off. As part of this fix, the right side scroll bar no longer works when the window is minimized. | Added
11 | SP Registry | TECH DEBT | 14 / 39 | 2026-06-18 | F3 Refresh causes column misalignment | Scenario A: SP Registry Column Shift 1. Add a row in SP registry tab 2. Open Edits or Updates tab 3. F3 Refresh the window 4. Select ""Yes"" for the save pending changes message 5. Open SP registry tab - Column header is no longer aligned Scenario B: Edits/ Updates Column Shift 1. Select Edits or Updates tabs 2. Select a category 3. Open SPs tab 4. Add row in SPs tab 5. Save Changes, or F3 Refresh to save changes 5. Open Edits or Updates tab - Column header is no longer aligned Scenario C: Expanded column width 1. Open SPs tab 2. Expand SP Name column width 3. F3 Refresh - SP Name column header is width than the column row width | 5/19/26: Devs reported ResetPersistDataAsync is bugged and submitted a ticket. 6/9/26: Syncfusion deployed a fix that was worse than the original defect. Devs submitted another support ticket. 6/18/26: Scenario C identified | Added | Original Ticket: https://support.syncfusion.com/support/tickets/841479
12 | SP Registry | TECH DEBT | 38 | 2026-06-18 | More options than configured appear | 1. Right click a parent row on any tab 2. Continue right clicking different rows quickly - eventually, more context menu options appear than the expected options for a brief moment | 6/18/26: This issue happens in all parent/ child windows, including code entries and event codes. Devs created Syncfusion ticket. | Added | https://support.syncfusion.com/support/tickets/849532
13 | Exhibit List | TECH DEBT | 1 |  | NG Exhibit List Search dialog box allows user to interact with PB menu/2nd row icons | Opening the Exhibit List window displays the Exhibit List Search dialog box, which locks the rest of the application until the user enters a value or closes the dialog. PB then releases the lock and restores normal application interaction. NG Exhibit List Search does not lock the rest of the Vision application | 08/18/26: issue also occurs in Minutes with Sealed Cases message as message is NG window; decision made to leave as-is in 08/18 meeting | Added
14 | Minutes | TECH DEBT |  | 2026-10-08 | Custom column filter autopopulates values | Custom filters autopopulate the values in the column. The default starts with filter allows for free text | 10/8/26: Santiago created support ticket 879957 for this issue. Added comment that this applies to all custom filters, not the contains filter 10/19/26: Issue resolved for Text column of the minutes window. If this change is needed for other windows, it needs to be set up on a column by column basis. Needs further discussion on if this should be updated in the base class, or if we should update certain columns only | Pending Discussion | https://support.syncfusion.com/support/tickets/879957/