## Vision NG Metrics
Stage 1 Date | Sprint | Window # | VISAR | Dev | QA/ BSA | Window Name | Functional Grouping | Latest Status | Component Group | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Total Dev Hrs | Total QA Hours | #QA Bug Major | #QA Bug Minor | #QA Bug Regression | #QA Cycle | Open Defects | No Action Defects | Resolved Defects | QA Pass Date | UAT Start Date | Ready for Deployment | Deployed | Deploy Date | Notes
CANCELED |  | 4 | VISAR-7333 | CN |  | Officer Consolidate | Low High
CANCELED |  | 52 |  |  | BY | Minutes - Generic Notice |  | Deactivated | Window deactivated 8/27
|  | 6 | VISAR-6499 | SM | MU | Purge Duplicates | Low | Deployed to Production | F1 | 7 | 8 | 9 | 16 |  | 40 | 12 | 4 | 10 | 0 | 2 | 0 | 1 | 13 | 2026-04-22 |  |  | Build 5.02 | 2026-05-05
2025-09-24 |  | 128 | VISAR-6190 | NV | BY | Code Entry | Low High | Deployed to Production |  | 42 | 32 | 11 | 71 |  | 151 | 71 | 28 | 62 | 6 | 9 | 0 | 29 | 69 | 2026-02-02 |  |  | Build 5.01 | 2026-02-05
|  | 129 | VISAR-6450 | JL | BY | CodesXref Maintenance | Medium | Deployed to Production |  | 4 | 12 | 2 | 4 |  | 22 | 4 | 2 | 10 | 0 | 2 | 0 | 6 | 5 | 2026-05-27 |  |  | Build 5.03 | 2026-06-30
2025-10-23 |  | 130 | VISAR-6274 | SM | MU | Court Control | Low High | Deployed to Production | F1 | 25 | 17 | 39 | 43 |  | 63 | 19 | 27 | 13 | 6 | 5 | 0 | 1 | 45 | 2026-04-30 |  |  | Pre-release | 2026-05-05
2025-09-16 |  | 137 | VISAR-6167 | SM | MU | Error Code | Low | Deployed to Production |  | 14 | 21 | 12 | 33 |  | 49 | 23 | 23 | 28 | 7 | 10 | 0 | 7 | 21 | 2026-02-03 |  |  | Pre-release | 2026-02-05
2025-10-06 |  | 138 | VISAR-6217 | SM | MU | Event Codes | Low | Deployed to Production |  | 44 | 24 | 11 | 35 |  | 68 | 21 | 24 | 18 | 2 | 9 | 0 | 6 | 38 | 2026-02-03 |  |  | Pre-release | 2026-02-05
2025-09-24 |  | 141 | VISAR-6189 | SM | BY | Job Error Log | Low | Deployed to Production |  | 18.5 | 17 | 10 | 32 |  | 33 | 31 | 15 | 39 | 3 | 5 | 0 | 36 | 23 | 2026-01-14 |  |  | Pre-release | 2026-02-05
2025-10-15 |  | 144 | VISAR-6254 | NV | BY | Parm Lookups | Low High | Deployed to Production |  | 26 | 24 | 21 | 31 |  | 102 | 31.5 | 13 | 29 | 3 | 6 | 0 | 9 | 36 | 2026-04-30 |  |  | Pre-release | 2026-05-05
2026-04-03 |  | 145 | VISAR-6848 | NV | CL | Sentence Workflow Maintanence | Medium-High | Deployed to Production |  | 20 | 24 | 2 | 26 |  | 72 | 34 | 5 | 16 | 0 | 4 | 0 | 5 | 17 | 2026-07-16 |  | Y | 1.0 | 2026-08-27
|  | 146 | VISAR-6316 | NV | BY | SP Registry | Low High | Deployed to Production |  | 22 | 20 | 6 | 22 |  | 70 | 21.5 | 13 | 24 | 3 | 5 | 0 | 7 | 32 | 2026-06-22 |  |  | Pre-release2 | 2026-06-30
|  | 125 | VISAR-6168 | JL | MU | Bail Schedule | Medium High | Deployed to Production |  | 75 | 35 | 20 | 45 |  | 175 | 31 | 29 | 26 | 3 | 3 | 0 | 6 | 52 | 2026-04-17 | 2026-04-29 | Y | 1.0 | 2026-08-27
|  | 125.1 |  |  | MU | Bail Schedule - Review | [19 empty] | Y
|  | 149 | VISAR-6474 | NV | MU | Violations | Medium | Deployed to Production |  | 20 | 30 | 6 | 28 |  | 84 | 24 | 21 | 9 | 2 | 5 | 0 | 1 | 31 | 2026-07-17 | 2026-07-22 | Y | 1.0 | 2026-08-27
|  | 51 | VISAR-6475 | SM | BY | Courtroom Setup | Low High | Deployed to Production | F1 | 9 | 9 | 2 | 25 |  | 45 | 14 | 7 | 21 | 4 | 7 | 0 | 2 | 30 | 5/15/2026 7/9/2026 | 2026-05-20 | Y | 1.0 | 2026-08-27
2026-01-13 |  | 148 | VISAR-6544 | NV | MU | Violation Agency X-Ref | Low High | Deployed to Production |  | 30 | 3 | 4 | 6 |  | 43 | 17 | 13 | 2 | 0 | 3 | 0 | 1 | 14 | 2026-07-13 | 2026-07-22 | Y | 1.0 | 2026-08-27
2026-03-25 |  | 60 | VISAR-6797 | NV | MU | Case Payment History |  | Deployed to Production |  | 24 | 12 | 4 | 21 |  | 61 | 17 | 11 | 12 | 4 | 6 | 0 | 2 | 25 | 2026-06-05 | 2026-06-05 | Y | 1.0 | 2026-08-27
|  | 122 | VISAR-6895 | NV | BY | Unlock Case | Low | Deployed to Production |  | 5 | 8 | 2 | 1 |  | 16 | 4 | 3 | 3 | 0 | 2 | 0 | 0 | 6 | 2026-05-28 | 2026-06-03 | Y | 1.0 | 2026-08-27
2026-07-25 | sprint2 | 55 | VISAR-7188 | JL | DC | Exhibit List | Low-Medium | UAT Ready |  | 12 | 20 | 20 | 2 |  |  | 19 | 3 | 28 | 0 | 3 | 25 | 4 | 26 | 2026-09-04
| sprint2 | 55.1 |  |  |  | Exhibit List Case Search |  |  |  | 4 | 6 | 2 |  |  |  | 2 |  |  |  | 3 |  |  |  | 2026-09-04
2026-07-15 | sprint2 | 56 | VISAR-7189 | SM | DC | Exhibit Maintenance | High | Deployment Ready |  | 23 | 15 | 10 | 10 |  |  | 12 | 2 | 9 | 2 | 2 |  |  | 11 | 2026-09-18 |  | Y
| sprint2 | 56.1 |  |  |  | New Exhibit Hearing LIst | High | Deployment Ready | [7 empty] | 0 | 0 | 0 |  | 2 |  |  |  | 2026-09-17 |  | Y
2026-07-10 | sprint2 | 57 | VISAR-7185 | NV | DC | Exhibit Management | High | Deployment Ready |  | 8 | 21 | 15 | 8 |  |  | 5 | 0 | 11 |  | 2 |  |  |  | 2026-09-14 |  | Y |  |  | Window deactivated 09/14/26, Deploy into Prod for CT_DEVELOPER only.
2026-07-20 | sprint2 | 57.1 | VISAR-7206 | NV | DC | Exhibit Management Search | Low | Deployment Ready |  | 4 | 8 | 6 |  |  |  | 0.5 | 0 | 0 |  | 2 |  |  |  | 2026-09-14 |  | Y |  |  | Window deactivated 09/14/26, Deploy into Prod for CT_DEVELOPER only.
| sprint2 | 57.2 |  |  |  | Exhibit History |  | UAT Ready |  | 7 | 6 | 6 |  |  |  | 2 | 0 | 0 |  | 2 |  |  | 1 | 2026-09-14 |  |  |  |  | Window deactivated 09/14/26, Deploy into Prod for CT_DEVELOPER only.
| sprint2 | 57.3 |  |  |  | Exhibit Disposition Notice |  | Deployment Ready |  | 7 | 7 | 4 | 4 |  |  | 1 | 1 | 6 |  | 2 |  |  |  | 2026-09-14 |  | Y |  |  | Window deactivated 09/14/26, Deploy into Prod for CT_DEVELOPER only.
| sprint1 | 90 | VISAR-7215 | NV | DC | JBSIS Maintenance |  | UAT Ready |  | 8 | 39 | 21 | 4 |  |  | 10 | 1 | 10 |  | 2 |  | 4 | 7 | 2026-09-04
2026-06-01 | sprint1 | 25 | VISAR-7012 | JL | MU | Priors | High | UAT Ready |  | 16 | 46 | 15 | 20 |  |  | 30 | 34 | 20 | 3 | 3 | 0 | 2 | 55 | 2026-09-08
|  | 53 | VISAR-6315 | SM | BY | Minutes | Medium High | QA Cycle 4 |  | 6 | 120 |  | 117 |  |  | 70 | 31 | 88 | 9 | 4 | 2 | 31 | 95
|  | 33 | VISAR-6907 | NV | CC | FTBCOD Interface | High | On Hold | hold L: drive | 12 | 40 | 16
|  | 34 |  |  | CC | FTBCOD Payment Processor | Medium-High | On Hold | hold L: drive
| sprint1 | 124 | VISAR-7296 | CN | BY | Agency X-Ref Maintenance | Low High | QA Cycle 3 |  | 1 | 4 | 4 | 7 |  |  | 4.5 | 3 | 5 | 1 | 2 | 3 | 0 | 6
| sprint1 | 131 | VISAR-7311 | CN | BY | Court Holidays | Low High | QA Cycle 1 |  | 2 | 24
| sprint1 | 1 | VISAR-7312 | JC | BY | Auto Process Schedule | Low High | QA Cycle 2 |  | 2 | 1 |  | 5 |  |  | 4 | 3 | 11 | 0 | 1 | 14 | 0 | 0
2026-08-28 | sprint1 | 2 | VISAR-7332 | CN | DC | Date of Action | Medium | Deployment Ready |  | 4 | 15 |  |  |  |  | 5 |  | 2 |  | 2 |  | 1 | 1 | 2026-09-16 |  | Y
2026-08-28 |  | 123 | VISAR-7368 | NV | BY | Agency Codes | Medium | On Hold | internal window | 4 | 4
2026-09-03 |  | 147 | VISAR-7382 | SM |  | Unit Codes | Medium | Backlog
|  | 130.1 | VISAR-7388 | JC |  | MOCS Docket Definition | Medium | In Development | hold
| VISAR-7418 | 9 | VISAR-7421 | NV |  | Calendar Report |  |  |  |  | 30
| VISAR-7418 | 9.1 | VISAR-7422 |  |  | Calendar Batch Print
| VISAR-7418 | 9.2 | VISAR-7423 |  |  | Web Browser of generated files
| VISAR-7418 | 10 |  | CN | DC | Calendar Transfer |  | In Development |  | 6 | 12
| VISAR-7418 | 8 | VISAR-7419 |  |  | Calendar List
| VISAR-7418 | 8.1 | VISAR-7420 |  |  | Post-Conviction Worksheet Report
|  |  | VISAR-7417 |  |  | Simple Search
Advanced Search
[18 empty] | Stage 1 | UI & analysis |  | Layout Creation
[18 empty] | Stage 2 | AI migration/ Development |  | Wiring up the layout with real data
[18 empty] | Stage 3 | Unit Testing |  | Testing
[18 empty] | Stage 4 | QA Regression Fixing
[18 empty] | Stage 5 | UAT Defects | More fixing
QA
[18 empty] | Deployment Ready |  |  | F1 | One datawindow section / updateable
Deployed

## Complexity LOE Tracking
Formula
Deployed Window | Grouping | LOE DEV | LOE QA | LOE TOTAL | DEV Actual | QA Actual | TOTAL Actual | DEV Delta | QA Delta | Total Delta |  |  | DEV |  |  |  |  | QA
Purge Duplicates | Low | 32 | 12 | 44 | 40 | 12 | 52 | -8 | 0 | -8 |  | Category | Analysis/Migration | Unit Testing | Defects Resolution | DEV LOE | DEV LOE Hours | QA Testing | Regression Testing | BSA LOE | BSA LOE Hours | Total LOE Hours
Code Entry | Low High | 64 | 40 | 104 | 151 | 71 | 222 | -87 | -31 | -118 | Under estimated | Low | 2 | 1 | 1 | 4 | 32 | 1 | 0.5 | 1.5 | 12 | 44
CodesXref Maintenance | Medium | 96 | 52 | 148 | 22 | 4 | 26 | 74 | 48 | 122 | Over Estimated | Low High | 4 | 2 | 2 | 8 | 64 | 4 | 1 | 5 | 40 | 104
Court Control | Low High | 64 | 40 | 104 | 63 | 19 | 82 | 1 | 21 | 22 |  | Medium | 7 | 2 | 3 | 12 | 96 | 5 | 1.5 | 6.5 | 52 | 148
Error Code | Low | 32 | 12 | 44 | 49 | 23 | 72 | -17 | -11 | -28 |  | Medium high | 11 | 3 | 4 | 18 | 144 | 6 | 2 | 8 | 64 | 208
Event Codes | Low | 32 | 12 | 44 | 68 | 21 | 89 | -36 | -9 | -45 |  | High | 13 | 3 | 5 | 21 | 168 | 7 | 3 | 10 | 80 | 248
Job Error Log | Low | 32 | 12 | 44 | 33 | 31 | 64 | -1 | -19 | -20 |  | Very High | 15 | 4 | 5 | 24 | 192 | 7 | 4 | 11 | 88 | 280
Parm Lookups | Low High | 64 | 40 | 104 | 102 | 31.5 | 133.5 | -38 | 8.5 | -29.5
Sentence Workflow Maintanence | Medium-High | 144 | 64 | 208 | 72 | 34 | 106 | 72 | 30 | 102
SP Registry | Low High | 64 | 40 | 104 | 70 | 21.5 | 91.5 | -6 | 18.5 | 12.5
Bail Schedule | Medium High | 144 | 64 | 208 | 175 | 31 | 206 | -31 | 33 | 2
Violations | Medium | 96 | 52 | 148 | 84 | 24 | 108 | 12 | 28 | 40
Courtroom Setup | Low High | 64 | 40 | 104 | 45 | 14 | 59 | 19 | 26 | 45
Violation Agency X-Ref | Low High | 64 | 40 | 104 | 43 | 17 | 60 | 21 | 23 | 44 | [9 empty] | Category | Dev | QA
Case Payment History | Low High | 64 | 40 | 104 | 61 | 17 | 78 | 3 | 23 | 26 | [9 empty] | Low | 4 | 1.5
Unlock Case | Low | 32 | 12 | 44 | 16 | 4 | 20 | 16 | 8 | 24 | [9 empty] | Low High | 8 | 5
[20 empty] | Medium | 12 | 6.5
[20 empty] | Medium high | 18 | 8
[20 empty] | High | 21 | 10
[20 empty] | Very High | 24 | 11

## Sheet2
Window | Nbr of hits / day
Case Payment History | 203
Bail Schedule / Bail Schedule Review | 45
Bail Schedule Information/Response | 288
Bail Schedule History Report | 2
Unlock Case | 21
Courtroom Setup | 42
Violations | 3
Violation Agency X-Ref | 3

## Sheet1
100 Hrs
Dev
QA
QA
Dev

## Windows
[6 empty] | WINDOW LIST FOUND AT | VISAR-4987 Vision NG - Grouping.xlsx
SUB-MENU | GROUPING |  | MENU | Notes
Activity Maintenance - NOT IN USE |  |  | 1 - ADMIN
Auto Process Schedule | Low High |  | 1 - ADMIN
Date of Action Maintenance | Low |  | 1 - ADMIN
Excel Batch Processing | Medium High |  | 1 - ADMIN
Maintenance Request - NOT IN USE |  |  | 1 - ADMIN
Maintenance Request Qry - NOT IN USE |  |  | 1 - ADMIN
Name Maintenance - NOT IN USE |  |  | 1 - ADMIN
Officer Consolidate | Low High |  | 1 - ADMIN | Deactivated 09/04/2026
Person Delete | Low High |  | 1 - ADMIN
Purge Duplicate Filings | Low |  | 1 - ADMIN
Task Maintenance - NOT IN USE |  |  | 1 - ADMIN
Vlan IP ranges | Low High |  | 1 - ADMIN
Appeal Maintenance - NOT IN USE |  |  | 2 - APPEALS
Appeal Summary - NOT IN USE |  |  | 2 - APPEALS
Case Documents - NOT IN USE |  |  | 2 - APPEALS
Calendar List | Medium |  | 3 - CALENDARING
Calendar Report | Medium |  | 3 - CALENDARING
Calendar Transfer | Low High |  | 3 - CALENDARING
Calendar Transfer Notices | Medium |  | 3 - CALENDARING
Court Closure Transfer | Low High |  | 3 - CALENDARING
Court Trial Transfer | Medium |  | 3 - CALENDARING
Notice of Packaged Hearings | Low High |  | 3 - CALENDARING
Bail Maintenance | Medium High |  | 4 - CASE
Case Backup and Restore | Low High |  | 4 - CASE
Case Maintenance | Very High |  | 4 - CASE
Case Summary | Medium High |  | 4 - CASE
Case Transfer | Low High |  | 4 - CASE
Citation Batches / Batch Entry | Medium High |  | 4 - CASE
Citation Entry | Medium High |  | 4 - CASE
DMV Case Backup/Restore - NOT IN USE |  |  | 4 - CASE
Image Viewer | Medium |  | 4 - CASE
LEA Interface | Low |  | 4 - CASE
Mass Case/Calendar Copy |  |  | 4 - CASE
MCS Interface |  |  | 4 - CASE
Missing Complaint | Medium High |  | 4 - CASE
NCIC Case Initiation | Medium |  | 4 - CASE
Priors | High |  | 4 - CASE
Amnesty |  |  | 5 - COLLECTIONS
Assign Account - NOT IN USE |  |  | 5 - COLLECTIONS
Campaign Maintenance | Low High |  | 5 - COLLECTIONS
Collections | Very High |  | 5 - COLLECTIONS
Collections Campaign Queue | Medium |  | 5 - COLLECTIONS
Collections Person Interface | Medium |  | 5 - COLLECTIONS
Collections Work Queue | Low High |  | 5 - COLLECTIONS | Deactivated 09/04/2026
Collector Maintenance | Low |  | 5 - COLLECTIONS | Deactivated 09/04/2026
Financial Evaluation | Low High |  | 5 - COLLECTIONS
FTBCOD Interface | High |  | 5 - COLLECTIONS
FTBCOD Payment Processor | Medium High |  | 5 - COLLECTIONS
FTBTI Interface | High |  | 5 - COLLECTIONS
FTBTI Payment Processor | Medium High |  | 5 - COLLECTIONS
OCV Payment Processor | High |  | 5 - COLLECTIONS
OCV Return | Low High |  | 5 - COLLECTIONS
Activity Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Bail Sched Mnt - NOT IN USE |  |  | 6 - CONVERSION
Case Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Case Status Maintenance - NOT IN USE |  |  | 6 - CONVERSION
Code Entries XWalk - NOT IN USE |  |  | 6 - CONVERSION
Conversion Reports - NOT IN USE |  |  | 6 - CONVERSION
DMV Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Generic Code XWalk - NOT IN USE |  |  | 6 - CONVERSION
Generic Event ROC Xwalk - NOT IN USE |  |  | 6 - CONVERSION
Missing Complaint Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Person Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Sentence Augmentation - NOT IN USE |  |  | 6 - CONVERSION
Agency Payment | Low High |  | 7 - COUNTER | Deactivated 09/04/2026
Cash Bail Notice (formerly Bail Bond Notice) | Medium High |  | 7 - COUNTER
Bail Entry | Medium High |  | 7 - COUNTER
Batch Payment Entry | Medium High |  | 7 - COUNTER | Deactivated 09/04/2026
Cashier Reconciliation | Low High |  | 7 - COUNTER
Counter Payment | Very High |  | 7 - COUNTER
Multi-Case Payment | Low High |  | 7 - COUNTER
Non-Case Payment | Low |  | 7 - COUNTER
Open Cashier Session | Low |  | 7 - COUNTER
TS Completion | Low High |  | 7 - COUNTER
Victim Restitution Notice | Low High |  | 7 - COUNTER
Admin Minutes Entry | Very High |  | 8 - COURTROOM
Courtroom | Very High |  | 8 - COURTROOM
Courtroom Setup | Low High |  | 8 - COURTROOM
Generic Notice Reporting (Minutes) | Medium High |  | 8 - COURTROOM
Minutes | Medium High |  | 8 - COURTROOM
MOCS | Very High |  | 8 - COURTROOM
Exhibit List | Low High |  | 9 - EXHIBITS
Exhibit Maintenance | Low High |  | 9 - EXHIBITS
Exhibit Management | Low |  | 9 - EXHIBITS
Exhibit Management Search | Low |  | 9 - EXHIBITS |  | Added
Bail Maintenance | Medium High |  | 10 - FISCAL
Case Distribution Override | Medium |  | 10 - FISCAL
Case Payment History | Low High |  | 10 - FISCAL
Check Approval | Medium |  | 10 - FISCAL
Check Maintenance | Medium |  | 10 - FISCAL
Fiscal Case Analysis | Medium High |  | 10 - FISCAL
Fiscal Reports |  |  | 10 - FISCAL
Misapplications/Voids | Medium |  | 10 - FISCAL
Reapply Payment | Low High |  | 10 - FISCAL
Reversals | Medium |  | 10 - FISCAL
Satellite Payment Approval - NOT IN USE |  |  | 10 - FISCAL
Victim Restitution Approval | Low |  | 10 - FISCAL
Summary Judgment | Medium |  | 10 - FISCAL
Bail Distribution Schedule | Medium High |  | 11 - FISCAL MAINTENANCE
Base Distribution Xref | Low High |  | 11 - FISCAL MAINTENANCE
Bondsman / Surety | Medium |  | 11 - FISCAL MAINTENANCE
Chart of Accounts | Low |  | 11 - FISCAL MAINTENANCE
Check Maintenance | Medium |  | 11 - FISCAL MAINTENANCE
Cost of Collections | Low High |  | 11 - FISCAL MAINTENANCE
Fee Distribution Schedule | Low High |  | 11 - FISCAL MAINTENANCE
Fund Maintenance | Low High |  | 11 - FISCAL MAINTENANCE
PA Distribution Mass Update - NOT IN USE |  |  | 11 - FISCAL MAINTENANCE
PA Distribution Schedule | Low High |  | 11 - FISCAL MAINTENANCE
PA Distribution Xref | Low |  | 11 - FISCAL MAINTENANCE
Special Distribution Schedule | Low High |  | 11 - FISCAL MAINTENANCE
VR Distribution Schedule | Low |  | 11 - FISCAL MAINTENANCE
ATP Dashboard | Medium |  | 12 - INTERFACES
Check 21 - Collections - NOT IN USE |  |  | 12 - INTERFACES
Check 21 - Operations - NOT IN USE |  |  | 12 - INTERFACES
Check Auditor/Controller | Low High |  | 12 - INTERFACES
DMV Abstract on Demand | Low |  | 12 - INTERFACES
DMV Admin Transactions | Low High |  | 12 - INTERFACES
DMV Error Cases Report | Medium |  | 12 - INTERFACES
DMV Error Maintenance | Medium High |  | 12 - INTERFACES
DMV Prior Missing Report | Low |  | 12 - INTERFACES
DOJ Data Validation - NOT IN USE |  |  | 12 - INTERFACES
DOJ Interface | High |  | 12 - INTERFACES
JMS Dashboard |  |  | 12 - INTERFACES
Mail Machine Interface - Collections - NOT IN USE |  |  | 12 - INTERFACES
Mail Machine Interface - Operations - NOT IN USE |  |  | 12 - INTERFACES
OneOC - Clerk Review Module | Medium |  | 12 - INTERFACES
JBSIS Audit Report | Medium |  | 13 - JBSIS
JBSIS Maintenance | Medium |  | 13 - JBSIS
JBSIS Report Defn. | Low High |  | 13 - JBSIS
JBSIS Reporting | Medium High |  | 13 - JBSIS
BR/SP Assoc - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
Case Characteristics - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
Courtroom Setup - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
Docket Definition - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
SP Registry - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
WorkFlow/Groups/Scenarios - NOT IN USE |  |  | 14 - MOCS MAINTENANCE
Attorney Maintenance | Medium |  | 15 - PERSON
Interpreters Maintenance | Low High |  | 15 - PERSON
Multi-Person Maintenance | Low High |  | 15 - PERSON
Person Link/Unlink | Medium |  | 15 - PERSON
Person Maintenance | Medium |  | 15 - PERSON
Person Unlink - NOT IN USE |  |  | 15 - PERSON
Professional Consolidation | Low High |  | 15 - PERSON
Professional Maintenance | Low High |  | 15 - PERSON
Sealed Access | Medium High |  | 15 - PERSON
Batch Purge | Medium |  | 16 - RECORDS
Calendar File Location | Medium |  | 16 - RECORDS
Case File Purge | Medium |  | 16 - RECORDS
File Location | Low High |  | 16 - RECORDS
File Request | Low High |  | 16 - RECORDS
File Request Inquiry | Low |  | 16 - RECORDS
File Request Maintenance | Low High |  | 16 - RECORDS
Image dummy pdf viewer - NOT IN USE |  |  | 16 - RECORDS
Image Maintenance | Medium |  | 16 - RECORDS
Image Viewer | Medium |  | 16 - RECORDS
Location History | Low |  | 16 - RECORDS
Metadata Sync Error Report - NOT IN USE |  |  | 16 - RECORDS
Missing Complaints Purge | Medium |  | 16 - RECORDS
File Import - NOT IN USE |  |  | 17 - REPORTS
Monthly Funding Report | Medium |  | 17 - REPORTS
Reports |  |  | 17 - REPORTS
State Prison Abstracts | Medium High |  | 17 - REPORTS
Special Schedule | Low |  | 18 - SCHEDULE MAINTENANCE
Speed Schedule | Low High |  | 18 - SCHEDULE MAINTENANCE
Speed Schedule 2 | Low High |  | 18 - SCHEDULE MAINTENANCE
Advanced Menu Manager | Medium |  | 19 - SECURITY
Basic Menu Manager | Medium |  | 19 - SECURITY
Broadcast Message - NOT IN USE |  |  | 19 - SECURITY
Data Search - NOT IN USE |  |  | 19 - SECURITY
Menu Admin |  |  | 19 - SECURITY
Password Reset - NOT IN USE |  |  | 19 - SECURITY
SCSWEB Security Admin - NOT IN USE |  |  | 19 - SECURITY
Security Admin | Medium High |  | 19 - SECURITY
Unlock Case | Low High |  | 19 - SECURITY
Agency Codes | Low |  | 20 - TABLES
Agency Location X-Ref Maintenance - NOT IN USE |  |  | 20 - TABLES
Agency X-Ref Maintenance | Low High |  | 20 - TABLES
Bail Schedule | Medium High |  | 20 - TABLES
Bail Schedule Review | Medium High |  | 20 - TABLES
Calendar Plan Maintenance | Medium High |  | 20 - TABLES
Code Mover | Low High |  | 20 - TABLES
Codes (Code Entry) | Low High | 3 | 20 - TABLES
Codes X-Ref Maintenance | Low |  | 20 - TABLES
Court Control | Low High | 6 | 20 - TABLES
Court Holidays | Low High |  | 20 - TABLES
Development Log - NOT IN USE |  |  | 20 - TABLES
Docket Code Macro Configuration | Low High |  | 20 - TABLES
Docket Code Macro Maintenance | Medium High |  | 20 - TABLES
Docket Code Macro Mover |  |  | 20 - TABLES
Docket Code Maintenance | Medium High |  | 20 - TABLES
Docket Code Reference | Low |  | 20 - TABLES
Error Codes | Low | 1 | 20 - TABLES
Event Codes | Low | 4 | 20 - TABLES
Fee Schedule | Medium |  | 20 - TABLES
Generic Notice Maintenance | Low High |  | 20 - TABLES
Job Error Log | Low | 2 | 20 - TABLES
Letter Maintenance | Low High |  | 20 - TABLES
PA Schedule Maintenance | Low |  | 20 - TABLES
Parm Lookups | Low High | 5 | 20 - TABLES
RACD night court dates - NOT IN USE |  |  | 20 - TABLES
Sentence Workflow Maintenance | Medium High |  | 20 - TABLES
SP Registry | Low High |  | 20 - TABLES
Unit Codes | Medium |  | 20 - TABLES
Violation Agency X-Ref | Low High |  | 20 - TABLES
Violations | Medium |  | 20 - TABLES
Warrant Control Maintenance - NOT IN USE |  |  | 20 - TABLES
File Mappings |  |  | 20 - TABLES
Appeal Activity Maintenance |  |  | 20 - TABLES
Pending Warrant Review | Medium |  | 21 - WARRANTS
Warrant Image Viewer (CTS) |  |  | 21 - WARRANTS
Warrant Maintenance | Medium |  | 21 - WARRANTS
Warrant Maintenance (CTS) (Warrant Signal Audit) | Medium |  | 21 - WARRANTS
Warrant Reports |  |  | 21 - WARRANTS
Warrant XML Viewer (CTS) | Low High |  | 21 - WARRANTS